## Cover
Level of Effort
Generated: | June 10, 2026
Solution: | Tmpwz9A4Npl
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Stakeholders | Single business unit (~50 users) | ~120 employees — pre-sales + delivery + sales teams as primary users | Up to 50 internal users | 50-200 internal users | 200+ internal users | Amatra has ~120 employees; all pre-sales consultants are day-1 users
AWS Services in Scope | Core compute + storage only | Bedrock, Lambda, API Gateway, DynamoDB, S3, Cognito — 6 named services | 1-3 AWS services | 4-6 AWS services | 7+ AWS services | Claude model integration via Bedrock adds AI/ML complexity
Regions / Geographies | Single AWS region (us-east-1) | Single region: us-west-2 (all customer data resident in US) | 1 region | 2 regions | 3+ regions | us-west-2 mandated; no multi-region failover in scope for MVP
Integration Points | No external system integrations | Okta to Cognito identity migration; Google Workspace doc import; Word/Excel/PPT template pipeline | 0 integrations | 1-3 integrations | 4+ integrations | Okta migration and legacy template carry-over are critical-path integrations
Environments | Dev + Prod only | Dev / Staging / Prod (3 environments) | Dev + Prod | Dev + Staging + Prod | Dev + Staging + Prod + DR | Staging required for QA gating before each phase go-live
Artifact Types Generated | Single artifact type | 7 artifact types: discovery questionnaire + solution briefing + SoW + infra costs + detailed design + implementation guide + Terraform automation | 1-2 artifact types | 3-5 artifact types | 6+ artifact types | Full automation pipeline spans pre-sales and delivery phases
Compliance Frameworks | No formal compliance requirements | SOC 2 Type II + GDPR-aligned data handling + US data residency | None | SOC 2 Type II only | SOC 2 Type II + GDPR + data residency controls | Security & Compliance Lead must sign off; adds controls design and audit evidence
Async Job Duration | Synchronous API calls only | Long-running generation jobs: 30-60 min per engagement; must not drop | Synchronous (< 30 s) | Short async (< 5 min) | Long async (30-60 min) | Requires durable async orchestration (Step Functions or SQS + Lambda chaining)
Legacy Artifact Templates | No existing templates to migrate | Word/Excel/PowerPoint templates in Google Workspace; Okta user records to migrate | No migration | Template migration only | Template + identity migration | Template parsing and pipeline integration adds significant implementation scope
Availability / SLA Target | Best-effort (no SLA) | 99.9% platform availability; artifacts pass QA on first review >= 90% of the time | Best-effort | 99.5% uptime | 99.9% uptime + QA >= 90% first-pass | High availability and quality gates drive additional testing and monitoring scope

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Baseline multiplier for stakeholder interviews and current-state review across all discovery tasks
Planning & Design | planning_factor | 1.2 | Elevated multiplier reflecting complex AWS serverless architecture with AI/ML integration and compliance requirements
Development & Implementation | development_factor | 1.3 | Higher multiplier for large-scope greenfield build spanning 6 AWS services and 7 artifact-type pipelines
Testing & Validation | testing_factor | 1.2 | Elevated for rigorous QA gating (>= 90% first-pass rate SLA) plus security and compliance validation
Deployment | deployment_factor | 1 | Standard multiplier for production rollout; phased delivery (Phase 1 MVP by 2026-09-30; Phase 2 by 2026-12-15)
Training & Enablement | training_factor | 1 | Standard multiplier for knowledge transfer to pre-sales consultants and delivery teams
Management | management_factor | 1 | Standard multiplier for project management and technical leadership overhead (10% of engineering hours)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Kickoff meeting with CTO (Exec Sponsor) and VP Engineering to align on scope and success criteria | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Week 1 activity
Discovery | Project Kickoff | Kickoff technical deep-dive with Head of Solutions and Security & Compliance Lead | Solution Architect | 8 | 1 | 8 | 225 | 1800 |  | Parallel to PM kickoff session
Discovery | Current State Assessment | Document current manual artifact workflow (3-week cycle) and identify bottlenecks across pre-sales and delivery teams | Solutions Engineer | 24 | 1 | 24 | 200 | 4800 |  | Interview pre-sales consultants and delivery team
Discovery | Current State Assessment | Inventory existing Word/Excel/PowerPoint templates and Google Workspace artifacts and document structure and variability | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 |  | Required for template migration scope
Discovery | Requirements Gathering | Conduct structured interviews with Head of Solutions to define artifact quality standards and QA criteria | Solution Architect | 24 | 1 | 24 | 225 | 5400 |  | Critical for >= 90% first-pass QA SLA definition
Discovery | Requirements Gathering | Gather technical requirements for async job orchestration (30-60 min) and per-user/global usage limits and admin governance | Solution Architect | 16 | 1 | 16 | 225 | 3600 |  | CTO + VP Eng input required
Discovery | Requirements Gathering | Define Okta to Cognito migration requirements and document user groups and admin governance model | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 |  | Security & Compliance Lead involvement
Discovery | Gap Analysis | Identify gaps between current manual process and target automated platform capabilities | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Current State Assessment | Output feeds Planning phase
Discovery | Cloud Readiness Assessment | Assess AWS account structure and evaluate Bedrock model availability in us-west-2 and Claude model selection | Cloud Engineer | 16 | 1 | 16 | 200 | 3200 |  | Verify Bedrock Claude regional availability
Discovery | AI/ML Data Assessment | Evaluate sample client briefs and existing artifacts to establish Bedrock prompt engineering baseline and quality benchmarks | ML/AI Engineer | 24 | 1 | 24 | 275 | 6600 |  | Sample set of 10-20 historical engagements
Discovery | Compliance Assessment | Conduct SOC 2 Type II scoping exercise and identify GDPR data flows and US data residency controls required | Security Engineer | 24 | 1 | 24 | 225 | 5400 |  | Security & Compliance Lead to co-lead
Discovery | Risk Assessment | Identify top risks (async job reliability; AI output quality; Okta migration data loss; SOC 2 timeline) and mitigation strategies | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Output: risk register
Discovery | Assessment Report | Document all findings and architecture recommendations and phased delivery roadmap (Phase 1 MVP + Phase 2 + GA) | Technical Writer | 16 | 1 | 16 | 125 | 2000 | All Discovery tasks | Delivered to CTO for phase gate approval
Planning & Design | Detailed Architecture Design | Design end-to-end serverless architecture (Bedrock, Lambda, API Gateway, DynamoDB, S3, Cognito) and produce architecture decision records | Solution Architect | 40 | 1.2 | 48 | 225 | 10800 | Assessment Report | Primary design deliverable
Planning & Design | AWS Landing Zone Setup | Configure AWS account structure with IAM roles/policies and enable CloudTrail and AWS Config for SOC 2 audit trail in us-west-2 | Cloud Engineer | 32 | 1.2 | 38 | 200 | 7600 | Detailed Architecture Design | Foundation for all environments
Planning & Design | Async Orchestration Design | Design durable async job architecture for 30-60 min generation jobs; evaluate Step Functions vs SQS+Lambda chaining and document state machine | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | Detailed Architecture Design | Critical path — all generation workflows depend on this
Planning & Design | Bedrock / AI Integration Design | Design prompt engineering framework for 7 artifact types and define Claude model parameters and token budgets per artifact | ML/AI Engineer | 40 | 1.2 | 48 | 275 | 13200 | Detailed Architecture Design | Drives implementation of Bedrock invocation layer
Planning & Design | Data Model Design | Design DynamoDB table schemas for solution state and usage tracking and design S3 object key taxonomy for artifact storage | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | Detailed Architecture Design | Supports per-user and global usage limit enforcement
Planning & Design | Security Baseline Design | Design IAM least-privilege policies and KMS key management for S3/DynamoDB encryption and WAF rules for API Gateway | Security Engineer | 32 | 1.2 | 38 | 225 | 8550 | Detailed Architecture Design | SOC 2 control mapping required
Planning & Design | Identity & Access Design | Design Cognito user pool configuration and plan Okta to Cognito migration approach and define admin group and governance controls | Security Engineer | 24 | 1.2 | 29 | 225 | 6525 | AWS Landing Zone Setup | Okta migration design critical for auth continuity
Planning & Design | CI/CD Pipeline Design | Design GitHub Actions / AWS CodePipeline CI/CD for multi-environment deployment with automated testing gates | DevOps Engineer | 24 | 1.2 | 29 | 200 | 5800 | AWS Landing Zone Setup | Enables consistent phased delivery
Planning & Design | Monitoring & Observability Design | Design CloudWatch dashboards and define alarms for async job failures and SLA monitoring for 99.9% availability and QA pass-rate tracking | Cloud Engineer | 16 | 1.2 | 19 | 200 | 3800 | Detailed Architecture Design | Feeds operational runbooks
Planning & Design | Artifact Template Pipeline Design | Design ingestion pipeline for Word/Excel/PPT legacy templates into automated generation workflow and define template schema | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Bedrock / AI Integration Design | Preserves existing Amatra branding and format standards
Planning & Design | Design Documentation | Produce as-designed architecture diagrams and architecture decision records and data-flow and sequence diagrams | Technical Writer | 24 | 1.2 | 29 | 125 | 3625 | All Planning tasks | Delivered to VP Engineering for sign-off
Development & Implementation | Bedrock Integration Layer | Implement Lambda functions for Bedrock Claude API invocation and prompt templates for all 7 artifact types and error handling and retries | ML/AI Engineer | 80 | 1.3 | 104 | 275 | 28600 | Bedrock / AI Integration Design | Core AI generation capability
Development & Implementation | Async Job Orchestration | Implement Step Functions state machine for durable 30-60 min generation jobs with status polling and webhook notifications | Solutions Engineer | 64 | 1.3 | 83 | 200 | 16600 | Async Orchestration Design | Must handle job failures and retries without data loss
Development & Implementation | API Gateway & Lambda API Layer | Implement REST API via API Gateway + Lambda for all platform endpoints (submit brief / poll status / retrieve artifacts / admin controls) | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | Async Orchestration Design | Supports Sales team portal integration
Development & Implementation | DynamoDB State & Usage Layer | Implement DynamoDB tables for solution state tracking and per-user/global monthly usage limits and admin enforcement logic | Cloud Engineer | 40 | 1.3 | 52 | 200 | 10400 | Data Model Design | Usage cap enforcement required for go-live
Development & Implementation | S3 Artifact Storage Layer | Implement S3 bucket policies and presigned URL generation for artifact delivery and lifecycle rules for retention management | Cloud Engineer | 32 | 1.3 | 42 | 200 | 8400 | AWS Landing Zone Setup | All generated artifacts stored in S3
Development & Implementation | Cognito Authentication & Admin | Configure Cognito user pool and implement admin group and governance controls and integrate with API Gateway authorizer | Security Engineer | 32 | 1.3 | 42 | 225 | 9450 | Identity & Access Design | Replaces Okta as identity provider
Development & Implementation | Okta to Cognito User Migration | Execute user record migration from Okta to Cognito and validate all accounts and update application auth endpoints | Solutions Engineer | 40 | 1.3 | 52 | 200 | 10400 | Cognito Authentication & Admin | Zero-downtime migration required; rollback plan needed
Development & Implementation | Artifact Template Pipeline | Build ingestion and parsing pipeline for Word/Excel/PPT templates and integrate with Bedrock generation prompts for format-consistent output | Solutions Engineer | 56 | 1.3 | 73 | 200 | 14600 | Artifact Template Pipeline Design | 7 artifact types across 3 format families
Development & Implementation | Pre-Sales Artifact Pipeline Phase 1 | Implement generation pipeline for Phase 1 artifacts: discovery questionnaire + solution briefing + SoW + infra cost model | ML/AI Engineer | 64 | 1.3 | 83 | 275 | 22825 | Bedrock Integration Layer | Target: delivered by 2026-09-30
Development & Implementation | Delivery Artifact Pipeline Phase 2 | Implement generation pipeline for Phase 2 artifacts: detailed design + implementation guide + Terraform automation scripts | ML/AI Engineer | 64 | 1.3 | 83 | 275 | 22825 | Development & Implementation Pre-Sales Artifact Pipeline Phase 1 | Target: delivered by 2026-12-15
Development & Implementation | CI/CD Pipeline Build | Implement multi-environment CI/CD with automated unit and integration test gates and deployment to dev/staging/prod | DevOps Engineer | 48 | 1.3 | 62 | 200 | 12400 | CI/CD Pipeline Design | Required for phased and reproducible deployments
Development & Implementation | Security Hardening | Implement IAM least-privilege policies and KMS encryption for S3/DynamoDB and WAF rules and enable GuardDuty and Security Hub | Security Engineer | 40 | 1.3 | 52 | 225 | 11700 | Security Baseline Design | SOC 2 evidence collection begins here
Development & Implementation | Monitoring & Observability Build | Implement CloudWatch dashboards and alarms and async job failure alerting and SLA availability and QA pass-rate dashboards | Cloud Engineer | 32 | 1.3 | 42 | 200 | 8400 | Monitoring & Observability Design | Required for 99.9% SLA validation
Development & Implementation | Configuration & Runbook Documentation | Document all Lambda configurations and API contracts and DynamoDB schemas and environment variable management | Technical Writer | 32 | 1.3 | 42 | 125 | 5250 | All Development tasks | Input to SOC 2 documentation set
Testing & Validation | Test Plan Development | Create comprehensive test plan covering functional / integration / performance / security and compliance validation | QA Engineer | 16 | 1.2 | 19 | 150 | 2850 | All Development tasks | Must include QA >= 90% first-pass acceptance criteria
Testing & Validation | Functional Testing Phase 1 Artifacts | Test generation pipelines for all Phase 1 artifact types against sample client briefs and validate output quality | QA Engineer | 40 | 1.2 | 48 | 150 | 7200 | Development & Implementation Pre-Sales Artifact Pipeline Phase 1 | Gate for Phase 1 go-live
Testing & Validation | Functional Testing Phase 2 Artifacts | Test Delivery and Terraform automation artifact generation pipelines against sample briefs | QA Engineer | 32 | 1.2 | 38 | 150 | 5700 | Development & Implementation Delivery Artifact Pipeline Phase 2 | Gate for Phase 2 go-live
Testing & Validation | Integration Testing Okta Cognito | Validate Okta to Cognito migration and test all auth flows and admin governance controls in staging | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Development & Implementation Okta to Cognito User Migration | Auth continuity is critical-path risk
Testing & Validation | Integration Testing Template Pipeline | Test Word/Excel/PPT template ingestion and format-consistent output for all 7 artifact types | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Development & Implementation Artifact Template Pipeline | Validates Amatra branding preservation
Testing & Validation | Async Job Reliability Testing | Load-test async generation jobs at concurrent volumes and validate 30-60 min job completion without dropping under stress | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Development & Implementation Async Job Orchestration | Validates core reliability SLA
Testing & Validation | Performance & Scalability Testing | Validate system under load and simulate 24 concurrent engagements per quarter and confirm API Gateway and Lambda scaling behaviour | Solutions Engineer | 16 | 1.2 | 19 | 200 | 3800 | All Development tasks | Validates tripled proposal throughput target
Testing & Validation | Security Testing | Perform security validation: IAM policy review and KMS encryption verification and WAF rule testing and GuardDuty alert validation | Security Engineer | 24 | 1.2 | 29 | 225 | 6525 | Development & Implementation Security Hardening | SOC 2 evidence artefact
Testing & Validation | Compliance Validation | Validate SOC 2 Type II controls implementation and GDPR data flow controls and US data residency verification and produce audit evidence | Security Engineer | 24 | 1.2 | 29 | 225 | 6525 | Testing & Validation Security Testing | Security & Compliance Lead sign-off required
Testing & Validation | UAT Pre-Sales Consultants | Coordinate UAT sessions with Head of Solutions and pre-sales consultants and validate artifact quality and usability | Project Manager | 16 | 1.2 | 19 | 175 | 3325 | Testing & Validation Functional Testing Phase 1 Artifacts | Validates >= 90% first-pass QA target
Testing & Validation | UAT Delivery Team | Coordinate UAT with Delivery Consulting team for Phase 2 artifacts and Terraform automation | Project Manager | 12 | 1.2 | 14 | 175 | 2450 | Testing & Validation Functional Testing Phase 2 Artifacts | Downstream consumer sign-off
Testing & Validation | Defect Resolution | Triage and resolve defects identified during all testing streams and execute regression testing | Solutions Engineer | 40 | 1.2 | 48 | 200 | 9600 | All Testing tasks | 10-15% defect-resolution buffer included
Testing & Validation | Test Results Report & Sign-Off | Document test results and produce sign-off report for CTO phase gate approval | QA Engineer | 8 | 1.2 | 10 | 150 | 1500 | All Testing tasks | Required for each phase gate
Deployment | Go-Live Planning Phase 1 MVP | Plan Phase 1 cutover approach and define rollback procedures and confirm 2026-09-30 production readiness checklist | Project Manager | 8 | 1 | 8 | 175 | 1400 | Testing & Validation UAT Pre-Sales Consultants | CTO sign-off required before cutover
Deployment | Production Deployment Phase 1 MVP | Deploy Phase 1 generation platform to production (us-west-2) and validate all endpoints and async job flows | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Deployment Go-Live Planning Phase 1 MVP | Phase 1 deadline: 2026-09-30
Deployment | Production Deployment Phase 2 | Deploy Phase 2 delivery artifact and Terraform automation pipelines to production | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Deployment Production Deployment Phase 1 MVP | Phase 2 deadline: 2026-12-15
Deployment | GA Rollout Planning | Plan General Availability rollout to all ~120 internal users in Q1 2027 with communications and onboarding plan | Project Manager | 8 | 1 | 8 | 175 | 1400 | Deployment Production Deployment Phase 2 | Must complete before 2027-01-31 client renewal
Deployment | Hypercare Support Phase 1 (8 weeks) | Provide 8-week post-go-live hypercare for Phase 1 MVP with triage and performance tuning and escalation support | Support Engineer | 80 | 1 | 80 | 150 | 12000 | Deployment Production Deployment Phase 1 MVP | Large complexity = 8-week hypercare per guidance
Deployment | Hypercare Support Phase 2 (4 weeks) | Provide 4-week post-go-live hypercare for Phase 2 delivery pipeline with triage and issue resolution | Support Engineer | 40 | 1 | 40 | 150 | 6000 | Deployment Production Deployment Phase 2 | Phase 2 additional support period
Deployment | Optimization Recommendations | Document AI prompt optimization opportunities and Lambda cold-start tuning and DynamoDB capacity planning recommendations | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Deployment Hypercare Support Phase 1 (8 weeks) | Input to post-GA steady-state operations
Deployment | Project Closeout | Project retrospective and lessons learned and final artifact delivery and transition to steady-state operations team | Project Manager | 8 | 1 | 8 | 175 | 1400 | All Deployment tasks | Formal engagement close with CTO
Training & Enablement | Training Material Development | Create user guides for pre-sales consultants covering brief submission and artifact retrieval and quality review workflows | Technical Writer | 32 | 1 | 32 | 125 | 4000 | Deployment Production Deployment Phase 1 MVP | Materials must cover all 7 artifact types
Training & Enablement | Administrator Training | Train VP Engineering team on platform administration: Cognito user management and usage limit controls and CloudWatch monitoring | Trainer | 16 | 1 | 16 | 150 | 2400 | Deployment Production Deployment Phase 1 MVP | Cognito admin group governance
Training & Enablement | Pre-Sales Consultant Training | Conduct hands-on training sessions for pre-sales team on brief submission workflow and artifact review | Trainer | 24 | 1 | 24 | 150 | 3600 | Training & Enablement Training Material Development | Target: all consultants trained before GA
Training & Enablement | Delivery Team Enablement | Enable Delivery Consulting team on Phase 2 artifacts and Terraform automation outputs | Trainer | 16 | 1 | 16 | 150 | 2400 | Deployment Production Deployment Phase 2 | Enables 40% consulting-hours-reduction target
Training & Enablement | Train-the-Trainer | Enable Head of Solutions to onboard future pre-sales hires independently | Trainer | 8 | 1 | 8 | 150 | 1200 | Training & Enablement Pre-Sales Consultant Training | Reduces long-term dependency on external support
Management | Technical Leadership | Quarterback technical oversight across all phases; AWS architecture governance and quality review | Solution Architect |  | 1 |  | 225 |  |  | 10% of engineering task hours
Management | Project Management | End-to-end project coordination and stakeholder reporting to CTO and VP Engineering and risk and issue management | Project Manager |  | 1 |  | 175 |  |  | 10% of engineering task hours
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -15000 | AWS Partner Network (APN) Advanced Tier credit applied to professional services for solution architecture and implementation of AWS-native platform (Bedrock, Lambda, API Gateway, DynamoDB, S3, Cognito)
AWS AI/ML Specialization Credit | -5000 | AWS Generative AI competency partner credit for Amazon Bedrock implementation and Claude model integration; applicable to APN partners with validated AI/ML practice
Implementation Volume Discount | -10000 | Strategic engagement discount for multi-phase engagement (Phase 1 MVP + Phase 2 + GA rollout) totalling Year 1 build commitment of $300K-$450K
New Workload Incentive | -5000 | AWS new workload launch incentive for greenfield serverless platform on AWS with net-new Bedrock consumption commitment
TOTAL |  | Total professional services cost minus all AWS Partner and engagement credits applied in Year 1 only; infrastructure credits (Reserved Instances and Savings Plans) are in infrastructure-costs.csv