## Cover
Level of Effort
Generated: | August 16, 2026
Solution: | Tmpjxtoe4F5
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
AWS Accounts | Single AWS account (dev only) | Multi-account OU hierarchy (Security / Infra / Workloads / Sandbox / Suspended) | 1-3 accounts | 4-10 accounts | 10+ accounts | Greenfield; Account Factory for Terraform (AFT) used for automated account vending
Regions / Geographies | Single AWS region | us-east-1 (primary) + us-east-2 (DR/secondary) | 1 region | 2 regions | 3+ regions | All services and guardrails deployed and governed in both regions
Environments | Single environment (prod) | Development / Non-Production / Production (3 environments) | 1 environment | 2 environments | 3+ environments | Separate OU paths for prod and non-prod workloads
OU Complexity | Flat OU structure | 7-OU hierarchy (Root / Security / Infrastructure / Workloads-Prod / Workloads-NonProd / Sandbox / Suspended) | 2-3 OUs | 4-6 OUs | 7+ OUs | Designed for future BU / acquisition expansion without redesign
Networking Complexity | Basic VPC per account | Hub-and-spoke via Transit Gateway; VPC IPAM; Network Firewall; centralised egress; VPN on-premises link | VPC only | TGW single-region | TGW multi-region + Firewall + IPAM | On-premises connectivity method (VPN vs Direct Connect) to be confirmed in discovery
Security & Compliance Frameworks | No formal compliance framework | AWS FSBP mandatory; NIST 800-53 / SOC 2 / HIPAA to be confirmed with client security team | 1 framework | 2 frameworks | 3+ frameworks | Additional frameworks confirmed during Phase 1 discovery
IaC Coverage | Manual console configuration | >=95% IaC coverage (Terraform + AFT); CI/CD pipeline tooling TBD | Partial IaC | Terraform modules | Full IaC + AFT pipeline + CI/CD | Zero manual console changes in production at go-live
Integrations / Source Systems | No external integrations | Centralised monitoring (CloudWatch / Security Hub / GuardDuty); SNS alerting; third-party SIEM TBD | 1-2 integrations | 3-5 integrations | 5+ integrations | Third-party SIEM / ticketing integration to be scoped post-discovery

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Stakeholder interviews; current-state review; requirements documentation; compliance framework confirmation
Planning | planning_factor | 1.2 | Detailed OU / network / security architecture; Terraform module design; IaC standards definition; architecture documentation
Development | development_factor | 1.3 | Control Tower deployment; OU structure; SCPs / RCPs; IAM Identity Center; networking build (TGW / IPAM / Firewall); AFT pipeline; security automation (Weeks 1-12)
Testing | testing_factor | 1 | End-to-end landing zone validation; SCP enforcement tests; account vending tests; network flow tests; security posture validation
Deployment | deployment_factor | 1 | Production go-live; runbook delivery; administrator and security team training; hypercare support (4 weeks post go-live)
Management | management_factor | 1 | Project management and technical leadership overhead — calculated as 10% of total engineering task hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Project kickoff meeting and stakeholder alignment; confirm RACI and engagement leads | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Stakeholder identification required at kick-off
Discovery | Current State Assessment | Confirm greenfield status; document existing on-premises context and connectivity requirements | Solution Architect | 16 | 1 | 16 | 250 | 4000 |  | AWS-certified architect rate applied
Discovery | Requirements Gathering | Conduct stakeholder interviews; document OU design requirements; confirm compliance frameworks (NIST / SOC 2 / HIPAA) | Solution Architect | 24 | 1 | 24 | 250 | 6000 |  | Compliance framework confirmation gates SCP design
Discovery | Cloud Readiness Assessment | Assess team cloud maturity; identify skills gaps; confirm IaC tooling preferences (Terraform / CDK) | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 |  | Drives training scope in Deployment phase
Discovery | Network Discovery | Confirm on-premises connectivity topology; validate IP address space and IPAM supernet (10.0.0.0/8) | Network Engineer | 16 | 1 | 16 | 200 | 3200 |  | VPN vs Direct Connect decision required
Discovery | Security & Compliance Scoping | Document security requirements; confirm compliance frameworks; map mandatory tags; define data classification policy | Security Engineer | 16 | 1 | 16 | 225 | 3600 |  | Security-certified specialist rate applied
Discovery | Risk Assessment | Identify project risks (scope / compliance / connectivity) and define mitigation strategies | Project Manager | 8 | 1 | 8 | 175 | 1400
Discovery | Discovery Report | Document findings; produce architecture recommendation memo and phased project plan | Solution Architect | 16 | 1 | 16 | 250 | 4000 |  | Gates Planning phase
Planning | Detailed OU & Account Architecture | Design 7-OU hierarchy; map Security / Infra / Workloads / Sandbox / Suspended OUs; define account naming convention | Solution Architect | 24 | 1.2 | 28.8 | 250 | 7200 | Discovery Report | Drives AFT customisations
Planning | Control Tower Design | Design Control Tower configuration; select managed guardrails; define landing zone manifest for both regions | Solution Architect | 24 | 1.2 | 28.8 | 250 | 7200 | Detailed OU & Account Architecture
Planning | Network Architecture Design | Design hub-and-spoke Transit Gateway topology; define VPC IPAM plan; design Network Firewall policy; plan centralised egress | Network Engineer | 32 | 1.2 | 38.4 | 200 | 7680 | Network Discovery | RFC 1918 /20 per spoke VPC
Planning | Security Architecture Design | Design SCP / RCP policy set; data perimeter controls; Security Hub standard selection; GuardDuty configuration | Security Engineer | 32 | 1.2 | 38.4 | 225 | 8640 | Security & Compliance Scoping
Planning | IaC Module Design | Design Terraform module structure for AFT; define repo layout; design CI/CD pipeline approach | Solutions Engineer | 32 | 1.2 | 38.4 | 200 | 7680 | Control Tower Design | IaC coverage target >=95%
Planning | IAM Identity Center Design | Design SSO permission sets; define identity source (existing IdP or native); map group-to-account assignments | Security Engineer | 16 | 1.2 | 19.2 | 225 | 4320 | Detailed OU & Account Architecture | IdP source to be confirmed with client
Planning | Monitoring & Alerting Architecture | Design centralised CloudWatch structure; define Security Hub aggregation; design SNS alert routing | Solutions Engineer | 16 | 1.2 | 19.2 | 200 | 3840 | Security Architecture Design | Third-party SIEM integration TBD
Planning | Architecture Documentation | Produce as-designed architecture diagrams and detailed design document | Technical Writer | 24 | 1.2 | 28.8 | 125 | 3600 | All planning tasks | Delivered as pre-build baseline
Development | Control Tower Deployment | Deploy AWS Control Tower in us-east-1; enrol us-east-2 as governed region; configure landing zone manifest | Cloud Engineer | 32 | 1.3 | 41.6 | 200 | 8320 | Control Tower Design | Weeks 1-4
Development | OU Structure Implementation | Implement 7-OU hierarchy in AWS Organizations; configure OU policies and tagging baseline | Cloud Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | Control Tower Deployment
Development | SCP & RCP Implementation | Deploy all SCPs (root deny; region restriction; CloudTrail/Config lock; MFA); deploy RCP data perimeter controls | Security Engineer | 24 | 1.3 | 31.2 | 225 | 7020 | Security Architecture Design | Critical path — gates workload account creation
Development | IAM Identity Center Setup | Configure IAM Identity Center; set up permission sets; integrate identity source; validate SSO login flow | Security Engineer | 24 | 1.3 | 31.2 | 225 | 7020 | IAM Identity Center Design
Development | Log Archive & Audit Accounts | Provision Log Archive and Audit/Security Tooling accounts; configure centralised CloudTrail org trail (both regions) | Cloud Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | OU Structure Implementation
Development | AWS Config Deployment | Enable AWS Config in both regions across all accounts; configure recording and delivery to Log Archive | Cloud Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | Log Archive & Audit Accounts
Development | AFT Pipeline Setup | Deploy Account Factory for Terraform (AFT); configure AFT pipeline; create initial account request templates | Solutions Engineer | 32 | 1.3 | 41.6 | 200 | 8320 | IaC Module Design | Enables <30 min account vending SLA
Development | Sandbox Account Vending Test | Vend first sandbox account via AFT; validate guardrail enrolment; confirm SCP inheritance | Solutions Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | AFT Pipeline Setup | Validates end-to-end vending pipeline
Development | Transit Gateway Deployment | Deploy Transit Gateway in us-east-1 and us-east-2; configure inter-region peering; define route tables | Network Engineer | 32 | 1.3 | 41.6 | 200 | 8320 | Network Architecture Design | Weeks 5-8
Development | VPC IPAM Configuration | Configure VPC IPAM; allocate 10.0.0.0/8 supernet; define regional pools and /20 delegation per spoke | Network Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | Transit Gateway Deployment
Development | Network Firewall Deployment | Deploy AWS Network Firewall in Network Hub account (us-east-1 + us-east-2); configure north-south and east-west inspection policies | Network Engineer | 32 | 1.3 | 41.6 | 200 | 8320 | Transit Gateway Deployment
Development | Hub VPC Build | Build Network Hub VPCs in both regions; configure centralised NAT Gateway egress; attach to Transit Gateway | Cloud Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | Transit Gateway Deployment
Development | Spoke VPC Templates | Create Terraform modules for spoke VPCs (/20); deploy sample Dev and Prod spoke VPCs; validate TGW routing | Solutions Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | Hub VPC Build
Development | On-Premises VPN Connectivity | Configure Site-to-Site VPN between Network Hub account and on-premises gateway (both regions); validate routing | Network Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | Hub VPC Build | Direct Connect upgrade path documented for future
Development | Security Hub Deployment | Enable Security Hub in all accounts and both regions; configure FSBP standard; aggregate findings to Audit account | Security Engineer | 16 | 1.3 | 20.8 | 225 | 4680 | Log Archive & Audit Accounts | Weeks 9-12
Development | GuardDuty Deployment | Enable GuardDuty org-wide in both regions; configure delegated administrator in Audit account | Security Engineer | 16 | 1.3 | 20.8 | 225 | 4680 | Security Hub Deployment
Development | AWS Config Rules & Conformance Packs | Deploy Config rules aligned to FSBP; configure conformance pack for chosen compliance framework | Cloud Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | AWS Config Deployment | Additional frameworks (NIST/SOC2/HIPAA) added post-confirmation
Development | CloudTrail Lake Configuration | Configure CloudTrail Lake in Audit account; enable event data stores; create sample queries for security investigations | Cloud Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | Log Archive & Audit Accounts
Development | Tagging Enforcement & Budgets | Implement tag policies via Organizations; configure AWS Cost Explorer; set per-account Budgets alerts at 80% and 100% | Solutions Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | OU Structure Implementation | Tags: Environment / Owner / CostCenter / Project / DataClassification
Development | Centralised Monitoring Setup | Configure centralised CloudWatch dashboards in Shared Services account; configure SNS alert routing; document alerting runbook | Solutions Engineer | 16 | 1.3 | 20.8 | 200 | 4160 | Monitoring & Alerting Architecture | Third-party SIEM integration out of scope (TBD post go-live)
Development | AFT Customisation & Account Templates | Build AFT account customisations for Prod / NonProd / Sandbox OUs; test full account vending pipeline end-to-end | Solutions Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | AFT Pipeline Setup | Validates <30 min vending SLA
Development | CI/CD Pipeline Finalization | Finalise IaC CI/CD pipeline (tooling TBD with client); configure branch protection and deployment gates | Solutions Engineer | 24 | 1.3 | 31.2 | 200 | 6240 | IaC Module Design | Tooling confirmation required from client
Testing | Test Plan Development | Create comprehensive landing zone test plan covering SCP enforcement; account vending; network flows; security findings | QA Engineer | 16 | 1 | 16 | 150 | 2400 | All development tasks
Testing | SCP & Guardrail Testing | Attempt policy-violating actions to validate SCP deny statements (root usage; region restriction; CloudTrail disable) | Security Engineer | 24 | 1 | 24 | 225 | 5400 | SCP & RCP Implementation
Testing | Account Vending Validation | Vend 2 workload accounts (1 prod / 1 non-prod) via AFT; validate guardrail enrolment; confirm < 30 min SLA | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | AFT Customisation & Account Templates | Satisfies hard deadline: 2 workload accounts by Month 3
Testing | Network Flow Testing | Validate spoke-to-spoke traffic through firewall; validate centralised egress; test VPN connectivity and routing | Network Engineer | 16 | 1 | 16 | 200 | 3200 | All networking development tasks
Testing | Security Posture Validation | Review Security Hub findings; confirm zero critical FSBP findings in production; validate GuardDuty threat detection | Security Engineer | 16 | 1 | 16 | 225 | 3600 | Security Hub Deployment
Testing | Disaster Recovery Smoke Test | Validate Control Tower governance in us-east-2; test failover routing via TGW inter-region peering | Cloud Engineer | 8 | 1 | 8 | 200 | 1600 | All development tasks
Testing | UAT Coordination | Coordinate client UAT sessions; facilitate sign-off against agreed success metrics | Project Manager | 16 | 1 | 16 | 175 | 2800 | Test Plan Development | Client stakeholder availability required
Testing | Defect Resolution | Triage and resolve issues identified during testing and UAT | Solutions Engineer | 24 | 1 | 24 | 200 | 4800 | All testing tasks | 10-20% contingency buffer included
Testing | Test Results Report | Document test results; record success metrics achieved; obtain formal client sign-off | QA Engineer | 8 | 1 | 8 | 150 | 1200 | All testing tasks
Deployment | Go-Live Planning | Finalise go-live checklist; confirm rollback procedures; schedule production cutover call | Project Manager | 8 | 1 | 8 | 175 | 1400 | UAT sign-off
Deployment | Production Go-Live | Execute final production validation; confirm all accounts enrolled in Control Tower at go-live | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Go-Live Planning | Success metric: 100% accounts enrolled
Deployment | Runbook Development | Create operational runbooks for: account vending; SCP updates; Security Hub triage; network changes; incident response | Technical Writer | 32 | 1 | 32 | 125 | 4000 | All development tasks
Deployment | As-Built Documentation | Produce final as-built architecture document; update design docs to reflect production configuration | Technical Writer | 24 | 1 | 24 | 125 | 3000 | Production Go-Live
Deployment | Administrator Training | Train cloud/infrastructure team on Control Tower; IAM Identity Center; AFT account vending; Config and Security Hub operations | Trainer | 24 | 1 | 24 | 150 | 3600 | Runbook Development
Deployment | Knowledge Transfer Sessions | Conduct knowledge transfer for security team on SCP management; Security Hub; GuardDuty; CloudTrail Lake queries | Trainer | 16 | 1 | 16 | 150 | 2400 | Administrator Training
Deployment | Hypercare Support | Provide 4-week post go-live hypercare support; triage issues; assist with first workload onboarding | Support Engineer | 40 | 1 | 40 | 150 | 6000 | Production Go-Live | 4-week hypercare = Medium/Large baseline
Deployment | Optimization Recommendations | Document cost optimization and architecture improvement opportunities (Savings Plans; TGW routing; Direct Connect evaluation) | Solution Architect | 16 | 1 | 16 | 250 | 4000 | Hypercare Support | AWS-certified architect rate applied
Deployment | Project Closeout | Project retrospective; lessons learned; deliver final project report | Project Manager | 8 | 1 | 8 | 175 | 1400 | All deployment tasks
Management | Technical Leadership | Quarterback technical oversight across all phases (Discovery through Project Closeout) | EO Quarterback |  | 1 |  | 225 |  |  | 10% of all engineering task hours
Management | Project Management | Project coordination, status reporting, stakeholder communication, and risk management | EO Project Manager |  | 1 |  | 175 |  |  | 10% of all engineering task hours
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -10000 | AWS Partner Network (APN) Advanced Tier credit applied to professional services for solution architecture, Control Tower design, and implementation on this greenfield engagement
APN Migration Acceleration Credit | -5000 | AWS Migration Acceleration Program (MAP) Assess/Mobilize credit applicable to greenfield landing zone deployments; subject to APN MAP eligibility confirmation with AWS account team
Implementation Volume Discount | -3000 | Volume discount on professional services for strategic greenfield engagement; applicable when total billable hours exceed 600
TOTAL |  | Total professional services cost minus AWS Partner and MAP credits (Year 1 only); infrastructure run-rate costs are itemised separately in infrastructure-costs.csv