## Cover
Level of Effort
Generated: | June 08, 2026
Solution: | Tmpaucs1Jvw
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Monthly Active Users | Single department ~100 MAU | Starting at 0; projections for 100 / 10K / 100K MAU | Up to 100 MAU | Up to 10,000 MAU | 100,000+ MAU | Cost modeling required for all three tiers for investor conversations
Content Catalog | Single-genre catalog ~1000 tracks | Existing FlutterFlow / Firebase catalog with titles + metadata; lyric and transcript files where available | Up to 2,000 tracks | Up to 50,000 tracks | 500,000+ tracks | Firebase data-migration execution is out of scope; catalog is read via API
AI/ML Models in Scope | 1 baseline recommendation model | Content-intelligence classifier + preference-learning model + mood-to-content matcher + playlist generator + retraining pipeline | 1 model | 3-5 models | 10+ models | Medium complexity — 5 interacting ML components built from scratch
AWS Environments | Single prod environment | Dev + Staging environments; production deployment out of scope for this engagement | 1 environment | 2 environments | 3+ environments | Production deployment deferred to a later phase
Integration Points / APIs | 1 downstream consumer | FlutterFlow mobile app calling secured REST API; no frontend modification required | 1 integration | 2-3 integrations | 5+ integrations | All API contracts must be documented for independent operation
Data Schemas | Basic metadata schema | User preference vectors + content metadata + mood taxonomy; defined and documented in Phase 1 | Basic schema | Intermediate schema with versioning | Full ontology with multi-language support | Mood taxonomy and data schema design are explicit Phase 1 deliverables
Compliance / Security | Standard AWS best practices | Dedicated AWS account provided by customer; security controls under existing or new dedicated security account | Standard IAM + encryption | NIST CSF aligned | FedRAMP / SOC 2 ready | No specific compliance framework stated; AWS security baseline assumed
Knowledge Transfer | Single handoff session | Two formal knowledge-transfer sessions + full operational runbook delivery | 1 session | 2 sessions | 4+ sessions | Runbooks and API documentation required for independent operation post-engagement

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery & Architecture Planning | discovery_factor | 1 | Baseline — requirements workshop + architecture design + data schema definition + tiered cost modeling
Content Intelligence Development | content_intelligence_factor | 1.2 | Elevated complexity — lyric/transcript NLP pipeline + audio analysis + catalog enrichment at ingest time
Recommendation Engine Development | recommendation_factor | 1.3 | Highest complexity — preference-learning model + mood-to-content matching + playlist generation + retraining pipeline
API Service Layer Development | api_factor | 1.1 | Moderate complexity — authenticated REST endpoints + feedback capture + API documentation
Testing & Validation | testing_factor | 1 | End-to-end functional + integration + performance testing across all pipeline components
Integration & Deployment | deployment_factor | 1 | End-to-end validation + production-readiness checks + knowledge-transfer sessions + final documentation delivery
Management | management_factor | 1 | Project management and technical leadership overhead (10% of engineering hours)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery & Architecture Planning | Project Kickoff | Project kickoff meeting — stakeholder alignment and delivery cadence agreement | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Requires CEO and nClouds delivery team availability
Discovery & Architecture Planning | Requirements Workshop | Facilitate requirements workshop covering mood taxonomy + content classification + recommendation goals + API contracts | Solution Architect | 24 | 1 | 24 | 225 | 5400 | Project Kickoff | Lilly Goyah + SMEs must attend
Discovery & Architecture Planning | Current State Assessment | Assess existing Firebase catalog schema + FlutterFlow app call patterns + available lyric/transcript coverage | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Project Kickoff | Feeds data schema design
Discovery & Architecture Planning | AWS Architecture Design | Design multi-service AWS architecture — SageMaker + Lambda + API Gateway + S3 + DynamoDB + EventBridge | Solution Architect | 32 | 1 | 32 | 225 | 7200 | Requirements Workshop | Produces architecture diagrams for SOW
Discovery & Architecture Planning | Data Schema Definition | Define user preference vector schema + content metadata schema + mood taxonomy (emotion and worship style labels) | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Requirements Workshop | Explicit Phase 1 deliverable
Discovery & Architecture Planning | Tiered AWS Cost Modeling | Model AWS consumption costs at 100 / 10K / 100K MAU tiers for investor and accelerator conversations | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | AWS Architecture Design | Must cover all three growth scenarios
Discovery & Architecture Planning | Risk Assessment | Identify risks — data sparsity for new catalog + cold-start for new users + AWS funding approval dependency | Project Manager | 8 | 1 | 8 | 175 | 1400 | Requirements Workshop | Informs contingency planning
Discovery & Architecture Planning | Phase 1 Documentation | Document architecture decisions + data schemas + mood taxonomy + cost model in deliverable package | Technical Writer | 16 | 1 | 16 | 125 | 2000 | AWS Architecture Design | Phase 1 formal deliverable for customer sign-off
Content Intelligence Development | Emotion & Mood Taxonomy | Finalize emotion / mood / worship-style label set and annotation guidelines for classifiers | ML/AI Engineer | 16 | 1.2 | 19 | 250 | 4750 | Phase 1 Documentation | Taxonomy drives all downstream classification work
Content Intelligence Development | Lyric & Transcript Ingestion Pipeline | Build AWS pipeline to ingest lyric and podcast transcript text from catalog and pre-process for NLP classification | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Emotion & Mood Taxonomy | Ingests from Firebase-backed catalog via API; migration execution out of scope
Content Intelligence Development | NLP Emotion Classifier | Train and deploy NLP model on SageMaker to classify emotion / mood / theme from lyric and transcript text | ML/AI Engineer | 40 | 1.2 | 48 | 250 | 12000 | Lyric & Transcript Ingestion Pipeline | Medium-complexity custom model; pre-trained base model fine-tuned on labeled data
Content Intelligence Development | Audio Analysis Pipeline | Build audio-feature extraction pipeline (valence / energy / worship style) using SageMaker custom model | ML/AI Engineer | 32 | 1.2 | 38 | 250 | 9500 | Emotion & Mood Taxonomy | Sonic characteristics beyond text-derived tags; extends classification depth
Content Intelligence Development | Catalog Enrichment Service | Build catalog-enrichment Lambda triggered at artist/podcast upload time to apply classification outputs to metadata | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | NLP Emotion Classifier, Audio Analysis Pipeline | Runs at ingest time; does not require frontend change
Content Intelligence Development | Classification Endpoint (Internal) | Expose internal classification endpoint consumed by catalog enrichment pipeline and tested end-to-end | Solutions Engineer | 16 | 1.2 | 19 | 200 | 3800 | Catalog Enrichment Service | Internal endpoint only; public-facing endpoint built in API Development phase
Recommendation Engine Development | Preference Data Schema & Ingestion | Implement DynamoDB schema for user preference vectors and ingestion path for mood inputs + genre selections + interaction events | Solutions Engineer | 16 | 1.3 | 21 | 200 | 4200 | Phase 1 Documentation | Listening-history storage analysis deferred to later phase; schema designed for forward compatibility
Recommendation Engine Development | Preference Learning Model | Build and train collaborative-filtering / content-based hybrid preference-learning model on SageMaker | ML/AI Engineer | 48 | 1.3 | 62 | 250 | 15500 | Preference Data Schema & Ingestion | Cold-start strategy required for new users with no history
Recommendation Engine Development | Mood-to-Content Matching Algorithm | Develop algorithm correlating mood-state input with multi-attribute content vectors from catalog enrichment | ML/AI Engineer | 32 | 1.3 | 42 | 250 | 10500 | Preference Learning Model, Content Intelligence Development | Bridges mental-health and faith use case — core differentiator
Recommendation Engine Development | Playlist Generation Service | Build playlist-generation service incorporating preference weighting + session context + feedback signals | Solutions Engineer | 32 | 1.3 | 42 | 200 | 8400 | Mood-to-Content Matching Algorithm | Lambda-based service; output is ordered list of track/podcast IDs
Recommendation Engine Development | Model Retraining Pipeline | Implement SageMaker Pipeline for scheduled model retraining as interaction data accumulates | ML/AI Engineer | 24 | 1.3 | 31 | 250 | 7750 | Playlist Generation Service | Retraining cadence configurable; initial cadence weekly
API Service Layer Development | API Design & Contract Documentation | Define and document all REST API contracts — user profile/session + classification + playlist + feedback endpoints | Solution Architect | 16 | 1.1 | 18 | 225 | 4050 | Recommendation Engine Development | API contracts must be documented for independent operation per brief
API Service Layer Development | API Gateway & Lambda Setup | Provision API Gateway + Lambda authorizer + IAM roles + WAF rules for secured public-facing API layer | Solutions Engineer | 24 | 1.1 | 26 | 200 | 5200 | API Design & Contract Documentation | Dedicated AWS account provided by customer
API Service Layer Development | User Profile & Session Endpoint | Implement authenticated user-profile and session management endpoint with JWT / Cognito integration | Solutions Engineer | 16 | 1.1 | 18 | 200 | 3600 | API Gateway & Lambda Setup | FlutterFlow calls this without frontend modification
API Service Layer Development | Content Classification Endpoint | Expose secured content-classification endpoint callable at artist/podcast upload time | Solutions Engineer | 16 | 1.1 | 18 | 200 | 3600 | API Gateway & Lambda Setup, Content Intelligence Development | Public-facing version of internal Phase 2 endpoint
API Service Layer Development | Playlist Generation Endpoint | Expose playlist-generation endpoint accepting mood and user context; return ordered track/podcast list | Solutions Engineer | 16 | 1.1 | 18 | 200 | 3600 | API Gateway & Lambda Setup, Playlist Generation Service | Core consumer-facing endpoint
API Service Layer Development | Listening History & Feedback Capture | Implement feedback-capture endpoint (play / skip / like / dislike) feeding preference-learning loop via EventBridge + SQS | Solutions Engineer | 16 | 1.1 | 18 | 200 | 3600 | Playlist Generation Endpoint, Model Retraining Pipeline | Feeds the continuous improvement loop
API Service Layer Development | API Security Hardening | Implement API throttling + request validation + secrets management (AWS Secrets Manager) + security review | Security Engineer | 16 | 1.1 | 18 | 225 | 4050 | All API Layer Endpoints | Security controls under existing or new dedicated security account
Testing & Validation | Content Intelligence Testing | Validate classifier accuracy against holdout set + catalog enrichment pipeline end-to-end functional test | QA Engineer | 16 | 1 | 16 | 150 | 2400 | Classification Endpoint (Internal) | Accuracy metrics documented in deliverable
Testing & Validation | Recommendation Engine Testing | Validate preference-learning model accuracy + playlist generation relevance + retraining pipeline execution | QA Engineer | 24 | 1 | 24 | 150 | 3600 | Model Retraining Pipeline | Bias and fairness review included
Testing & Validation | API Layer Testing | End-to-end API functional + integration tests; simulate FlutterFlow call patterns against all endpoints | QA Engineer | 16 | 1 | 16 | 150 | 2400 | API Security Hardening | Validates no frontend modification required
Testing & Validation | Performance & Load Testing | Test API performance under simulated load for 100 / 10K MAU scenarios; document latency and throughput baselines | QA Engineer | 16 | 1 | 16 | 150 | 2400 | API Layer Testing | Feeds tiered cost model accuracy
Integration & Deployment | End-to-End Validation | Validate full pipeline — content upload to classification to catalog enrichment to mood input to playlist generation to feedback capture | Solutions Engineer | 24 | 1 | 24 | 200 | 4800 | Testing & Validation | Validates against FlutterFlow call patterns from brief
Integration & Deployment | Operational Runbook Development | Create comprehensive operational runbooks covering all services — deployment + scaling + retraining + incident response | Technical Writer | 24 | 1 | 24 | 125 | 3000 | End-to-End Validation | Required for independent operation per brief
Integration & Deployment | Knowledge Transfer Session 1 | Conduct KT session 1 — architecture overview + pipeline operations + retraining procedure for engineering team | Solution Architect | 8 | 1 | 8 | 225 | 1800 | Operational Runbook Development | Two formal KT sessions required per brief
Integration & Deployment | Knowledge Transfer Session 2 | Conduct KT session 2 — API operations + security runbook + monitoring + incident-response walkthrough | Solutions Engineer | 8 | 1 | 8 | 200 | 1600 | Knowledge Transfer Session 1 | Customer technical team must attend both sessions
Integration & Deployment | Final Deliverable Package | Compile and deliver complete as-built documentation — architecture diagrams + data schemas + API contracts + runbooks | Technical Writer | 16 | 1 | 16 | 125 | 2000 | Operational Runbook Development, Both KT Sessions | All deliverables documented for independent operation
Integration & Deployment | Project Closeout | Project retrospective + lessons learned + AWS funding reconciliation + final invoice preparation | Project Manager | 8 | 1 | 8 | 175 | 1400 | Final Deliverable Package | Net-10 invoicing after project kickoff per brief
Management | Technical Leadership | Quarterback technical oversight across all phases — architecture review, escalation, quality assurance | EO Quarterback |  | 1 |  | 225 |  |  | 10% of all engineering task hours
Management | Project Management | Project coordination + status reporting + stakeholder communication + schedule management across all phases | EO Project Manager |  | 1 |  | 175 |  |  | 10% of all engineering task hours
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Funding Credit | -25000 | AWS Partner Funding Portal (AFP) credit covering 100% of professional services fee; nClouds does not begin work until AWS funding approval is confirmed. Eligibility: nClouds APN partner program — AI/ML solution build on AWS for qualified ISV customer ANP Streaming.
TOTAL | $0.00 | Total professional services cost fully offset by AWS Partner Funding — net customer cost is $0.00 on professional services. Customer remains responsible for all AWS service-consumption fees incurred by the delivered solution.