## Cover
Project Plan
Generated: | June 08, 2026
Solution: | Tmpjphst02H
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff Meeting | 1 day | 2026-03-19 | 2026-03-19 | None | Project Manager | Not Started
Phase 1 | AWS Account Access Provisioning | 1 day | 2026-03-20 | 2026-03-20 | Project Kickoff Meeting | Solutions Engineer | Not Started
Phase 1 | Requirements Workshop | 1 day | 2026-03-23 | 2026-03-23 | AWS Account Access Provisioning | Solution Architect | Not Started
Phase 1 | Firebase Catalog API & Mood Schema Review | 2 days | 2026-03-23 | 2026-03-24 | Requirements Workshop | Solution Architect | Not Started
Phase 1 | Current-State Assessment (Firebase/FlutterFlow) | 3 days | 2026-03-24 | 2026-03-26 | Firebase Catalog API & Mood Schema Review | Solution Architect | Not Started
Phase 1 | AWS Architecture Design & Decision Record | 5 days | 2026-03-26 | 2026-04-01 | Current-State Assessment (Firebase/FlutterFlow) | Solution Architect | Not Started
Phase 1 | Mood Taxonomy & Annotation Guidelines | 3 days | 2026-03-26 | 2026-03-30 | Requirements Workshop | Solution Architect | Not Started
Phase 1 | Data Schema Package Definition | 3 days | 2026-04-01 | 2026-04-03 | AWS Architecture Design & Decision Record | Solution Architect | Not Started
Phase 1 | Tiered AWS Cost Model (100 / 10K / 100K MAU) | 2 days | 2026-04-03 | 2026-04-07 | Data Schema Package Definition | Solution Architect | Not Started
Phase 1 | Risk Register | 1 day | 2026-04-07 | 2026-04-07 | Tiered AWS Cost Model (100 / 10K / 100K MAU) | Project Manager | Not Started
Phase 1 | Phase 1 Documentation Package Review & Sign-Off | 3 days | 2026-04-07 | 2026-04-09 | Risk Register | Project Manager | Not Started
Phase 2 | Lyric & Transcript Ingestion Pipeline Development | 5 days | 2026-04-09 | 2026-04-15 | Phase 1 Documentation Package Review & Sign-Off | Solutions Engineer | Not Started
Phase 2 | NLP Emotion/Mood/Theme Classifier Training & Deployment | 5 days | 2026-04-15 | 2026-04-21 | Lyric & Transcript Ingestion Pipeline Development | ML/AI Engineer | Not Started
Phase 2 | Audio Feature Extraction Pipeline Deployment | 5 days | 2026-04-15 | 2026-04-21 | Lyric & Transcript Ingestion Pipeline Development | ML/AI Engineer | Not Started
Phase 2 | Catalog Enrichment Service Development | 5 days | 2026-04-21 | 2026-04-27 | NLP Emotion/Mood/Theme Classifier Training & Deployment | Solutions Engineer | Not Started
Phase 2 | Internal Classification Endpoint Testing | 3 days | 2026-04-27 | 2026-04-29 | Catalog Enrichment Service Development | QA Engineer | Not Started
Phase 3 | User Preference Vector DynamoDB Schema | 3 days | 2026-04-21 | 2026-04-23 | Phase 1 Documentation Package Review & Sign-Off | Solutions Engineer | Not Started
Phase 3 | Preference-Learning Model Development & Deployment | 7 days | 2026-04-23 | 2026-04-30 | User Preference Vector DynamoDB Schema | ML/AI Engineer | Not Started
Phase 3 | Mood-to-Content Matching Algorithm Deployment | 5 days | 2026-04-29 | 2026-05-05 | Preference-Learning Model Development & Deployment | ML/AI Engineer | Not Started
Phase 3 | Playlist Generation Service (Lambda) Development | 5 days | 2026-05-05 | 2026-05-11 | Mood-to-Content Matching Algorithm Deployment | Solutions Engineer | Not Started
Phase 3 | Automated Model Retraining Pipeline (SageMaker Pipelines) | 5 days | 2026-05-05 | 2026-05-11 | Preference-Learning Model Development & Deployment | ML/AI Engineer | Not Started
Phase 4 | REST API Contract Documentation | 3 days | 2026-05-06 | 2026-05-08 | Phase 1 Documentation Package Review & Sign-Off | Solution Architect | Not Started
Phase 4 | API Gateway & Cognito Auth Implementation | 5 days | 2026-05-08 | 2026-05-14 | REST API Contract Documentation | Solutions Engineer | Not Started
Phase 4 | User Profile & Session Endpoint Development | 2 days | 2026-05-14 | 2026-05-15 | API Gateway & Cognito Auth Implementation | Solutions Engineer | Not Started
Phase 4 | Content Classification Endpoint Development | 2 days | 2026-05-14 | 2026-05-15 | API Gateway & Cognito Auth Implementation | Solutions Engineer | Not Started
Phase 4 | Playlist Generation Endpoint Development | 2 days | 2026-05-15 | 2026-05-18 | User Profile & Session Endpoint Development | Solutions Engineer | Not Started
Phase 4 | Feedback Capture Endpoint Development | 2 days | 2026-05-15 | 2026-05-18 | Playlist Generation Endpoint Development | Solutions Engineer | Not Started
Phase 4 | API Security Hardening (WAF / Throttling / Secrets Manager) | 3 days | 2026-05-18 | 2026-05-20 | Feedback Capture Endpoint Development | Solutions Engineer | Not Started
Phase 5 | End-to-End Pipeline Validation | 3 days | 2026-05-20 | 2026-05-22 | API Security Hardening (WAF / Throttling / Secrets Manager) | QA Engineer | Not Started
Phase 5 | Performance & Load Testing (100 / 10K MAU) | 2 days | 2026-05-22 | 2026-05-25 | End-to-End Pipeline Validation | QA Engineer | Not Started
Phase 5 | Operational Runbooks Development | 4 days | 2026-05-20 | 2026-05-25 | End-to-End Pipeline Validation | Solutions Engineer | Not Started
Phase 5 | Knowledge Transfer Session 1 (Architecture & Pipelines) | 1 day | 2026-05-25 | 2026-05-25 | Operational Runbooks Development | Solution Architect | Not Started
Phase 5 | Knowledge Transfer Session 2 (API & Security Runbook) | 1 day | 2026-05-26 | 2026-05-26 | Knowledge Transfer Session 1 (Architecture & Pipelines) | Solution Architect | Not Started
Phase 5 | Final Deliverable Package Compilation | 2 days | 2026-05-26 | 2026-05-27 | Knowledge Transfer Session 2 (API & Security Runbook) | Project Manager | Not Started
Phase 5 | Project Closeout & AWS Funding Reconciliation | 1 day | 2026-05-28 | 2026-05-28 | Final Deliverable Package Compilation | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Project Kickoff Complete | 2026-03-19 | Phase 1 | Kickoff meeting completed; stakeholder alignment confirmed; AWS account access granted to nClouds; delivery cadence agreed | Project Manager | Not Started
MS-002 | Architecture Approved | 2026-04-09 | Phase 1 | Phase 1 Documentation Package (architecture, data schemas, mood taxonomy, cost model, risk register) delivered and formally accepted by ANP | Solution Architect | Not Started
MS-003 | Content Intelligence Live | 2026-04-29 | Phase 2 | NLP classifier, audio analysis pipeline, and catalog enrichment service deployed and tested in Dev; internal classification endpoint validated | ML/AI Engineer | Not Started
MS-004 | Recommendation Engine Live | 2026-05-11 | Phase 3 | Preference-learning model, mood-to-content matcher, playlist generation service, and retraining pipeline deployed and tested in Dev | ML/AI Engineer | Not Started
MS-005 | API Layer Live | 2026-05-20 | Phase 4 | All five REST API endpoints deployed, secured with Cognito auth, documented, and validated against FlutterFlow call patterns | Solution Architect | Not Started
MS-006 | End-to-End Validated | 2026-05-25 | Phase 5 | Full pipeline validated against FlutterFlow call patterns; performance test confirms ≤2s playlist generation latency at 100 MAU; no critical security findings | QA Engineer | Not Started
MS-007 | Handover Complete | 2026-05-28 | Phase 5 | Both knowledge-transfer sessions conducted with confirmed attendance; final deliverable package accepted by Lilly Goyah; project formally closed | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | nClouds PM | nClouds Architect | nClouds Engineer | nClouds QA | ANP CEO | ANP Tech Lead | ANP SME
Project Kickoff & Stakeholder Alignment | R | C | I | I | C | C | I
Project Schedule & Status Reporting | A | C | I | I | I | C | I
Requirements Workshop Facilitation | A | R | C | I | C | C | R
Current-State Assessment (Firebase/FlutterFlow) | C | R | C | I | I | A | C
AWS Architecture Design & Decision Record | I | A | C | I | I | C | I
Mood Taxonomy & Data Schema Definition | C | A | R | I | C | C | R
Tiered AWS Cost Model (100 / 10K / 100K MAU) | C | A | R | I | C | I | I
Risk Register Development | A | C | R | I | I | C | I
Phase 1 Documentation Package Sign-Off | I | I | I | I | A | R | C
Lyric & Transcript Ingestion Pipeline | I | C | A | C | I | I | I
NLP Emotion/Mood/Theme Classifier Training | I | A | R | C | I | I | I
Audio Feature Extraction Pipeline | I | C | A | C | I | I | I
Catalog Enrichment Service Development | I | C | A | C | I | I | I
Internal Classification Endpoint Testing | C | C | R | A | I | C | I
User Preference Vector DynamoDB Schema | I | A | R | C | I | C | I
Preference-Learning Model Development | I | A | R | C | I | I | I
Mood-to-Content Matching Algorithm | I | A | R | C | I | I | I
Playlist Generation Service Development | I | C | A | C | I | I | I
Automated Model Retraining Pipeline | I | C | A | C | I | I | I
REST API Contract Documentation | I | A | R | I | I | C | I
API Gateway & Cognito Auth Implementation | I | C | A | C | I | C | I
REST API Endpoint Development | I | C | A | C | I | I | I
API Security Hardening | I | C | A | C | I | C | I
Functional & Integration Testing | C | C | C | A | I | C | I
Performance & Load Testing | C | C | C | A | I | C | I
End-to-End Validation | C | C | R | A | I | C | I
Operational Runbooks Development | C | C | A | C | I | C | I
Knowledge Transfer Sessions | C | A | R | I | C | R | R
Deliverable Review & Acceptance | I | I | I | I | A | R | C
AWS Funding Portal Submission & Reconciliation | A | C | I | I | C | I | I
Project Closeout & Final Invoice | A | I | I | I | C | I | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | Responsible - Does the work
A | Accountable - Ultimate ownership
C | Consulted - Provides input
I | Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders; nClouds full team; ANP CEO, Tech Lead, and SMEs | Launch project; align on scope, RACI, and governance; confirm AWS account access and delivery cadence | Project Manager | 2026-03-19 (2 hours)
Weekly Status Call | Weekly | nClouds Project Manager; ANP Tech Lead; nClouds team leads | Review progress against plan; surface blockers and decisions; update risk register | Project Manager | Mondays 10:00 AM ET
Requirements Workshop | Once | Solution Architect; ANP CEO; ANP Tech Lead; ANP SMEs | Deep-dive on mood taxonomy, content classification goals, recommendation requirements, and API contract objectives | Solution Architect | 2026-03-23 (3 hours)
Mid-Point Stakeholder Review | Once | nClouds PM; Solution Architect; ANP CEO; ANP Tech Lead | Review Phase 1 and Phase 2 completion; confirm design decisions; address scope or timeline risks before Phase 3 | Project Manager | 2026-04-29 (1 hour)
Design Review & Sign-Off Workshop | Once | Solution Architect; ANP Tech Lead; ANP CEO | Review and formally accept Phase 1 Documentation Package including architecture and mood taxonomy | Solution Architect | 2026-04-07 (2 hours)
Phase Gate Review | End of each phase | Project Manager; ANP Tech Lead; ANP CEO | Review phase completion criteria; confirm deliverable acceptance; approve next phase commencement | Project Manager | 2026-04-09, 2026-04-29, 2026-05-11, 2026-05-20 (1 hour each)
UAT Session | Once | ANP Tech Lead; ANP CEO; nClouds QA Engineer | Validate end-to-end system in Staging against FlutterFlow call patterns; confirm UAT sign-off record | QA Engineer | 2026-05-22 (3 hours)
Knowledge Transfer Session 1 | Once | Solution Architect; ANP Tech Lead; ANP engineering team | Architecture overview; content intelligence pipeline operations; recommendation engine; retraining procedure walkthrough | Solution Architect | 2026-05-25 (3 hours)
Knowledge Transfer Session 2 | Once | Solution Architect; ANP Tech Lead; ANP security responsible | API operations; security runbook; CloudWatch dashboard; incident-response scenarios | Solution Architect | 2026-05-26 (3 hours)
Hypercare Incident Escalation | As required | nClouds PM; ANP Tech Lead; nClouds Engineer on call | Notify and resolve functional issues directly traceable to engagement deliverables during 2-week hypercare window | Project Manager | Within 4 business hours of detection
Project Closeout Meeting | Once | nClouds PM; ANP CEO; ANP Tech Lead | Formal project closure; final deliverable package acceptance; AWS funding reconciliation; lessons learned | Project Manager | 2026-05-28 (1 hour)