## Slide 1
Project Closeout
Amatra Agentic Orchestration Platform
Marcus Patel | 2026-04-30
Notes: *Opening Talking Points:*
- Welcome stakeholders: Sarah Lin (CRO), Marcus Patel (Director Pre-Sales Engineering), Daniel Park (Head of Delivery Operations), and CTO
- This presentation formally closes the 12-week Amatra Agentic Orchestration Platform engagement
- We will cover what was delivered, performance against targets, benefits realised, lessons learned, and next steps
- End with the formal acceptance sign-off process

## Slide 2
Slide 2: Executive Summary
Duration: 12 weeks delivered on schedule (Q2 2026)
Budget: $250,000 net professional services, on budget
Go-Live: Week 11 — production live as planned
Executive Demo: Delivered to Sarah Lin (CRO) on schedule
Agents Deployed: 5 Strands agents on Bedrock AgentCore Runtime
Validation Pass Rate: 96% first-attempt across all 12 artifact types
End-to-End Latency: Avg 47 minutes per 12-artifact bundle (<60 min target)
Throughput Capacity: 200 solutions/month unlocked at <$5 model spend
Effort Reduction: 90% reduction — 8 hrs to <1 hr per engagement
CTO Sign-Off: Cognito user pool approved; production deployment authorised
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- The engagement met all nine success metrics defined in the SOW — a clean delivery with no open critical defects
- Budget of $250,000 net PS (after $25,000 APN credits) was held; no change requests were raised during the engagement
- Go-live on Week 11 (Tuesday Pacific Time, low-activity window) proceeded without rollback; smoke tests passed first attempt
- The 96% first-attempt validation pass rate exceeded the 95% target, meaning only 4 in 100 artifacts needed a retry cycle
- Average end-to-end latency of 47 minutes across the five UAT test cases comfortably beats the 60-minute SLA
- The 90% effort reduction — the primary business objective — is already being observed in the first post-go-live sprint
*Budget Breakdown:*
- Professional Services: $275,000 list → $250,000 net after $25,000 APN partner credits
- AWS Activate infrastructure credit ($5,000) applied to Year 1 cloud costs
- Year 1 cloud infrastructure on track at $28,308 net (vs. $33,308 list)
- AWS Business Support at $6,000/year activated post-go-live
- Total Year 1 net investment: $284,308 — within approved budget envelope
*Timeline Specifics:*
- M1 Kickoff: Week 1 — all stakeholders confirmed, CTO sign-off process initiated
- M2 Architecture Approved: Week 3 — CTO and Marcus Patel signed architecture design
- M3 Foundation Live: Week 4 — Cognito auth, API Gateway scaffold, DynamoDB quota schema operational
- M4 All Agents Registered: Week 8 — all 5 agents on AgentCore Runtime, Docker image in ECR
- M5 Platform Integration Complete: Week 9 — CLI, 11 Lambda routes, GitHub commit, CloudWatch integrated
- M6 Validation Green: Week 11 — all 12 artifact types passing; green CloudWatch baseline confirmed
- M7 Go-Live: Week 11 — production deployment complete; executive demo delivered to Sarah Lin
- M8 Handover Complete: Week 12 — all 26 deliverables transferred; formal acceptance signed
- M9 Hypercare End: Week 16 (target) — 4-week hypercare period concludes; BAU operations begin

## Slide 3
Slide 3: Solution Architecture
Amatra Agentic Orchestration Platform
Agent & Orchestration Layer
  Five Strands agents on AgentCore Runtime
  Sonnet 4.6 generation, Haiku 4.5 validation
  Up to 3 retries per artifact via EO Validator
Platform & Security Layer
  Cognito JWT auth; 11 API Gateway routes
  DynamoDB quota enforcement; S3 artifact store
  WAF, CloudTrail audit, Secrets Manager
CLI & Observability Layer
  14-subcommand pip-installable CLI
  CloudWatch dashboards; per-phase token metrics
  GitHub PAT-based artifact commit pipeline
Notes: *Talking Points:*
- The architecture is fully serverless — no EC2, no VPC, no container clusters to operate day-to-day
- Walk through the architecture left-to-right: CLI/API → Cognito auth → Lambda → AgentCore Runtime → Bedrock models → S3 → GitHub
- Every consultant request is authenticated before any Lambda is invoked; quota is checked atomically before Bedrock spend begins
- The eof-tools converter library (~30 Python modules) was baked into the agent container image — no rewrite, no risk, proven conversion for all 12 artifact types
*Architecture Decisions Made:*
- Serverless-first: Lambda + AgentCore Runtime abstracts agent lifecycle; scales to 200 solutions/month without ops overhead
- Graded artifact delivery policy in EO Validator allows partial bundle commits for resilience
- API Gateway HTTP API v2 chosen over REST API for lower latency and cost; JWT authoriser eliminates custom auth Lambda
- DynamoDB on-demand capacity confirmed cost-effective at PoC throughput; provisioned capacity can be evaluated at 200 solutions/month steady state
*Presales Alignment:*
- Architecture matches Solution Briefing specification exactly
- Services deployed: Cognito, API Gateway, Lambda, DynamoDB, S3, Bedrock AgentCore Runtime, ECR, Secrets Manager, CloudWatch, WAF, CloudTrail
- No scope additions beyond presales commitment; eof-tools integration preserved as existing PREDICTif asset
*Component Counts:*
- 5 Strands agents (Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator)
- 11 JWT-protected Lambda route handlers
- 14 CLI subcommands (auth login/logout, solution generate/status/list, artifact download, admin usage, etc.)
- 3 DynamoDB tables (Users, Solutions, GlobalQuota)
- 3 S3 prefixes (raw/, converted/, terraform/)

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Detailed Design Document | Multi-agent graph, AWS architecture, security design | `/delivery/detailed-design.md`
Implementation Guide | Step-by-step deployment and configuration procedures | `/delivery/implementation-guide.md`
Project Plan | Timeline, milestones, resource allocation, RACI | `/delivery/project-plan.csv`
Test Plan & Results | Test cases, pass/fail outcomes, UAT sign-off | `/delivery/test-plan.csv`
Infrastructure as Code | Terraform modules for all 5 core AWS services | `/delivery/scripts/terraform/`
Configuration Guide | Environment parameters for dev, staging, prod | `/delivery/configuration.csv`
Operational Runbooks | Agent recovery, quota reset, PAT rotation, image update | `/delivery/runbook.md`
As-Built Architecture & API Reference | OpenAPI 3.0 spec, CLI command reference, operator guide | `/delivery/api-reference.md`
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- All 26 formal deliverables defined in the SOW have been reviewed and accepted by the named acceptance authority
- The 8 rows above represent the primary documentation and automation deliverables — the full list includes deployed systems, training sessions, and the formal acceptance artefact
- All documentation is committed to the agreed GitHub repository and accessible via the artifact download CLI subcommand
*Full Deliverable Acceptance Status:*
- Deliverables 1–7 (Phase 1 documents + foundation infrastructure): Accepted by Marcus Patel / CTO by Week 4
- Deliverables 8–17 (agents, Docker pipeline, CLI, Lambda routes, observability): Accepted by Marcus Patel by Week 9
- Deliverables 18–19 (test plan, test results): Accepted by QA sign-off and Marcus Patel by Week 11
- Deliverables 20–21 (production deployment, CLI published to PyPI): Accepted by CTO / Marcus Patel by Week 11
- Deliverables 22–24 (runbooks, as-built docs, knowledge transfer): Accepted by Daniel Park / Marcus Patel by Week 12
- Deliverables 25–26 (Phase 2 roadmap, formal acceptance): Accepted by Sarah Lin by Week 12
*Key Deliverable Highlights:*
- Terraform IaC bundle: all 5 core service modules pass `terraform validate` gate; committed to GitHub
- Pip-installable CLI: published to internal PyPI; `pip install amatra-cli` tested end-to-end on macOS and Linux
- Operational Runbooks: 4 runbooks covering the 4 highest-risk operational scenarios reviewed and approved by Daniel Park
- Phase 2 Optimisation Roadmap: documents multi-region, additional artifact types, and 200 solutions/month cost optimisation path

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Unit test coverage: 97% (target: 80%)
  All 12 artifact types: integration tested
  Critical defects at go-live: 0
  Security findings resolved: 100%
  UAT sign-off: Marcus Patel — passed
Performance Metrics
  Validation pass rate: 96% (target: 95%)
  End-to-end latency: 47 min (target: <60 min)
  Lambda error rate: 0.3% (target: <1%)
  DynamoDB throttles at go-live: 0
  API Gateway 4xx rate: 1.1% (target: <2%)
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- Quality was embedded into the delivery process from Day 1 — unit tests written alongside each agent and Lambda route
- Zero critical defects at go-live is the headline achievement; the security test found 2 medium-severity WAF rule gaps that were resolved before production deployment
- The 96% first-attempt validation pass rate is particularly significant because it directly drives the platform ROI — fewer retries mean lower Bedrock token spend per solution
*Detailed Testing Breakdown:*
- Unit Tests: 5 agent modules + 11 Lambda route handlers; mocked with pytest and moto respectively; 97% line coverage achieved
- Integration Tests: all 12 artifact types (5 presales + 6 delivery + 1 Terraform bundle) tested end-to-end against staging with real Bedrock calls
- API Route Tests: all 11 Lambda routes tested via CLI and HTTP client; JWT bypass tests all returned 401/403; rate limiting confirmed at 100 req/IP/min
- Quota Contention Tests: 20 concurrent solution submissions; DynamoDB conditional writes enforced per-user (10/month) and global (1,000/month) quotas atomically with zero race conditions observed
- Security Tests: JWT bypass (6 test vectors, all blocked), WAF SQLi/XSS (12 payloads, all blocked), IAM privilege escalation (Access Analyzer — no unintended access), Secrets Manager access control confirmed
*Presales SLA Alignment:*
- 95% validation pass rate target: achieved at 96% ✓
- <60 minute end-to-end latency: achieved at 47 minutes average ✓
- Per-user quota (10/month) and global quota (1,000/month): enforced and tested ✓
- Green CloudWatch baseline: Lambda error <1%, DynamoDB throttles = 0, API GW 4xx <2% ✓
- `terraform validate` passes on all Terraform IaC output ✓

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Per-Engagement Effort | 90% reduction | 90% reduction | 8–10 hrs → under 1 hr per bundle
End-to-End Latency | <60 min/bundle | 47 min avg | Same-day proposal response enabled
Validation Pass Rate | 95% first attempt | 96% first attempt | Fewer retries; lower model cost
Pipeline Throughput | 200 solutions/month | 200/month unlocked | Sequential bottleneck eliminated
Model Spend per Solution | <$5 per solution | ~$4.20 per solution | 16% under target; ROI accelerated
Consultant Hours Freed | 120 consultants × savings | Realised from Day 1 | Senior time redirected to client work
Audit & Quota Governance | Full DynamoDB audit trail | Operational from Day 1 | CloudTrail + quota enforcement live
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- All seven benefit categories tracked against the SOW success metrics; all targets met or exceeded
- The most impactful benefit is the per-engagement effort reduction — at 120 consultants × 8 hours saved × 200 engagements/month, the annualised consultant time saving is substantial
- The $4.20/solution model spend is 16% under the $5 target, meaning the 3-year infrastructure cost projection may improve as throughput grows
*ROI Calculation:*
- Scenario: 120 consultants, average 2 engagements/consultant/month = 240 bundles/month
- Pre-platform: 240 bundles × 8 hrs avg = 1,920 senior consultant hours/month
- Post-platform: 240 bundles × 0.75 hrs avg (submission + review) = 180 senior consultant hours/month
- Hours saved per month: 1,740 hours; at blended $175/hr = $304,500/month saved in consultant capacity
- Payback on $250,000 net PS investment: under 1 month of realised savings at full throughput
- More conservatively, assuming 50% of saved hours redirected to billable work: payback in ~2 months
*Future Benefit Projections:*
- Phase 2 multi-region deployment could extend the platform to EMEA and APAC, multiplying throughput and savings
- Additional artifact types in Phase 2 would further reduce manual residual per engagement
- Cost optimisation at 200 solutions/month: amortised infrastructure converges to under $0.50/solution

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Foundation-first: auth proven before AI spend began
  Incremental agent validation de-risked Phase 3
  eof-tools baked into image — zero rewrite risk
  DynamoDB conditional writes ensured atomic quota
  Fixed scope gates protected the April deadline
Challenges Overcome
  Bedrock quota in us-west-2 needed early request
  CTO sign-off scheduling required proactive outreach
Recommendations
  Initiate Phase 2 multi-region design immediately
  Optimise Sonnet 4.6 vs. Haiku 4.5 usage ratio
  Evaluate Bedrock Provisioned Throughput at scale
  Formalise quarterly platform performance reviews
  Expand artifact types to cover additional use cases
Amatra Agentic Orchestration Platform
Notes: *What Worked Well — Detail:*
- Foundation-first (Cognito + DynamoDB + API GW before agents): ensured the team never spent Bedrock budget on an unauthenticated system; also gave Marcus Patel an early tangible deliverable to rally stakeholder confidence
- Incremental agent validation: each of the 5 agents was unit-tested independently before wiring into the multi-agent graph; Phase 3 integration revealed only minor issues, not fundamental design flaws
- eof-tools as container image bake-in: decision to avoid rewriting eof-tools saved an estimated 3–4 weeks of engineering effort and eliminated conversion bug risk
- DynamoDB conditional writes: atomic pattern prevented quota races under the 20-concurrent-submissions load test; a simpler get-then-update pattern would have had race conditions
- Scope deferral policy: agreeing upfront which items were deferred to Phase 2 protected the April executive demo deadline when timeline pressure arose in Week 9
*Challenges and How They Were Resolved:*
- Bedrock service quota in us-west-2: Claude Sonnet 4.6 tokens-per-minute quota hit during load testing in Week 10; resolved by submitting a quota increase request in Week 5 (earlier than planned) and running load tests during off-peak hours while the increase was processed
- CTO sign-off scheduling: CTO availability for the Week 3 architecture review was delayed by two days due to a conflicting board meeting; resolved by distributing the architecture document for asynchronous review and holding a 30-minute focused sign-off call; no timeline impact
*Recommendations — Priority and Expected Benefit:*
- Phase 2 multi-region: primary recommendation; EMEA and APAC regions extend the platform to international consultants; estimated 3-month build; requires separate SOW
- Sonnet/Haiku ratio optimisation: some artifact types (e.g., RAID log, configuration CSV) may be fully generatable by Haiku 4.5 alone; shifting these would reduce model spend per solution by ~15–20%
- Bedrock Provisioned Throughput: at 200 solutions/month, provisioned throughput for Sonnet 4.6 may reduce per-token cost by ~30% vs. on-demand; worth evaluating at Month 6 post-go-live
- Quarterly platform performance reviews: formalised review cadence to assess validation pass rate trends, quota utilisation, and CloudWatch alarm frequency

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 12–16)
  Dedicated vendor team available business hours
  Daily standup with Daniel Park's ops team
  Sev 1 response: 2-hour workaround SLA
  Sev 2 response: 4-hour resolution SLA
  Proactive CloudWatch dashboard monitoring
Transition (Week 16 Handover)
  Full runbook walkthrough completed
  CloudWatch dashboard access transferred
  Admin API keys and Cognito admin provisioned
  GitHub PAT rotation procedure demonstrated
Steady State (Week 17+)
  Daniel Park's team owns ops independently
  Monthly CloudWatch performance review
  Quarterly business reviews with Sarah Lin
  Phase 2 planning workshop at Month 4
Escalation Contacts
  L1 (ops): daniel.park@predictif.com
  L2 (technical): marcus.patel@predictif.com
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- The hypercare period runs for exactly 4 weeks (Weeks 12–16) as committed in the SOW; coverage is business hours Monday–Friday, 8 AM–6 PM Pacific Time
- After hypercare, the platform runs under Daniel Park's Delivery Operations team using the 4 operational runbooks delivered as Deliverable 22
- The escalation structure is internal to PREDICTif after Week 16 — Amatra's involvement post-hypercare is by separate agreement only
*Response Time by Severity (Hypercare):*
- Severity 1 (platform down, generation completely blocked): 2-hour response and workaround; vendor team contacted via marcus.patel@predictif.com
- Severity 2 (generation degraded, individual artifact type failing): 4-hour response
- Severity 3 (cosmetic issues, documentation queries): next business day
*What is Covered in Hypercare:*
- Production defects in delivered platform code and configuration
- Agent prompt tuning (adjustments within EO Framework spec)
- Quota adjustment (per-user or global limit changes)
- GitHub commit troubleshooting
- CloudWatch alert investigation and resolution
*What is NOT Covered in Hypercare:*
- New feature requests or new artifact types
- Additional CLI subcommands
- Changes to EO Framework guidance files (client responsibility)
- These require a change request or Phase 2 engagement
*Key Contacts Post-Hypercare:*
- Platform Operations: Daniel Park — owns CloudWatch dashboards, runbooks, and quota management
- Technical Escalation: Marcus Patel — architecture decisions and Phase 2 scoping
- AWS Support: Business Support case via AWS console (24x7, <1-hour critical response SLA active)

## Slide 9
Slide 9: Acknowledgments & Next Steps
Sarah Lin (CRO) — executive vision, budget authority, and UAT leadership
Marcus Patel — technical leadership, architecture approval, and UAT ownership
Daniel Park — delivery operations readiness and runbook acceptance
CTO — architecture sign-off enabling production deployment on schedule
This Week: Formal acceptance sign-off and documentation handover
Next 30 Days: Hypercare support — daily standups and proactive monitoring
Month 4: Phase 2 planning workshop — multi-region and artifact expansion
Amatra Agentic Orchestration Platform
Notes: *Talking Points:*
- Emphasise that delivery success was a true partnership — the client's responsiveness on CTO scheduling, UAT participation, and Bedrock quota management were all critical enablers
- Recognise the Pre-Sales Engineering team members who participated in UAT with Marcus Patel — their feedback shaped the final prompt tuning pass in Week 11
- Daniel Park's early involvement in runbook review (Week 11, ahead of the Week 12 target) meant the ops team was confident before hypercare began
*Specific Recognition:*
- Sarah Lin: reviewed UAT output personally in Week 11 as part of exec demo preparation; her direct feedback on the solution briefing artifact quality led to a prompt adjustment that improved presales bundle coherence
- Marcus Patel: primary day-to-day counterpart for 12 weeks; responded to every technical clarification within hours; co-authored the UAT scenarios that became the regression test suite
- Daniel Park: accepted all 4 operational runbooks ahead of schedule; proactively added CloudWatch alarm thresholds for quota utilisation based on operational experience
- CTO: turned around the Cognito user pool sign-off within 24 hours of receiving the architecture document; no timeline impact
*Next Steps Timeline:*
- This week (Week 12): formal project acceptance document signed by Sarah Lin; all 26 deliverables confirmed received; Milestone 4 invoice (15% — $37,500) issued
- Weeks 12–16: hypercare in effect; daily standup with Daniel Park at 9 AM Pacific; vendor team available for production issues
- Week 16: hypercare close-out meeting; support formally transitioned to BAU under Daniel Park
- Month 4 (approx. August 2026): Phase 2 planning workshop — multi-region design, additional artifact type prioritisation, Bedrock provisioned throughput evaluation, and Sonnet/Haiku ratio optimisation

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions — the team has backup detail on budget variance, test results breakdown, quota enforcement mechanics, and Phase 2 roadmap sizing
- Have the Test Results Report (Deliverable 19) and Phase 2 Optimisation Recommendations (Deliverable 25) ready as reference documents for deep-dive questions
- If Sarah Lin asks about the formal acceptance process: the acceptance form is pre-populated and ready to sign today; Milestone 4 invoice will be issued within 24 hours of signature
- If there are questions about the hypercare period scope or escalation: refer to Slide 8 and the Operational Runbook (Deliverable 22)
- Close on a positive note — the platform is live, validated, and already delivering the 90% effort reduction that PREDICTif committed to at project kickoff
- Express genuine appreciation for the partnership and signal readiness to begin Phase 2 scoping discussions at the Month 4 planning workshop