## Cover
Project Plan
Generated: | June 05, 2026
Solution: | Tmpnaegu_A5
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff & Scope Alignment | 1 day | 2026-02-02 | 2026-02-02 | None | Project Manager | Not Started
Phase 1 | Current-State Assessment & Legacy CLI Workflow Documentation | 3 days | 2026-02-03 | 2026-02-05 | Project Kickoff & Scope Alignment | Solution Architect | Not Started
Phase 1 | eof-tools Module & Artifact Type Mapping | 2 days | 2026-02-03 | 2026-02-04 | Project Kickoff & Scope Alignment | ML/AI Engineer | Not Started
Phase 1 | AWS Cloud Readiness Assessment & us-west-2 Landing Zone Design | 3 days | 2026-02-05 | 2026-02-07 | Current-State Assessment & Legacy CLI Workflow Documentation | Solution Architect | Not Started
Phase 1 | DynamoDB Data & Quota Model Design | 3 days | 2026-02-05 | 2026-02-07 | AWS Cloud Readiness Assessment & us-west-2 Landing Zone Design | Solution Architect | Not Started
Phase 1 | Architecture Decision Record (ADR) Authoring | 5 days | 2026-02-05 | 2026-02-11 | Current-State Assessment & Legacy CLI Workflow Documentation | Solution Architect | Not Started
Phase 1 | AWS Foundation Provisioning (VPC; IAM; S3; CloudTrail; KMS) | 5 days | 2026-02-09 | 2026-02-13 | AWS Cloud Readiness Assessment & us-west-2 Landing Zone Design | DevOps Engineer | Not Started
Phase 1 | Amazon Cognito User Pool Implementation (pending CTO sign-off) | 5 days | 2026-02-09 | 2026-02-13 | AWS Foundation Provisioning (VPC; IAM; S3; CloudTrail; KMS) | Solutions Engineer | Not Started
Phase 1 | API Gateway HTTP API v2 — 11 Lambda Routes & JWT Authoriser | 5 days | 2026-02-09 | 2026-02-13 | Amazon Cognito User Pool Implementation (pending CTO sign-off) | Solutions Engineer | Not Started
Phase 1 | DynamoDB Tables Implementation (users; solutions; quotas; audit_events) | 4 days | 2026-02-10 | 2026-02-13 | DynamoDB Data & Quota Model Design | Solutions Engineer | Not Started
Phase 1 | CloudWatch Dashboards & CloudTrail Audit Logging Baseline | 3 days | 2026-02-11 | 2026-02-13 | AWS Foundation Provisioning (VPC; IAM; S3; CloudTrail; KMS) | DevOps Engineer | Not Started
Phase 1 | Security Hardening (Secrets Manager; GuardDuty; Security Hub) | 3 days | 2026-02-11 | 2026-02-13 | AWS Foundation Provisioning (VPC; IAM; S3; CloudTrail; KMS) | Security Engineer | Not Started
Phase 1 | Phase 1 Completion Report | 1 day | 2026-02-16 | 2026-02-16 | DynamoDB Tables Implementation (users; solutions; quotas; audit_events) | Project Manager | Not Started
Phase 2 | Five-Agent Strands Multi-Agent Graph Design & Implementation | 10 days | 2026-02-17 | 2026-02-27 | Phase 1 Completion Report | ML/AI Engineer | Not Started
Phase 2 | Bedrock AgentCore Runtime Registration (Sonnet 4.6 + Haiku 4.5) | 5 days | 2026-02-17 | 2026-02-21 | Phase 1 Completion Report | ML/AI Engineer | Not Started
Phase 2 | Docker Image Pipeline — eof-tools Baked Agent Image & ECR Push | 7 days | 2026-02-17 | 2026-02-25 | Phase 1 Completion Report | DevOps Engineer | Not Started
Phase 2 | Per-Artifact Validation Loop (format-check + LLM quality-check; 3 retries) | 8 days | 2026-02-24 | 2026-03-05 | Five-Agent Strands Multi-Agent Graph Design & Implementation | ML/AI Engineer | Not Started
Phase 2 | eof-tools Converter Integration (DOCX; PPTX; XLSX across 12 artifact types) | 8 days | 2026-02-24 | 2026-03-05 | Docker Image Pipeline — eof-tools Baked Agent Image & ECR Push | Solutions Engineer | Not Started
Phase 2 | Graded Artifact Delivery Policy Implementation | 3 days | 2026-03-03 | 2026-03-05 | Per-Artifact Validation Loop (format-check + LLM quality-check; 3 retries) | Solutions Engineer | Not Started
Phase 2 | CLI Implementation (pip-installable; 14 subcommands; per-phase token usage) | 10 days | 2026-03-02 | 2026-03-13 | Bedrock AgentCore Runtime Registration (Sonnet 4.6 + Haiku 4.5) | Solutions Engineer | Not Started
Phase 2 | DynamoDB Atomic Quota Enforcement (per-user 10/month; global 1000/month) | 5 days | 2026-03-02 | 2026-03-06 | DynamoDB Tables Implementation (users; solutions; quotas; audit_events) | Solutions Engineer | Not Started
Phase 2 | GitHub Integration — PAT-Based Automated Artifact Commit Pipeline | 4 days | 2026-03-05 | 2026-03-10 | DynamoDB Atomic Quota Enforcement (per-user 10/month; global 1000/month) | Solutions Engineer | Not Started
Phase 2 | Terraform IaC Automation Bundle (all infrastructure modules) | 8 days | 2026-03-02 | 2026-03-11 | AWS Foundation Provisioning (VPC; IAM; S3; CloudTrail; KMS) | DevOps Engineer | Not Started
Phase 2 | CI/CD Pipeline (GitHub Actions; Docker build; ECR push; Lambda deploy) | 5 days | 2026-03-09 | 2026-03-13 | Terraform IaC Automation Bundle (all infrastructure modules) | DevOps Engineer | Not Started
Phase 2 | CloudWatch Per-Phase Token Usage Metrics & X-Ray Tracing | 4 days | 2026-03-09 | 2026-03-13 | CI/CD Pipeline (GitHub Actions; Docker build; ECR push; Lambda deploy) | DevOps Engineer | Not Started
Phase 3 | Test Plan Authoring (unit; integration; E2E; performance; security; UAT) | 3 days | 2026-03-16 | 2026-03-18 | CI/CD Pipeline (GitHub Actions; Docker build; ECR push; Lambda deploy) | QA Engineer | Not Started
Phase 3 | End-to-End Artifact Validation (all 12 artifact types; format-check + quality-check) | 5 days | 2026-03-16 | 2026-03-20 | Per-Artifact Validation Loop (format-check + LLM quality-check; 3 retries) | QA Engineer | Not Started
Phase 3 | Load & Performance Testing (200 solutions/month; per-solution model cost validation) | 4 days | 2026-03-19 | 2026-03-24 | End-to-End Artifact Validation (all 12 artifact types; format-check + quality-check) | QA Engineer | Not Started
Phase 3 | Security Testing (JWT auth; quota bypass; PAT protection; IAM review) | 4 days | 2026-03-19 | 2026-03-24 | End-to-End Artifact Validation (all 12 artifact types; format-check + quality-check) | Security Engineer | Not Started
Phase 3 | DynamoDB PITR Restore Test & Resilience Validation | 2 days | 2026-03-23 | 2026-03-24 | Load & Performance Testing (200 solutions/month; per-solution model cost validation) | DevOps Engineer | Not Started
Phase 3 | UAT Coordination & Executive Demo (Marcus Patel; Daniel Park; Sarah Lin) | 3 days | 2026-03-24 | 2026-03-26 | Load & Performance Testing (200 solutions/month; per-solution model cost validation) | Project Manager | Not Started
Phase 3 | CloudWatch Green Metrics Baseline Confirmation | 2 days | 2026-03-25 | 2026-03-26 | CloudWatch Per-Phase Token Usage Metrics & X-Ray Tracing | DevOps Engineer | Not Started
Phase 3 | CTO Sign-Off on Production Cognito User Pool & Deployment | 1 day | 2026-03-27 | 2026-03-27 | UAT Coordination & Executive Demo (Marcus Patel; Daniel Park; Sarah Lin) | Project Manager | Not Started
Phase 3 | Operational Runbook Authoring (quota reset; agent failure; Bedrock throttle; GitHub push) | 4 days | 2026-03-23 | 2026-03-26 | End-to-End Artifact Validation (all 12 artifact types; format-check + quality-check) | Solution Architect | Not Started
Phase 3 | Knowledge Transfer Session 1 — CLI & API (14 subcommands; 11 routes) | 1 day | 2026-03-30 | 2026-03-30 | Operational Runbook Authoring (quota reset; agent failure; Bedrock throttle; GitHub push) | Solution Architect | Not Started
Phase 3 | Knowledge Transfer Session 2 — Agent Operations (5-agent graph; token usage; quotas) | 1 day | 2026-03-31 | 2026-03-31 | Knowledge Transfer Session 1 — CLI & API (14 subcommands; 11 routes) | ML/AI Engineer | Not Started
Phase 3 | As-Built Documentation (architecture diagrams; ADRs; configuration inventory) | 4 days | 2026-03-23 | 2026-03-26 | End-to-End Artifact Validation (all 12 artifact types; format-check + quality-check) | Solution Architect | Not Started
Phase 3 | Optimization Recommendations — Phase 2 Scope Backlog | 2 days | 2026-03-30 | 2026-03-31 | As-Built Documentation (architecture diagrams; ADRs; configuration inventory) | Solution Architect | Not Started
Phase 3 | Production Go-Live Execution & Cutover | 1 day | 2026-04-01 | 2026-04-01 | CTO Sign-Off on Production Cognito User Pool & Deployment | Solutions Engineer | Not Started
Phase 3 | Project Closeout Report | 1 day | 2026-04-02 | 2026-04-02 | Production Go-Live Execution & Cutover | Project Manager | Not Started
Hypercare | Hypercare Support (Weeks 13–16) | 20 days | 2026-04-06 | 2026-04-30 | Production Go-Live Execution & Cutover | Solutions Engineer | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Project Kickoff Complete | 2026-02-02 | Phase 1 | All stakeholders aligned; project charter confirmed; scope and success criteria signed off by Marcus Patel and Sarah Lin | Project Manager | Not Started
MS-002 | AWS Foundation Live | 2026-02-13 | Phase 1 | us-west-2 VPC/IAM/S3/CloudTrail/KMS operational; CTO sign-off gate for Cognito initiated; JWT-authenticated API call demonstrable | Solution Architect | Not Started
MS-003 | Identity & API Ready | 2026-02-16 | Phase 1 | Cognito user pool live; API Gateway HTTP API v2 with 11 routes operational; DynamoDB schema deployed; ADR and Phase 1 Completion Report accepted by Marcus Patel | Project Manager | Not Started
MS-004 | First Agent Generating | 2026-02-27 | Phase 2 | Single Strands agent producing one artifact type end-to-end in Bedrock AgentCore Runtime with format-check passing | ML/AI Engineer | Not Started
MS-005 | Presales Bundle Automated | 2026-03-13 | Phase 2 | All five presales artifacts generated end-to-end via CLI with format-check and LLM quality-check passing; Docker image pipeline green; quota enforcement verified; GitHub commit confirmed | ML/AI Engineer | Not Started
MS-006 | All 12 Artifacts Validated | 2026-03-20 | Phase 3 | Full twelve-artifact solution bundle passes format-check and LLM quality-check (≤ 3 retries per artifact); CloudWatch baseline green; load test at 200 solutions/month passed with per-solution Bedrock spend < $5 | QA Engineer | Not Started
MS-007 | UAT Sign-Off & Executive Demo | 2026-03-26 | Phase 3 | All critical UAT scenarios passed; executive demonstration delivered to Sarah Lin; UAT sign-off obtained from Marcus Patel; CTO sign-off on production deployment confirmed | Project Manager | Not Started
MS-008 | Production Go-Live | 2026-04-01 | Phase 3 | Production deployment complete; all 11 API routes smoke-tested with live JWT tokens; GitHub commit pipeline delivering to production repository; CloudWatch alarms active and routing to Daniel Park | Solutions Engineer | Not Started
MS-009 | Hypercare Conclusion & BAU Handover | 2026-04-30 | Hypercare | Four-week hypercare period concluded; all runbooks validated in production; platform ownership fully transferred to Daniel Park; no open P1 or P2 incidents | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Architect | Vendor Engineer | Vendor QA | Client IT Lead (Daniel Park) | Client CTO | Marcus Patel | Sarah Lin
Project Kickoff & Scope Alignment | A | R | I | I | C | I | R | C
Current-State Assessment & ADR | C | A | R | I | C | I | R | I
AWS Foundation Provisioning (us-west-2) | C | A | R | I | R | I | C | I
Amazon Cognito User Pool Provisioning | C | A | R | I | C | A | R | I
API Gateway & Lambda Route Implementation | C | C | A | I | I | I | R | I
DynamoDB Schema & Quota Enforcement | C | A | R | I | C | I | R | I
Strands Multi-Agent Graph Implementation | C | A | R | C | I | I | C | I
Bedrock AgentCore Runtime Registration | C | A | R | I | I | I | C | I
eof-tools Converter Integration | C | C | A | C | I | I | R | I
CLI Implementation (14 subcommands) | C | C | A | C | I | I | R | I
GitHub Integration (PAT Commit Pipeline) | C | C | A | I | C | I | R | I
Terraform IaC Automation Bundle | C | A | R | C | I | I | C | I
Security Hardening & GuardDuty Setup | C | A | R | C | R | C | C | I
CI/CD Pipeline Implementation | C | C | A | C | C | I | C | I
Per-Artifact Validation Loop (3-retry logic) | C | C | R | A | C | I | R | I
End-to-End Artifact Validation Testing | C | C | R | A | C | I | R | I
Load & Performance Testing | C | C | R | A | I | I | C | I
Security Testing | C | A | R | C | R | C | C | I
UAT Coordination & Executive Demo | A | C | C | C | C | C | R | R
CTO Sign-Off (Cognito and Production) | I | C | I | I | C | A | R | C
Runbook Authoring | C | R | R | C | C | I | A | I
Knowledge Transfer Delivery | A | R | R | I | C | I | R | I
As-Built Documentation | C | A | R | C | C | I | R | I
Project Go-Live Approval | A | C | I | C | C | A | R | R
Hypercare Support Management | A | C | R | I | R | I | C | I
Project Closeout Report | A | C | I | I | C | I | C | R
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | I C A C A A A: Responsible - Does the work
A | I C A C A A A: Accountable - Ultimate ownership
C | I C A C A A A: Consulted - Provides input
I | I C A C A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders; EO Framework vendor team; Marcus Patel; Daniel Park; Sarah Lin; CTO | Launch project; align on scope; confirm RACI; review success criteria and governance cadence | Project Manager | 2026-02-02 09:00 PT
Weekly Status Call | Weekly | Vendor PM; Marcus Patel; Daniel Park; relevant vendor leads | Review progress against project plan; surface blockers and decisions; update milestone status | Project Manager | Mondays 10:00 PT
Architecture Review Workshop | Once (Week 2) | Solution Architect; Marcus Patel; Daniel Park; ML/AI Engineer | Review and approve ADR; confirm us-west-2 landing zone design and DynamoDB data model | Solution Architect | 2026-02-11 10:00 PT (3 hours)
Phase 1 Gate Review | Once (Week 4) | Vendor PM; Solution Architect; Marcus Patel; Daniel Park | Review Phase 1 completion criteria; confirm Cognito and API Gateway are live; approve Phase 2 start | Project Manager | 2026-02-16 10:00 PT (1 hour)
Phase 2 Mid-Sprint Check-In | Bi-weekly | Vendor PM; ML/AI Engineer; Solutions Engineer; Marcus Patel | Review agent build progress; confirm eof-tools integration status; address quota and CLI blockers | Project Manager | Alternating Mondays 14:00 PT
Phase 2 Gate Review | Once (Week 9) | Vendor PM; Solution Architect; Marcus Patel; Daniel Park | Review Phase 2 completion criteria; confirm all five agents operational and CLI deployed; approve Phase 3 start | Project Manager | 2026-03-13 10:00 PT (1 hour)
UAT Session & Executive Demo | Once (Week 11) | Vendor PM; all vendor team leads; Marcus Patel; Daniel Park; Sarah Lin | Conduct UAT across twelve artifact types; present load test results; deliver executive demonstration for go-live approval | Project Manager | 2026-03-24 10:00 PT (4 hours)
Go-Live Readiness Review | Once (Week 12) | Vendor PM; Solution Architect; Marcus Patel; Daniel Park; CTO | Present go-live readiness checklist; confirm all criteria satisfied; obtain CTO and Marcus Patel sign-off for production deployment | Project Manager | 2026-03-27 10:00 PT (1 hour)
Hypercare Incident Escalation | As required | Vendor engineer on-call; Marcus Patel; Daniel Park | Notify and resolve P1 incidents (platform down / quota enforcement broken) during hypercare period | Solutions Engineer | Within 2 business hours of detection
Hypercare Weekly Check-In | Weekly (Weeks 13–16) | Vendor PM; Solutions Engineer; Daniel Park; Marcus Patel | Review open hypercare issues; confirm platform health metrics; track any outstanding runbook gaps | Project Manager | Mondays 10:00 PT
Project Closeout Meeting | Once (Week 16) | Vendor PM; Solution Architect; Marcus Patel; Daniel Park; Sarah Lin | Formal project closure; BAU handover confirmation; Phase 2 scope backlog review; final invoice reconciliation | Project Manager | 2026-04-30 10:00 PT (1 hour)