## Cover
Level of Effort
Generated: | June 05, 2026
Solution: | Tmpbl4V3_Rd
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Consultants | Single business unit | ~120 consultants across US and Canada | Up to 50 users | 51–200 users | 200+ users | Amatra team is ~120 consultants; all will use the CLI and API
Regions / Geographies | Single AWS region | us-west-2 (primary) | 1 region | 2 regions | 3+ regions | New footprint isolated in us-west-2; existing workloads remain in us-east-1
Agents / Microservices | 3–4 Lambda functions | 5 agents + 14 CLI subcommands + 11 API Lambda routes | 3–5 functions | 6–15 functions | 16+ functions | Five Strands agents: Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator
Artifact Types | 4–6 artifact types | 12 artifacts per solution (5 presales + 6 delivery + 1 automation) | Up to 6 artifacts | 7–12 artifacts | 13+ artifacts | EO Framework defines 12 artifacts; each has format-check + LLM quality validation with up to 3 retries
Integrations / External Systems | 1–2 integrations | 4 integrations (Bedrock AgentCore + Cognito + GitHub + DynamoDB quota) | 1–2 integrations | 3–5 integrations | 6+ integrations | GitHub PAT push, Cognito JWT auth, DynamoDB atomic quotas, Bedrock model calls
Environments | Dev + Prod | Dev / Staging / Prod (3 environments) | Dev + Prod | Dev + Staging + Prod | Dev + Staging + Prod + DR | Blast-radius isolation between POC (us-west-2) and existing managed-services (us-east-1)
Compliance / Security | Standard AWS security baseline | CTO sign-off required; JWT auth; per-user + global quotas; audit trail | Basic IAM | IAM + Cognito + audit logging | IAM + Cognito + SIEM + compliance reporting | CTO approval gate for Cognito user pool and production deployment
SLA / Availability Target | Business-hours availability | POC target; production path to 99.9% uptime | Best effort | 99.5% uptime | 99.9%+ with DR | 12-week POC hard deadline (end of April 2026); Bedrock + AgentCore SLAs inherited

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Baseline stakeholder interviews; current-state review of legacy CLI workflow and eof-tools library
Planning | planning_factor | 1.2 | Elevated for multi-agent graph design; AWS Landing Zone and IAM architecture complexity
Development | development_factor | 1.3 | Core build phase; AgentCore Runtime + Strands framework integration, Docker image pipeline, 12-artifact converters
Testing | testing_factor | 1.1 | End-to-end artifact validation across all 12 artifact types; CloudWatch metrics baseline; multi-agent retry logic
Deployment | deployment_factor | 1 | Production deployment; knowledge transfer to Amatra team; runbook delivery
Management | management_factor | 1 | Project management and technical leadership overhead (10% of engineering tasks)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Kickoff meeting with Sarah Lin / Marcus Patel / Daniel Park; align on scope and success criteria | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Week 1
Discovery | Current-State Assessment | Document legacy CLI workflow; map eof-tools converter library (~30 modules) and 12 artifact types | Solution Architect | 24 | 1 | 24 | 225 | 5400 | Project Kickoff | Produces as-is architecture baseline
Discovery | Requirements Gathering | Gather requirements for 14 CLI subcommands, 11 API routes, 5-agent graph, quota model, and GitHub push | Solution Architect | 32 | 1 | 32 | 225 | 7200 | Current-State Assessment | Interviews with Marcus Patel and Daniel Park
Discovery | AWS Cloud Readiness Assessment | Review existing AWS account; define us-west-2 landing zone, blast-radius controls, and account strategy | Cloud Engineer | 16 | 1 | 16 | 200 | 3200 | Requirements Gathering | Ensures new footprint isolation
Discovery | Data & Quota Model Design | Design DynamoDB schema for per-user (10/month) and global (1000/month) atomic quota enforcement | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Requirements Gathering | Drives DynamoDB partition key strategy
Discovery | Gap Analysis | Identify gaps between current manual process and target agentic engine; document risk register | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Current-State Assessment
Discovery | Assessment Report | Document findings; produce architecture decision record (ADR) and phase-1 scope baseline | Technical Writer | 16 | 1 | 16 | 125 | 2000 | Gap Analysis | Delivered to Marcus Patel for CTO review
Planning | AWS Landing Zone Setup | Design VPC, IAM roles, S3 bucket policies, and CloudTrail in us-west-2 for POC footprint | Cloud Engineer | 40 | 1.2 | 48 | 200 | 9600 | Assessment Report | Phase 1 (Weeks 1–4) foundation
Planning | API Gateway & Lambda Architecture | Design HTTP API v2 structure: 11 routes, JWT authoriser, Lambda integration patterns, throttling | Solution Architect | 32 | 1.2 | 38 | 225 | 8550 | AWS Landing Zone Setup
Planning | Cognito User Pool Design | Design user pool, app client, post-confirmation trigger Lambda, 30-day refresh token policy | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | API Gateway & Lambda Architecture | CTO sign-off required before provisioning
Planning | DynamoDB Schema Design | Design tables for user profiles, solution records, quota counters, and audit events | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | Data & Quota Model Design
Planning | Strands Multi-Agent Graph Design | Design 5-agent orchestration graph: Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator | Solution Architect | 48 | 1.2 | 58 | 225 | 13050 | Requirements Gathering | Phase 2 (Weeks 5–9) core design
Planning | Bedrock AgentCore Runtime Design | Design AgentCore Runtime hosting config for serverless agents; Claude Sonnet 4.6 primary + Haiku 4.5 validator | ML/AI Engineer | 32 | 1.2 | 38 | 275 | 10450 | Strands Multi-Agent Graph Design | ML/AI rate adjusted for specialised Bedrock expertise
Planning | Container Image Pipeline Design | Design Docker image build pipeline: bake eof-tools converters, Python deps, agent code; ECR repo strategy | DevOps Engineer | 24 | 1.2 | 29 | 200 | 5800 | Strands Multi-Agent Graph Design
Planning | Security Baseline Design | IAM least-privilege roles, KMS key design, Cognito JWT validation, GitHub PAT secret storage in Secrets Manager | Security Engineer | 32 | 1.2 | 38 | 200 | 7600 | Cognito User Pool Design
Planning | CLI Architecture Design | Design pip-installable CLI: 14 subcommands, auth flow, status command with per-phase token usage display | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | API Gateway & Lambda Architecture
Planning | Design Documentation | Produce detailed architecture diagrams, ADRs, and design specification for all components | Technical Writer | 24 | 1.2 | 29 | 125 | 3625 | All design tasks
Development | AWS Foundation Build | Provision VPC, subnets, S3 buckets, IAM roles, CloudTrail, and KMS keys in us-west-2 | Cloud Engineer | 40 | 1.3 | 52 | 200 | 10400 | Design Documentation | Phase 1 delivery (Weeks 1–4)
Development | API Gateway HTTP API v2 | Implement all 11 Lambda routes, JWT Cognito authoriser, CORS config, and throttling rules | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | AWS Foundation Build
Development | Cognito User Pool Implementation | Implement user pool, app client, post-confirmation Lambda writing profiles to DynamoDB | Solutions Engineer | 32 | 1.3 | 42 | 200 | 8400 | API Gateway HTTP API v2 | Requires CTO approval gate before production
Development | DynamoDB Implementation | Implement user, solution, quota, and audit tables; atomic counter logic for quota enforcement | Solutions Engineer | 32 | 1.3 | 42 | 200 | 8400 | DynamoDB Schema Design
Development | Strands Agent Framework Integration | Implement 5-agent Strands graph; wire agent-to-agent message passing and retry orchestration | ML/AI Engineer | 80 | 1.3 | 104 | 275 | 28600 | Strands Multi-Agent Graph Design | Largest single work package — core platform capability
Development | Bedrock AgentCore Runtime Integration | Register agents in AgentCore Runtime; configure Claude Sonnet 4.6 and Haiku 4.5 model bindings | ML/AI Engineer | 48 | 1.3 | 62 | 275 | 17050 | Strands Agent Framework Integration
Development | eof-tools Converter Integration | Integrate ~30 Python eof-tools modules for DOCX, PPTX, XLSX conversion; bake into container image | Solutions Engineer | 64 | 1.3 | 83 | 200 | 16600 | Container Image Pipeline Design | 12 artifact types × format-check + LLM quality validation
Development | Per-Artifact Validation Pipeline | Implement deterministic format-check + LLM quality-check loop with up to 3 retries per artifact | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | eof-tools Converter Integration | Covers all 12 artifact types
Development | GitHub Integration | Implement GitHub PAT push logic; commit generated artifacts to fixed public repository per solution | Solutions Engineer | 24 | 1.3 | 31 | 200 | 6200 | Per-Artifact Validation Pipeline
Development | CLI Implementation | Build pip-installable CLI with 14 subcommands including auth, generate, status (with per-phase token usage), and admin | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | API Gateway HTTP API v2
Development | Quota Enforcement Implementation | Implement atomic per-user (10/month) and global (1000/month) quota checks in DynamoDB; admin override endpoint | Solutions Engineer | 24 | 1.3 | 31 | 200 | 6200 | DynamoDB Implementation
Development | Graded Artifact-Delivery Policy | Implement policy engine that surfaces partial results if some artifacts pass while others fail validation | Solutions Engineer | 24 | 1.3 | 31 | 200 | 6200 | Per-Artifact Validation Pipeline
Development | Security Hardening | Implement Secrets Manager for GitHub PAT; enforce IAM boundaries; enable GuardDuty and Security Hub | Security Engineer | 32 | 1.3 | 42 | 200 | 8400 | AWS Foundation Build
Development | Observability & Monitoring | Implement CloudWatch dashboards, alarms, and per-phase token-usage metrics; X-Ray tracing on Lambda | DevOps Engineer | 32 | 1.3 | 42 | 200 | 8400 | Strands Agent Framework Integration | Phase 3 requirement (green CloudWatch baseline)
Development | Terraform IaC for Automation Bundle | Author Terraform modules for all infrastructure; implement terraform validate as syntax gate in CI | DevOps Engineer | 48 | 1.3 | 62 | 200 | 12400 | AWS Foundation Build | 12th artifact is automation bundle with Terraform
Development | CI/CD Pipeline | Implement CodePipeline or GitHub Actions: Docker build, ECR push, Lambda deploy, terraform validate gate | DevOps Engineer | 48 | 1.3 | 62 | 200 | 12400 | Container Image Pipeline Design
Testing | Test Plan Development | Create comprehensive test plan covering all 5 agents; 12 artifact types; API routes; CLI subcommands | QA Engineer | 16 | 1.1 | 18 | 150 | 2700 | Development (all)
Testing | Unit & Integration Testing | Test each Lambda function, agent, and converter module in isolation and in combination | Solutions Engineer | 40 | 1.1 | 44 | 200 | 8800 | Test Plan Development
Testing | End-to-End Artifact Validation | Run full solution generation for all 12 artifacts; verify format-check pass and LLM quality-check pass | QA Engineer | 40 | 1.1 | 44 | 150 | 6600 | Unit & Integration Testing | Phase 3 deliverable
Testing | Multi-Agent Retry Logic Testing | Stress-test validation retry loop (up to 3 retries per artifact); confirm no infinite-loop edge cases | Solutions Engineer | 24 | 1.1 | 26 | 200 | 5200 | End-to-End Artifact Validation
Testing | Performance & Load Testing | Load test API at projected 200 solutions/month; measure per-solution Bedrock token cost (target <$5) | Solutions Engineer | 24 | 1.1 | 26 | 200 | 5200 | End-to-End Artifact Validation | Validates cost target
Testing | Security Testing | Penetration test JWT auth; test quota bypass scenarios; validate Secrets Manager PAT protection | Security Engineer | 24 | 1.1 | 26 | 200 | 5200 | Security Hardening
Testing | CLI Acceptance Testing | Test all 14 CLI subcommands end-to-end including auth flow and status token-usage display | QA Engineer | 16 | 1.1 | 18 | 150 | 2700 | CLI Implementation
Testing | UAT Coordination | Coordinate UAT with Marcus Patel and Daniel Park; facilitate demo run for executive sponsor (Sarah Lin) | Project Manager | 16 | 1.1 | 18 | 175 | 3150 | End-to-End Artifact Validation | Required for CTO sign-off
Testing | Defect Resolution | Triage and resolve defects identified during testing phases | Solutions Engineer | 32 | 1.1 | 35 | 200 | 7000 | All testing tasks
Testing | CloudWatch Metrics Baseline | Validate green CloudWatch metrics baseline across all agents and Lambda functions | DevOps Engineer | 16 | 1.1 | 18 | 200 | 3600 | Observability & Monitoring | Phase 3 completion criterion
Testing | Terraform Validate Gate Testing | Confirm terraform validate syntax gate passes for all IaC modules in automation bundle | DevOps Engineer | 8 | 1.1 | 9 | 200 | 1800 | Terraform IaC for Automation Bundle
Testing | Test Results Report | Document test results and sign-off report for CTO approval | QA Engineer | 8 | 1.1 | 9 | 150 | 1350 | All testing tasks
Deployment | Go-Live Planning | Plan production cutover; define rollback procedures; confirm CTO sign-off on Cognito user pool | Project Manager | 8 | 1 | 8 | 175 | 1400 | Test Results Report | Hard deadline: end of April 2026
Deployment | Production Deployment | Deploy all Lambda functions, Cognito user pool, DynamoDB tables, and AgentCore Runtime to production | Solutions Engineer | 16 | 1 | 16 | 200 | 3200 | Go-Live Planning
Deployment | Runbook Development | Author operational runbooks for quota resets, agent failure recovery, Bedrock throttle handling, and GitHub push failures | Technical Writer | 24 | 1 | 24 | 125 | 3000 | Production Deployment
Deployment | Knowledge Transfer — CLI & API | Conduct hands-on CLI and API sessions with Amatra consultants; cover 14 subcommands and 11 API routes | Trainer | 24 | 1 | 24 | 150 | 3600 | Production Deployment
Deployment | Knowledge Transfer — Agent Operations | Train Marcus Patel's team on monitoring 5-agent graph; interpreting per-phase token usage; managing quotas | Trainer | 16 | 1 | 16 | 150 | 2400 | Observability & Monitoring
Deployment | As-Built Documentation | Deliver complete as-built architecture diagrams, ADRs, and configuration inventory | Technical Writer | 24 | 1 | 24 | 125 | 3000 | Production Deployment
Deployment | Hypercare Support (4 Weeks) | Provide on-call support for 4 weeks post go-live; triage Bedrock quota issues, agent failures, and GitHub push errors | Support Engineer | 80 | 1 | 80 | 150 | 12000 | Production Deployment | 80 hours aligns with Medium–Large complexity guideline
Deployment | Optimization Recommendations | Document Phase 2 scope candidates: additional artifact types, multi-region HA, advanced Bedrock model routing | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Hypercare Support (4 Weeks)
Deployment | Project Closeout | Project retrospective with PREDICTif leadership; lessons learned; final invoice reconciliation | Project Manager | 8 | 1 | 8 | 175 | 1400 | All deployment tasks
Management | Technical Leadership | Quarterback technical oversight across all phases; architecture governance and escalation path | Solution Architect |  | 1 |  | 225 |  | All phases | 10% of total engineering hours
Management | Project Management | Project coordination, status reporting, risk management, and stakeholder communications | Project Manager |  | 1 |  | 175 |  | All phases | 10% of total engineering hours
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -10000 | AWS Partner Network (APN) Advanced Tier credit applied to solution architecture and implementation services for this engagement
APN Migration Acceleration Credit | -5000 | AWS Migration Acceleration Program (MAP) services credit; applicable given new AWS footprint build-out in us-west-2
Volume Implementation Discount | -5000 | 10% professional services volume discount applied to total engagement; reflects strategic partnership and multi-phase opportunity
TOTAL |  | Total professional services cost minus AWS Partner and volume credits applied in Year 1 only; infrastructure credits tracked separately in infrastructure-costs.csv