## Slide 1
Project Closeout
AWS Cloud Governance Platform — Contoso Financial
Rachel Moore | 2026-05-01

## Slide 2
Slide 2: Executive Summary
Project Duration: 16 weeks (4 months), on schedule
Budget: $404,900 net professional services, on budget
Go-Live Date: End of Week 15 as planned
Quality: Zero critical defects at production go-live
Guardrail Coverage: 100% of production accounts under SCPs
Identity: Shared credentials fully retired; IdP federation live
Audit Package: ISO 27001 evidence package delivered to CISO
DR Validated: RTO < 4h and RPO < 1h confirmed in drill
Hypercare: 8-week period covers April 2026 regulatory review
ROI: Audit remediation effort reduced by 80% — payback on track
AWS Cloud Governance Platform — Contoso Financial
Notes: *Talking Points:*
- Open with confidence — the platform was delivered on time, on budget, and to full scope.
- The April 2026 regulatory deadline was the defining constraint for every phase-gate decision, and we met it.
- Emphasise the zero-critical-defect go-live as proof of the quality embedded in the delivery process.
*Background Details:*
- Professional services: $434,900 list price less $30,000 in APN, MAP, and volume credits = $404,900 net. This matches the SOW Investment Summary exactly.
- Phased timeline: Phase 1 (Weeks 1–6 Discovery & Design), Phase 2 (Weeks 7–12 Build & Integrate), Phase 3 (Weeks 13–16 Testing & Handover).
- 8-week hypercare period (Weeks 17–24) was specifically sized to cover the regulatory review window — this was a deliberate presales commitment and it has been honoured.
- ISO 27001 evidence package compiled and accepted by CISO before go-live (Milestone M9).
- DR drill confirmed RTO 3h 20min and RPO 42min — both within SOW targets of < 4h and < 1h respectively.
*Presales Commitments Met:*
- 80% reduction in audit remediation effort — target set in SOW Success Metrics, validated post-go-live.
- Zero shared administrative credentials — IAM Identity Center federation replaced all shared-credential access.
- Account provisioning reduced from days to under 4 hours — AFT pipeline validated during functional testing.
- All data remains within Australia (ap-southeast-2 primary, ap-southeast-4 DR) — data sovereignty confirmed.

## Slide 3
Slide 3: Solution Architecture
AWS Cloud Governance Platform — Contoso Financial
Governance & Provisioning
  Control Tower + AFT account vending pipeline
  SCPs enforcing no-console-access organisation-wide
  ITSM change-approval gate on all vending requests
Security & Compliance
  Security Hub aggregating GuardDuty + Config findings
  Centralised S3 log archive (12-month WORM retention)
  ISO 27001 conformance pack with auto-remediation
Network & Identity
  Transit Gateway hub-spoke with Network Firewall
  IAM Identity Center federation from on-prem IdP
  Dual-region deployment: ap-southeast-2 + ap-southeast-4
Notes: *Talking Points:*
- Walk through the architecture top-to-bottom: governance layer, then security, then network and identity.
- Every component maps directly to a presales commitment in the Solution Briefing — no scope additions were made.
- The dual-region deployment (ap-southeast-2 primary, ap-southeast-4 DR) was a hard data sovereignty requirement and was delivered as designed.
*Technical Details:*
- Control Tower OU hierarchy: Management, Log Archive, Audit, Security, Network, and Workload OUs — exactly as designed in the Architecture Design Document (Deliverable #5).
- AFT pipeline uses Terraform Cloud Plus workspaces with Sentinel policy-as-code for pre-deployment compliance checks.
- ~80 AWS Config rules deployed: ISO 27001 conformance pack + custom rules for Contoso Financial's internal security baseline.
- Network Firewall in the Network Account inspects all east-west and north-south traffic; no direct peer-to-peer between workload accounts.
- IAM Identity Center: SAML 2.0 federation with on-prem IdP; four permission sets (Developer, Operator, SecurityViewer, BreakGlass); MFA enforced at IdP level.
*Cost Alignment:*
- Annual infrastructure run rate: ~$9,956/year list; effectively covered by AWS MAP and partner credits in Year 1.
- Year 2 and Year 3 recurring run cost is ~$34,130/year (cloud + connectivity + software + support) — as documented in the SOW Investment Summary.
*Presales Alignment:*
- Architecture is identical to the Solution Briefing (Slide 4) and the Architecture Design Document.
- Services deployed: AWS Control Tower, AFT (Terraform), AWS Config, SCPs, Security Hub, GuardDuty, IAM Identity Center, CloudTrail, S3 (WORM), Transit Gateway, Network Firewall, Direct Connect, EventBridge, Lambda, CloudWatch, Systems Manager.
- No services were added beyond the presales scope.

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Architecture Design Document | OU hierarchy, guardrail framework, design decisions | `/delivery/detailed-design.md`
IaC Module Library (Terraform) | Reusable AFT modules, VPC, IAM, Config packs | `/delivery/scripts/terraform/`
Configuration & Operations Guide | Platform configuration reference and procedures | `/delivery/configuration.csv`
Test Results & Compliance Evidence | ISO 27001 control validation and DR test results | `/delivery/test-plan.csv`
Operational Runbook Suite | Account vending, break-glass, DR failover SOPs | `/delivery/runbook/`
Knowledge Transfer Recordings | Recorded sessions: AFT, Security Hub, IAM IdC | `/delivery/training/`
Platform Optimisation Roadmap | Cost optimisation and guardrail enhancement plan | `/delivery/optimisation-roadmap.md`
Project Closeout Report | Engagement summary and lessons learned | `/delivery/closeout-report.md`
AWS Cloud Governance Platform — Contoso Financial
Notes: *Talking Points:*
- All 25 deliverables listed in the SOW Deliverables table have been completed and accepted.
- This slide highlights the eight most strategically significant deliverables for executive awareness.
- Every deliverable was accepted in writing by the designated authority before the next phase commenced — no phase-gate was bypassed.
*Deliverable Status (all 25 SOW deliverables):*
- Deliverables 1–5 (Phase 1): Project Kickoff Deck, Current State Assessment, Gap Analysis, ISO 27001 Control Mapping, Architecture Design — all accepted by Week 6.
- Deliverables 6–17 (Phase 2): IaC Module Library, Control Tower, AFT, SCPs/Config, IAM Identity Center, Security Hub/GuardDuty/CloudTrail, SIEM Integration, DR Baseline, Network Infrastructure, Environment Onboarding, CI/CD GitOps Pipeline, Config & Ops Guide — all accepted by Week 12.
- Deliverables 18–25 (Phase 3): Test Plan, Test Results/Evidence Package, DR Failover Report, Operational Runbooks, Knowledge Transfer, Administrator Training, Optimisation Roadmap, Project Closeout Report — all accepted by Week 16.
*Key Highlights:*
- IaC Module Library: 14 reusable Terraform modules committed to Git; Contoso Financial owns the repository post-handover.
- ISO 27001 compliance evidence package: formatted for direct regulatory submission; includes Config conformance reports, CloudTrail attestation, GuardDuty findings report, Security Hub trend analysis, DR test results.
- Knowledge Transfer: four sessions delivered (IaC/AFT, Guardrail Management, Security Hub/Compliance Evidence, IAM Identity Center Operations) — all recorded and delivered.

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Test cases executed: 100% of plan
  Critical defects at go-live: 0
  SCP denial tests: all passed (100%)
  Config rule fire time: <60s (target: <60s)
  SIEM forwarding latency: <3 min (target: <5 min)
Performance Metrics
  Platform availability: 99.9% (target: 99.9%)
  Account provisioning time: <2h (target: <4h)
  DR drill RTO: 3h 20min (target: <4h)
  DR drill RPO: 42 min (target: <1h)
  Security Hub → SIEM: <3 min (target: <5 min)
AWS Cloud Governance Platform — Contoso Financial
Notes: *Talking Points:*
- Quality was not an afterthought — it was embedded into the delivery process from Phase 1 through structured test planning.
- Every SOW success metric has been validated and met or exceeded.
- The CISO sign-off on all controls before go-live (Milestone M8) is the authoritative acceptance gate.
*Detailed Metrics:*
- SCP validation: 12 distinct prohibited actions tested across production OUs — all resulted in `AccessDenied` with corresponding CloudTrail entries in the Log Archive account.
- Config rule validation: deliberate non-compliant configurations introduced in a test account (unencrypted S3 bucket, open security group, disabled CloudTrail) — all detected within 45 seconds and remediated automatically for applicable rules.
- Break-glass procedure tested end-to-end: time-limited access granted in <10 minutes, SIEM alert generated, full CloudTrail log captured.
- Account provisioning load test: 5 concurrent AFT vending requests processed without throttling — all accounts provisioned and baseline-applied within 90 minutes.
- DR drill details: ap-southeast-2 primary simulated failure at 09:00 AEST; ap-southeast-4 DR governance platform fully operational by 12:20 AEST (3h 20min RTO). Log Archive replication lag measured at 42 minutes (RPO).
- Platform availability measured over a 30-day post-go-live observation window — zero platform outages recorded.
*SOW Success Metric Alignment:*
- Zero compliance findings from Q2 2026 regulatory review: on track — ISO 27001 evidence package accepted by CISO.
- 80% reduction in audit remediation effort: baseline 3–4 findings/quarter; post-go-live: zero findings in first cycle.
- 100% production accounts under SCPs with no manual console access: confirmed.
- All new provisioning via AFT pipeline with ITSM gate: confirmed — 3 production environments onboarded via AFT.
- IAM Identity Center live; zero shared credentials: confirmed — on-premises IdP federated; all IAM users retired.
- DR RTO < 4h and RPO < 1h: confirmed by drill results.

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Audit Remediation Effort | 80% reduction | 80% reduction (0 findings) | Platform team capacity freed
Account Provisioning Time | < 4 hours | < 2 hours | Faster environment delivery
Console Access in Production | 0 manual sessions | 0 (SCP enforced) | Eliminated credential risk
Compliance Findings/Quarter | 0 (post go-live) | 0 (first cycle) | Clean regulatory review
SIEM Alert Latency | < 5 minutes | < 3 minutes | Faster incident response
DR Recovery Time (RTO) | < 4 hours | 3h 20min | Confirmed resilience
Data Sovereignty Coverage | 100% in-country | 100% (AU regions only) | Regulatory obligation met
Shared Credentials Retired | 100% | 100% (IdP federation live) | Zero credential-sharing risk
AWS Cloud Governance Platform — Contoso Financial
Notes: *Talking Points:*
- Benefits are already being realised — the first post-go-live audit cycle produced zero findings.
- This is the core business case that drove the engagement: protect the April 2026 regulatory review.
- Every benefit row maps directly to a SOW Success Metric or Key Outcome.
*Detailed Impact:*
- Audit remediation effort: the platform team previously spent an estimated 15–20 hours per finding per quarter across 3–4 findings. At 80% reduction, this represents ~50–60 hours/quarter returned to strategic work.
- Account provisioning: the previous manual process took "days" (SOW Background). AFT pipeline provisions in under 2 hours — a reduction of at least 75–80% in calendar time, with zero manual steps.
- Compliance findings: the first post-go-live Config conformance run across all accounts produced zero non-compliant findings — all previously identified gaps were remediated during Phase 2.
- SIEM latency: measured end-to-end (Security Hub finding generated to SIEM correlation alert) at an average of 2 minutes 47 seconds across 50 test events.
- ROI timeline: SOW projected ongoing audit remediation avoidance of $420K+ per year (benchmark from success story, proportionally adjusted). Net Year 1 investment $409,830. Payback period approximately 12 months.
- Data sovereignty: region-lock SCP confirmed blocking all non-ap-southeast-2/4 API calls in production OUs — tested with 8 API calls to disallowed regions, all denied.
*Future Benefit Projections:*
- Year 2+ cloud run cost: ~$34,130/year — significant reduction from Year 1 as MAP and partner credits do not recur.
- Guardrail maturity: as the Config rule library is extended post-handover, compliance posture will continue to improve without additional implementation cost.
- Phase 2 opportunity (see Slide 7): expanding AFT coverage to developer sandbox accounts and implementing FinOps dashboards are the highest-priority near-term enhancements.

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  CISO sign-off gate before Phase 2 prevented rework
  IaC-first approach accelerated all environment builds
  Evidence collection automated from day one of Phase 2
  AFT pipeline reduced onboarding time significantly
  Phased cutover (3 environments over 3 days) de-risked go-live
Challenges Overcome
  Direct Connect lead time: mitigated with VPN fallback in Phase 2
  On-prem IdP attribute mapping: resolved via additional workshop
Recommendations
  Extend AFT coverage to developer sandbox accounts
  Implement FinOps dashboards (AWS Cost Explorer + budgets)
  Add PCI-DSS conformance pack as next compliance framework
  Schedule quarterly CISO-led compliance evidence reviews
  Engage Amatra Managed Services for ongoing CloudOps
AWS Cloud Governance Platform — Contoso Financial
Notes: *What Worked Well — Details:*
- CISO sign-off gate (Milestone M3, end of Week 6): by requiring formal CISO acceptance of the architecture before Phase 2 began, we avoided mid-build design changes. This is a best practice for all regulated financial services engagements.
- IaC-first approach: using AFT and Terraform for all account and guardrail provisioning meant every environment was born compliant — there were no "catch-up" remediation tasks in Phase 3.
- Evidence collection from day one of Phase 2: Config conformance packs were deployed in the first week of Phase 2, meaning 6 weeks of continuous compliance data was available when the evidence package was compiled in Phase 3.
- Phased cutover: onboarding one production environment per day across 3 days (Week 15) allowed the team to validate each cutover fully before proceeding to the next. No rollbacks were required.
*Challenges Overcome — Details:*
- Direct Connect lead time: Contoso Financial ordered the ap-southeast-4 Direct Connect circuit 2 weeks later than the SOW dependency required (Dependency #1). Amatra stood up a Site-to-Site VPN as a fallback during Phase 2, enabling federation configuration and SIEM integration to proceed without delay. The Direct Connect circuit was provisioned before Phase 3 DR testing.
- On-prem IdP attribute mapping: the on-premises directory's group structure required a non-standard attribute mapping to IAM Identity Center groups. An additional 2-hour workshop with the IdP team (beyond the Week 11 session) was required to resolve. No timeline impact.
*Recommendations — Prioritised:*
1. **AFT expansion to dev sandboxes (Next 30 days):** Low effort, high consistency benefit — eliminates manual developer account setup.
2. **FinOps dashboards (Next 60 days):** AWS Cost Explorer tags are already applied; adding budget alerts and anomaly detection is a low-cost enhancement.
3. **PCI-DSS conformance pack (Next Quarter):** Contoso Financial's card payment workloads may benefit; a scoping exercise is recommended before commitment.
4. **Quarterly compliance evidence reviews (Ongoing):** Establish a rhythm of CISO-led reviews using the Security Hub dashboard and Config compliance reports — no additional tooling required.
5. **Managed Services (Next Quarter):** Refer to Amatra's Managed Services Agreement for ongoing CloudOps, guardrail management, and compliance monitoring post-hypercare.

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 17–24)
  Dedicated Amatra delivery team on-call
  2-hour P1 response (compliance-blocking issues)
  Next-business-day P2 response
  Covers April 2026 regulatory review window
  Guardrail tuning and SIEM alert refinement in scope
Transition to Self-Sufficiency
  Four knowledge transfer sessions completed
  All sessions recorded and delivered to Priya Nair
  Operational runbooks accepted by platform team
  IaC Git repository transferred to Contoso Financial
Steady State (Post-Week 24)
  Platform team operates independently
  Quarterly CISO-led compliance evidence reviews
  Monthly CloudWatch dashboard reviews recommended
Escalation Contacts
  P1/P2: delivery@amatra.com.au | +61 2 9000 0000
  Account Manager: accounts@amatra.com.au
AWS Cloud Governance Platform — Contoso Financial
Notes: *Hypercare Coverage Details:*
- Hypercare scope (from SOW Section 9): triage and resolution of post-go-live defects, guardrail tuning, SIEM alert correlation refinement, regulatory review evidence query assistance, advisory support for new account vending requests.
- Out of scope during hypercare: new features, additional integrations, compliance frameworks not in the original SOW scope. These require a change order or a new engagement.
- Business hours: 09:00–17:00 AEST, Monday to Friday. For P1 issues outside business hours, the on-call contact is the delivery@amatra.com.au email (monitored for P1 severity).
- Hypercare end: Week 24 final handover call with Priya Nair and Rachel Moore to confirm platform stability, all hypercare items resolved, and platform team self-sufficiency.
*Knowledge Transfer Completion:*
- Session 1 — IaC Pipeline & Account Vending (4 hours): completed Week 15. Attended by Platform Engineers.
- Session 2 — Guardrail Management (3 hours): completed Week 15. Attended by Platform Engineers + CISO.
- Session 3 — Security Hub & Compliance Evidence (3 hours): completed Week 16. Attended by Platform Engineers + CISO.
- Session 4 — IAM Identity Center Operations (2 hours): completed Week 16. Attended by Platform Engineers + CISO.
- All sessions recorded; recordings and slide decks delivered to Priya Nair's SharePoint.
*Steady State Recommendations:*
- Monthly: review CloudWatch platform health dashboards (AFT pipeline success rate, Config evaluation errors, GuardDuty finding volumes).
- Quarterly: CISO-led compliance evidence review using Security Hub and Config compliance reports.
- Annually: access review — IAM Identity Center permission set assignments reviewed against current role requirements.
- Change process: all SCP and Config rule changes must be raised via ITSM, reviewed by the Security Engineer role, approved by the CISO, and deployed via the AFT pipeline — no console changes.
*Post-Hypercare Options:*
- Managed Services Agreement: Amatra can provide ongoing CloudOps, guardrail management, and compliance monitoring under a separate MSA. Contact accounts@amatra.com.au to scope.

## Slide 9
Slide 9: Acknowledgments & Next Steps
James Wu (CTO) — executive sponsorship and decisive governance support
Priya Nair (Head of Platform Engineering) — technical leadership and knowledge transfer
Contoso Financial CISO — security rigour and timely architecture sign-off
Rachel Moore (IT Delivery Manager) — project coordination and milestone delivery
This Week: Final documentation handover and repository transfer
Next 30 Days: Hypercare support with 2-hour P1 response
Before April 30: Regulatory review with full evidence package ready
AWS Cloud Governance Platform — Contoso Financial
Notes: *Acknowledgment Talking Points:*
- This was a genuine partnership — the April 2026 regulatory deadline demanded close collaboration on both sides and the Contoso Financial team delivered on every critical-path dependency.
- James Wu's executive sponsorship meant escalations were resolved quickly — no decision sat unresolved for more than 48 hours.
- Priya Nair's 25% time commitment (as specified in the SOW assumptions) was honoured throughout the engagement — her technical engagement was essential for architecture decisions and UAT.
- The CISO's timely sign-off at Week 4 (architecture gate) and Week 15 (UAT gate) was the single most important client-side action in protecting the April 2026 deadline.
- Rachel Moore's coordination of ITSM change windows, Direct Connect circuit chasing, and IdP team availability kept Phase 2 on track despite the Direct Connect delay.
*Next Steps Timeline:*
- This week: Amatra to transfer the IaC Git repository to Contoso Financial's GitHub organisation; deliver final project closeout report; confirm hypercare escalation contacts with platform team.
- Next 30 days (Weeks 17–20): Hypercare active; focus on guardrail tuning, SIEM alert refinement, and any post-go-live defect resolution.
- Before April 30, 2026: Regulatory review window — Amatra available under hypercare to assist with any audit queries or evidence supplementation.
- Week 24: Final hypercare handover call; confirm platform team self-sufficiency; agree any Phase 2 roadmap next steps.
- Optional (Next Quarter): Phase 2 scoping workshop — AFT expansion, FinOps dashboards, PCI-DSS conformance pack.

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion.
- Have this document's speaker notes available for deep-dive questions on budget, metrics, and architecture.
- Offer to schedule a follow-up session specifically on Phase 2 roadmap planning if there is executive appetite.
- Remind Priya Nair of the hypercare escalation path — delivery@amatra.com.au for P1/P2 issues starting today.
- End on a positive note: the platform is live, the regulatory review is covered, and Contoso Financial now owns a best-practice cloud governance foundation that will serve the organisation for years.
*Backup Detail Topics (if asked):*
- Budget breakdown by phase: Discovery ~$83,600 | Architecture ~$57,700 | Build ~$166,100 | Testing ~$55,700 | Hypercare ~$44,500 | Management ~$74,800.
- Credit details: $30,000 in professional services credits (APN $10K + MAP $15K + volume discount $5K); $29,200 in cloud credits (MAP infrastructure $15K + Solutions Partner $5K + Reserved Instance savings $8K + Terraform partner credit $1.2K).
- 3-year TCO: $478,090 total (Year 1 net $409,830 + Year 2 $34,130 + Year 3 $34,130).
- Managed Services: separate MSA available for ongoing CloudOps post-hypercare — contact accounts@amatra.com.au.