## Cover
Level of Effort
Generated: | June 04, 2026
Solution: | Tmpwj0_95K9
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Agents / Workflows | Single-agent workflow | 5 agents (Input Validator; Pre-Sales Generator; Delivery Generator; Code Generator; EO Validator) | 1-2 agents | 3-5 agents | 6+ agents | Multi-agent Strands graph with Bedrock AgentCore Runtime
Artifacts per Solution | 3-5 artifacts per solution | 12 artifacts per solution (5 presales + 6 delivery + 1 automation bundle) | 3-5 artifacts | 6-9 artifacts | 10-12 artifacts | Includes Terraform automation bundle with terraform validate gate
API Routes / CLI Subcommands | 5 Lambda routes + 5 CLI subcommands | 11 Lambda routes + 14 CLI subcommands behind API GW HTTP API v2 | 5 routes / 5 cmds | 8 routes / 8 cmds | 11+ routes / 14+ cmds | JWT-protected via Cognito User Pools with 30-day refresh tokens
Environments | Single production environment | 3 environments (dev / staging / prod) | 1 environment | 2 environments | 3 environments | us-west-2 greenfield footprint; isolated from existing us-east-1 workloads
Validation & Retry Logic | Single-pass validation | Deterministic format-check + LLM quality check with up to 3 retries per artifact | 1 pass | 2 passes | 3 retries per artifact | Haiku 4.5 for validation; Sonnet 4.6 for generation
Integrations | None | 3 integrations (GitHub PAT commit; DynamoDB quota enforcement; eof-tools converter pipeline) | 1 integration | 2 integrations | 3 integrations | eof-tools ~30 Python modules baked into container image
User Scale / Quotas | No quota enforcement | Per-user quota 10 solutions/month; global pool 1000 solutions/month enforced atomically in DynamoDB | Up to 50 users | 50-200 users | 200+ users | Cognito MAU-based; post-confirmation trigger Lambda for user profiles
Compliance / Observability | Basic logging only | CloudWatch metrics baseline; per-phase token usage in CLI + admin API; graded artifact delivery policy | Basic CloudWatch | Enhanced monitoring | Full observability + token reporting | Green CloudWatch baseline required before Phase 3 sign-off

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Baseline for stakeholder interviews; requirements gathering; current-state review of eof-tools library
Planning | planning_factor | 1.2 | Elevated for detailed architecture design; multi-agent graph design; Cognito + API GW; container pipeline design
Development | development_factor | 1.3 | Elevated for 5-agent implementation; 14 CLI subcommands; 11 Lambda routes; Docker image pipeline; eof-tools integration
Testing | testing_factor | 1.1 | End-to-end artifact validation across 12 artifact types; Terraform validate gate; CloudWatch baseline verification
Deployment | deployment_factor | 1 | Baseline for production deployment; knowledge transfer; runbook delivery; 4-week hypercare support
Management | management_factor | 1 | Project management and technical leadership overhead (10% of engineering tasks)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Kickoff meeting with Sarah Lin; Marcus Patel; Daniel Park — align on scope; objectives and timeline | Project Manager | 8 | 1 | 8 | 175 | 1400 |  | Week 1
Discovery | Current State Assessment | Document legacy Claude Code CLI workflow; map eof-tools library modules (~30 Python modules covering 12 artifact types) | Solution Architect | 24 | 1 | 24 | 225 | 5400 |  | Basis for eof-tools integration design
Discovery | Requirements Gathering | Conduct stakeholder interviews; document 14 CLI subcommands; 11 API routes; 5-agent specs; quota and auth requirements | Solution Architect | 32 | 1 | 32 | 225 | 7200 |  | Inputs to Planning phase
Discovery | Cloud Readiness Assessment | Review existing us-east-1 footprint; plan us-west-2 greenfield provisioning; assess Bedrock and AgentCore service limits | Cloud Engineer | 16 | 1 | 16 | 200 | 3200 |  | Informs infrastructure architecture
Discovery | AI/ML Capability Assessment | Evaluate Bedrock model selection (Sonnet 4.6 / Haiku 4.5); assess token throughput; per-solution cost targeting under $5 model spend | ML/AI Engineer | 20 | 1 | 20 | 250 | 5000 |  | Informs agent design and cost model
Discovery | Gap Analysis | Identify gaps between legacy manual process and target agentic automation; document deferred scope items | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Current State Assessment
Discovery | Risk Assessment | Identify risks: Bedrock quota limits; AgentCore cold-start latency; GitHub PAT rotation; DynamoDB hot-partition risk | Project Manager | 8 | 1 | 8 | 175 | 1400
Discovery | Assessment Report | Document findings; recommended architecture; phased delivery plan aligned to Q2 2026 timeline | Technical Writer | 16 | 1 | 16 | 125 | 2000 | Gap Analysis | Deliverable for CTO review
Planning | Detailed Architecture Design | Design multi-agent Strands graph: Agent 0 Input Validator; Pre-Sales Generator; Delivery Generator; Code Generator; EO Validator agents with AgentCore Runtime hosting | Solution Architect | 48 | 1.2 | 58 | 225 | 13050 | Assessment Report | Critical path — CTO sign-off required
Planning | AWS Foundation Design | Design us-west-2 account structure; VPC; IAM roles and policies; S3 bucket layout; DynamoDB table design with GSIs for quota enforcement | Cloud Engineer | 40 | 1.2 | 48 | 200 | 9600 | Detailed Architecture Design
Planning | Cognito & Auth Design | Design Cognito User Pool; app client; JWT token settings (30-day refresh); post-confirmation Lambda trigger; API GW HTTP API v2 authoriser | Security Engineer | 32 | 1.2 | 38 | 225 | 8550 | Detailed Architecture Design | Rate includes security cert premium
Planning | API Gateway & Lambda Architecture | Design 11 Lambda route handlers; API GW HTTP API v2 stage; throttling; CORS; request and response schemas for all 14 CLI subcommands | Solutions Engineer | 32 | 1.2 | 38 | 200 | 7600 | Cognito & Auth Design
Planning | Agent Orchestration Design | Design Strands agent graph topology; inter-agent messaging; graded artifact delivery policy; per-phase token usage tracking; retry logic up to 3 retries per artifact | ML/AI Engineer | 40 | 1.2 | 48 | 250 | 12000 | Detailed Architecture Design
Planning | Container Image Pipeline Design | Design Docker image architecture for eof-tools integration; ECR repository; image build pipeline; AgentCore Runtime registration workflow | DevOps Engineer | 24 | 1.2 | 29 | 200 | 5800 | Agent Orchestration Design
Planning | Security Baseline Design | Design IAM least-privilege policies; Secrets Manager for GitHub PAT; CloudTrail; WAF for API Gateway; DynamoDB encryption at rest | Security Engineer | 24 | 1.2 | 29 | 225 | 6525 | AWS Foundation Design
Planning | Monitoring & Observability Design | Design CloudWatch dashboards; per-phase token usage metrics; alarms for quota thresholds; structured logging schema for all agents | DevOps Engineer | 20 | 1.2 | 24 | 200 | 4800 | Agent Orchestration Design
Planning | Design Documentation | Produce architecture diagrams; sequence diagrams for agent flows; data flow diagrams; API specification in OpenAPI format | Technical Writer | 24 | 1.2 | 29 | 125 | 3625 | All Planning tasks | Inputs to Statement of Work
Development | Foundation Infrastructure | Provision Cognito User Pool; DynamoDB tables (user profiles + quota counters); S3 buckets; IAM roles; API GW HTTP API v2 — Phase 1 Weeks 1-4 | Cloud Engineer | 48 | 1.3 | 62 | 200 | 12400 | AWS Foundation Design | Phase 1 deliverable
Development | Post-Confirmation Lambda | Develop Cognito post-confirmation trigger Lambda; DynamoDB user profile write on registration; unit tests | Solutions Engineer | 16 | 1.3 | 21 | 200 | 4200 | Foundation Infrastructure
Development | Agent 0 — Input Validator | Develop Input Validator agent; brief parsing; schema validation; error surfacing; integration with Strands framework | ML/AI Engineer | 32 | 1.3 | 42 | 250 | 10500 | Agent Orchestration Design | Phase 2 Weeks 5-9
Development | Pre-Sales Generator Agent | Develop Pre-Sales Generator agent; 5-artifact workflow (solution briefing; infra costs; LOE; SoW; proposal); LLM prompting with Sonnet 4.6; format-check integration | ML/AI Engineer | 48 | 1.3 | 62 | 250 | 15500 | Agent 0 — Input Validator
Development | Delivery Generator Agent | Develop Delivery Generator agent; 6-artifact workflow (project charter; implementation plan; RAID log; runbooks; test plan; closure report) | ML/AI Engineer | 40 | 1.3 | 52 | 250 | 13000 | Pre-Sales Generator Agent
Development | Code Generator Agent | Develop Code Generator agent; Terraform IaC templates for 5 core AWS services; terraform validate gate; output bundled as automation artifact | ML/AI Engineer | 40 | 1.3 | 52 | 250 | 13000 | Delivery Generator Agent
Development | EO Validator Agent | Develop EO Validator agent; deterministic format-check pass; LLM quality check using Haiku 4.5; up to 3 retries per artifact; pass/fail envelope | ML/AI Engineer | 32 | 1.3 | 42 | 250 | 10500 | Pre-Sales Generator Agent
Development | eof-Tools Integration | Integrate eof-tools converter pipeline (~30 Python modules) into Docker container image; test DOCX/PPTX/XLSX conversion for all 12 artifact types | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | Container Image Pipeline Design | Key existing asset — must not be rewritten
Development | Docker Image & ECR Pipeline | Build multi-stage Dockerfile; ECR push workflow; AgentCore Runtime image registration; image tagging and versioning strategy | DevOps Engineer | 32 | 1.3 | 42 | 200 | 8400 | Container Image Pipeline Design
Development | CLI Development — 14 Subcommands | Develop pip-installable CLI; 14 subcommands (auth login/logout; solution generate; solution status; artifact download; admin usage); JWT token handling | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | Foundation Infrastructure
Development | Lambda Route Handlers — 11 Routes | Develop 11 JWT-protected Lambda handlers (solution create; status; artifact fetch; user profile; quota check; admin usage); request validation; error handling | Solutions Engineer | 40 | 1.3 | 52 | 200 | 10400 | Foundation Infrastructure
Development | DynamoDB Quota Enforcement | Implement atomic per-user 10/month and global 1000/month quota counters using DynamoDB conditional writes; overflow error handling | Solutions Engineer | 16 | 1.3 | 21 | 200 | 4200 | Foundation Infrastructure
Development | GitHub Integration | Implement GitHub PAT-based commit workflow; solution artifact bundle commit to fixed public repository; branch strategy | Solutions Engineer | 16 | 1.3 | 21 | 200 | 4200 | eof-Tools Integration
Development | CloudWatch Observability Implementation | Implement per-phase token usage metrics emission; structured log groups; CloudWatch dashboards; quota alarm notifications | DevOps Engineer | 24 | 1.3 | 31 | 200 | 6200 | Monitoring & Observability Design | Phase 3 prerequisite
Development | Security Hardening | Implement Secrets Manager for GitHub PAT; WAF rules on API GW; CloudTrail for audit; DynamoDB KMS encryption; Cognito MFA option | Security Engineer | 24 | 1.3 | 31 | 225 | 6975 | Security Baseline Design
Development | Configuration Documentation | Document all Lambda environment variables; DynamoDB table schemas; S3 bucket policies; Cognito app client settings | Technical Writer | 32 | 1.3 | 42 | 125 | 5250 | All Development tasks
Testing | Test Plan Development | Create comprehensive test plan covering agent workflows; CLI commands; API routes; quota enforcement; converter pipeline; Terraform validation | QA Engineer | 16 | 1.1 | 18 | 150 | 2700 | All Development tasks | Phase 3 Weeks 10-12
Testing | Unit Testing — Agent Logic | Execute unit tests for all 5 agent modules; mock Bedrock calls; validate input/output schemas; retry logic coverage | Solutions Engineer | 24 | 1.1 | 26 | 200 | 5200 | All Development tasks
Testing | Integration Testing — End-to-End Artifacts | Execute end-to-end artifact generation for all 12 artifact types; validate format-check pass; LLM quality check; converter pipeline output (DOCX/PPTX/XLSX) | ML/AI Engineer | 32 | 1.1 | 35 | 250 | 8750 | eof-Tools Integration | Critical — must pass before Phase 3 sign-off
Testing | API Route Testing | Test all 11 Lambda routes via CLI and HTTP client; JWT auth validation; error response codes; rate limiting behaviour | Solutions Engineer | 20 | 1.1 | 22 | 200 | 4400 | Lambda Route Handlers — 11 Routes
Testing | Terraform Validate Gate Testing | Validate Terraform IaC output for all 5 core AWS services passes terraform validate; test error surfacing on syntax failures | Solutions Engineer | 12 | 1.1 | 13 | 200 | 2600 | Code Generator Agent
Testing | Performance & Quota Testing | Load test quota enforcement (concurrent solution submissions); verify atomic DynamoDB writes under contention; measure per-solution latency (target under 60 minutes) | Solutions Engineer | 20 | 1.1 | 22 | 200 | 4400 | DynamoDB Quota Enforcement
Testing | Security Testing | Perform JWT validation bypass attempts; API GW WAF rule verification; IAM privilege escalation checks; Secrets Manager access control validation | Security Engineer | 16 | 1.1 | 18 | 225 | 4050 | Security Hardening
Testing | CloudWatch Baseline Validation | Verify green CloudWatch metrics baseline; validate per-phase token usage reporting in CLI status command and admin usage endpoint | DevOps Engineer | 12 | 1.1 | 13 | 200 | 2600 | CloudWatch Observability Implementation | Gate for Phase 3 completion
Testing | UAT Coordination | Coordinate UAT with Marcus Patel (Pre-Sales Engineering); execute representative presales bundle generation; review output with Sarah Lin (CRO) | Project Manager | 16 | 1.1 | 18 | 175 | 3150 | Integration Testing — End-to-End Artifacts
Testing | Defect Resolution | Address and resolve defects identified during testing phases; regression testing after fixes; 10% contingency buffer | Solutions Engineer | 24 | 1.1 | 26 | 200 | 5200 | Test Plan Development
Testing | Test Results Report | Document test results; sign-off checklist; known limitations; deferred items for Phase 2 engagement | QA Engineer | 8 | 1.1 | 9 | 150 | 1350 | Defect Resolution
Deployment | Go-Live Planning | Plan production cutover approach; rollback procedures; CloudWatch alarm thresholds; stakeholder communication plan | Project Manager | 8 | 1 | 8 | 175 | 1400 | Test Results Report
Deployment | Production Deployment | Deploy all infrastructure (Cognito; API GW; Lambda; DynamoDB; S3; AgentCore) to production us-west-2 via Terraform; smoke test | Cloud Engineer | 24 | 1 | 24 | 200 | 4800 | Go-Live Planning | CTO sign-off required pre-deployment
Deployment | CLI Package Publishing | Publish pip-installable CLI to internal or public PyPI; versioning and changelog documentation | DevOps Engineer | 8 | 1 | 8 | 200 | 1600 | Production Deployment
Deployment | Runbook Development | Create operational runbooks: agent failure recovery; quota reset procedures; GitHub PAT rotation; AgentCore image update process | Technical Writer | 24 | 1 | 24 | 125 | 3000 | Production Deployment
Deployment | Knowledge Transfer Sessions | Conduct training sessions for Marcus Patel Pre-Sales Engineering team; Daniel Park Delivery Operations team; CLI usage; admin API; quota management | Trainer | 24 | 1 | 24 | 150 | 3600 | Runbook Development
Deployment | Documentation Delivery | Deliver as-built architecture documentation; API reference; CLI command reference; operator guide; user onboarding guide | Technical Writer | 16 | 1 | 16 | 125 | 2000 | Runbook Development
Deployment | Hypercare Support | 4-week post-go-live hypercare support; incident triage; agent prompt tuning; quota adjustment; GitHub commit troubleshooting | Support Engineer | 40 | 1 | 40 | 150 | 6000 | Production Deployment | 4-week medium-complexity hypercare
Deployment | Optimization Recommendations | Document Phase 2 roadmap recommendations: parallel pipeline throughput; multi-region expansion; additional artifact types; cost optimisation at 200 solutions/month | Solution Architect | 16 | 1 | 16 | 225 | 3600 | Hypercare Support
Deployment | Project Closeout | Project retrospective with Sarah Lin; Marcus Patel; Daniel Park — lessons learned; 90% effort-reduction metric validation; formal acceptance | Project Manager | 8 | 1 | 8 | 175 | 1400 | Optimization Recommendations
Management | Technical Leadership | Quarterback technical oversight across all phases: architecture decisions; agent design reviews; Bedrock model governance; CTO briefings |  | 1 |  | 225 |  |  | 10% of engineering tasks (rows 3-62)
Management | Project Management | Project coordination; weekly status reporting; risk log maintenance; budget tracking; procurement liaison for AWS spend envelope |  | 1 |  | 175 |  |  | 10% of engineering tasks (rows 3-62)
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -15000 | AWS Partner Network (APN) Advanced Tier credit for Bedrock and AgentCore solution architecture and implementation services — applied to Year 1 professional services
AWS Generative AI Competency Incentive | -5000 | AWS Generative AI competency partner incentive for validated multi-agent Bedrock implementations — eligibility subject to APN competency verification
Volume Implementation Discount | -5000 | Strategic account discount on professional services for 12-week fixed-scope engagement — approximately 2% of total services value
TOTAL |  | Total professional services cost minus AWS Partner and volume credits — reflects Year 1 billable amount to PREDICTif Solutions