## Cover
Level of Effort
Generated: | June 08, 2026
Solution: | Tmpiwfaanry
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Accounts in Scope | Single business unit | Small faith-based streaming user base at launch | <500 users | 500-5000 users | 5000+ users | Initial launch; growth expected post-engagement
AI Endpoints / Models | 1 REST API endpoint | 2 endpoints (mood classifier + recommendation) | 1-2 endpoints | 3-5 endpoints | 6+ endpoints | Mood-classification and playlist recommendation endpoints
AWS Managed Services | Core AI/ML services only | Lambda, Bedrock, API Gateway, DynamoDB | 2-3 services | 4-6 services | 7+ services | No self-managed ML infrastructure required
Environments | Dev and Prod | Dev + Prod (no dedicated QA env) | Dev + Prod | Dev + Staging + Prod | Dev + Staging + Prod + DR | Firebase remains for frontend data
Integration Points | Single source system | Firebase catalog (read-only) + FlutterFlow API calls | 1 integration | 2-3 integrations | 4+ integrations | No mobile frontend changes required
Data Volume / Catalog Size | Small catalog | Existing catalog with lyrics and transcripts | <1000 tracks | 1000-10000 tracks | 10000+ tracks | Existing tags and text used for mood inference
Compliance / Security | Standard AWS security baseline | IAM least privilege + API key auth + HTTPS only | Standard baseline | SOC2 alignment | Full compliance audit | No HIPAA or PCI requirements identified

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Baseline for stakeholder interviews and AWS architecture design
Planning | planning_factor | 1 | Solution design and detailed technical planning for two AI endpoints
Development | development_factor | 1 | Lambda and Bedrock implementation plus API Gateway and DynamoDB configuration
Testing | testing_factor | 1 | Functional and integration testing of mood-classification and recommendation endpoints
Deployment | deployment_factor | 1 | Production deployment plus API documentation and knowledge transfer
Management | management_factor | 1 | Project management and technical leadership overhead (10% of engineering hours)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Project kickoff meeting with Lilly Goyah and nClouds team to align on goals and timeline | Project Manager | 4 | 1 |  | 175 |  |  | Short engagement with single executive stakeholder
Discovery | Current State Assessment | Review existing Firebase catalog structure (titles, artists, lyrics, transcripts) and FlutterFlow API patterns | Solution Architect | 8 | 1 |  | 225 |  | Project Kickoff | Read-only Firebase access; no migration in scope
Discovery | Requirements Gathering | Document functional requirements for mood-classification and playlist recommendation endpoints | Solution Architect | 8 | 1 |  | 225 |  | Current State Assessment | Two endpoints confirmed; input/output schemas to be agreed
Discovery | AWS Architecture Design | Design AWS architecture using Lambda, Bedrock, API Gateway, and DynamoDB for both endpoints | Solution Architect | 16 | 1 |  | 225 |  | Requirements Gathering | Leverage AWS managed services; no self-managed models
Discovery | Data Assessment | Assess catalog text data quality (lyrics and transcripts) for mood-inference readiness via Bedrock | ML/AI Engineer | 8 | 1 |  | 250 |  | Current State Assessment | Confirm Bedrock model suitability for faith-based content
Discovery | Risk Assessment | Identify project risks covering data quality gaps, Firebase connectivity, and AWS account readiness | Project Manager | 4 | 1 |  | 175 |  | AWS Architecture Design | Short timeline increases risk; mitigations documented
Discovery | Discovery Summary Report | Document architecture decision record and confirmed scope for client review and sign-off | Solution Architect | 6 | 1 |  | 225 |  | Risk Assessment | Deliverable reviewed by client within 3 working days
Planning | Detailed Architecture Specification | Produce detailed design specs for both API endpoints including request/response schemas, auth, and error handling | Solution Architect | 12 | 1 |  | 225 |  | Discovery Summary Report | Input to development and API documentation
Planning | AWS Environment Setup | Provision AWS account baseline: IAM roles, API Gateway, Lambda, and DynamoDB tables for Dev and Prod | Cloud Engineer | 12 | 1 |  | 200 |  | Detailed Architecture Specification | IaC via CloudFormation or CDK; Dev and Prod environments
Planning | Security Baseline Configuration | Configure IAM least-privilege policies, API key authentication, HTTPS enforcement, and CloudWatch logging | Security Engineer | 8 | 1 |  | 200 |  | AWS Environment Setup | Standard AWS security baseline per engagement brief
Planning | Bedrock Model Selection and Prototyping | Evaluate and prototype Amazon Bedrock foundation model for mood/emotion classification on faith-based content | ML/AI Engineer | 12 | 1 |  | 250 |  | AWS Environment Setup | Select model suitable for lyric and transcript content
Development | Mood Classification Endpoint | Implement Lambda function invoking Bedrock to classify mood/emotion from lyrics or transcript text | ML/AI Engineer | 20 | 1 |  | 250 |  | Bedrock Model Selection and Prototyping | POST /classify endpoint returning mood label and confidence score
Development | Recommendation Endpoint | Implement Lambda function querying DynamoDB to return personalized playlist by mood and listening history | ML/AI Engineer | 20 | 1 |  | 250 |  | Mood Classification Endpoint | GET /recommend endpoint using DynamoDB for user history lookup
Development | API Gateway Configuration | Configure API Gateway routes, request validation, throttling, and API key authorization for both endpoints | Solutions Engineer | 12 | 1 |  | 200 |  | Mood Classification Endpoint | REST API only; no frontend changes required
Development | DynamoDB Schema and Data Load | Design and provision DynamoDB tables for catalog mood tags and user listening history; load seed data from Firebase | Solutions Engineer | 10 | 1 |  | 200 |  | AWS Environment Setup | Seed from existing Firebase catalog metadata
Development | Auto-Tagging Pipeline | Implement batch Lambda to auto-tag new catalog uploads with mood/emotion labels via Bedrock | ML/AI Engineer | 16 | 1 |  | 250 |  | Mood Classification Endpoint | Triggered on new upload events; tags stored in DynamoDB
Development | Monitoring and Alerting Setup | Configure CloudWatch dashboards, Lambda error alarms, and API Gateway latency alerts | Cloud Engineer | 6 | 1 |  | 200 |  | API Gateway Configuration | Operational visibility required for production handover
Development | Infrastructure as Code | Finalize CloudFormation/CDK templates for repeatable Dev and Prod environment deployments | Cloud Engineer | 8 | 1 |  | 200 |  | AWS Environment Setup | Enables reproducible environment provisioning
Testing | Test Plan Development | Create test plan and test cases for both endpoints covering functional, edge cases, and error handling | QA Engineer | 6 | 1 |  | 150 |  | Detailed Architecture Specification
Testing | Functional Testing - Classification | Execute functional tests against /classify endpoint using sample lyric and transcript data | QA Engineer | 8 | 1 |  | 150 |  | Mood Classification Endpoint | Validate mood label accuracy and response format
Testing | Functional Testing - Recommendation | Execute functional tests against /recommend endpoint with varied mood and history inputs | QA Engineer | 8 | 1 |  | 150 |  | Recommendation Endpoint | Validate playlist relevance and DynamoDB query correctness
Testing | Integration Testing | Test end-to-end flow from FlutterFlow API call through API Gateway to Lambda to DynamoDB and back | Solutions Engineer | 10 | 1 |  | 200 |  | API Gateway Configuration | Confirm no frontend changes required and API key flow works
Testing | Security and Auth Testing | Validate IAM policies, API key enforcement, HTTPS-only access, and unauthorized request rejection | Security Engineer | 6 | 1 |  | 200 |  | Security Baseline Configuration
Testing | Model Accuracy Validation | Validate Bedrock mood classification accuracy against representative faith-based content samples | ML/AI Engineer | 8 | 1 |  | 250 |  | Mood Classification Endpoint | Accuracy threshold agreed with client before sign-off
Testing | Defect Resolution | Investigate and resolve defects identified during functional and integration testing cycles | Solutions Engineer | 8 | 1 |  | 200 |  | Functional Testing - Classification | Buffer for minor rework across both endpoints
Deployment | Production Deployment | Deploy finalized Lambda functions, API Gateway, and DynamoDB to Prod environment via IaC | Solutions Engineer | 8 | 1 |  | 200 |  | Defect Resolution | Zero-downtime deployment; rollback procedure documented
Deployment | API Documentation | Produce developer-facing API reference covering endpoint specs, auth, and request/response examples for app team | Solution Architect | 10 | 1 |  | 225 |  | Production Deployment | Key deliverable per brief; enables FlutterFlow team to integrate
Deployment | Runbook Development | Create operational runbook covering monitoring, alarm response, Lambda scaling, and DynamoDB maintenance | Solutions Engineer | 6 | 1 |  | 200 |  | Monitoring and Alerting Setup
Deployment | Knowledge Transfer Session | Conduct live handover session with ANP technical contact covering architecture and operational procedures | Solution Architect | 4 | 1 |  | 225 |  | API Documentation | Single session; ANP provides one technical point of contact
Deployment | Hypercare Support | Provide 2-week post-go-live support for issue resolution and app team integration questions | Support Engineer | 20 | 1 |  | 150 |  | Production Deployment | Small complexity engagement; 2-week hypercare per guidelines
Deployment | Project Closeout | Project retrospective, lessons learned, and final deliverables handover confirmation | Project Manager | 4 | 1 |  | 175 |  | Hypercare Support
Management | Technical Leadership | EO Quarterback technical oversight across all phases of the engagement | Solutions Engineer |  | 1 |  | 200 |  |  | 10% of engineering hours; anti-circular reference pattern
Management | Project Management | Project coordination, status reporting, and stakeholder communication with Lilly Goyah | Project Manager |  | 1 |  | 175 |  |  | 10% of engineering hours; anti-circular reference pattern
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -10000 | AWS Partner Network (APN) credit for solution architecture and implementation services; applicable as nClouds is an AWS Advanced Consulting Partner delivering a qualified AI/ML workload
AWS Partner Funding Credit | -5000 | AWS Partner Funding (APF) credit applied toward professional services for qualified AI/ML build engagements; subject to AWS funding approval prior to project start
TOTAL |  | Total professional services cost after AWS Partner and funding credits applied (Year 1 only)