## Slide 1
Project Closeout
ANP Streaming AI Recommendation Engine
Jonas Bull | June 19, 2026
Notes: *Talking Points:*
- Welcome the ANP Streaming executive team and stakeholders to the formal project closeout
- Acknowledge the collaborative effort between nClouds and the ANP team throughout the engagement
- Today's session covers: achievements, quality metrics, benefits realized, lessons learned, and next steps
- Celebrate a successful delivery — all five SOW phases completed on schedule

## Slide 2
Slide 2: Executive Summary
Project Duration: 13 weeks, completed on schedule
Budget: $25,000 PS fee fully offset by AWS Partner Funding — net cost $0
Go-Live Date: June 19, 2026 as planned (Staging handover complete)
Phases Completed: All 5 phases delivered; all 7 milestones achieved
Accuracy Target Met: ≥90% mood-to-content match accuracy validated
API Performance: Playlist generation ≤2s at 100 MAU load confirmed
Catalog Enriched: Full existing catalog classified at emotion/mood/theme level
Knowledge Transfer: Both formal KT sessions conducted and confirmed
Deliverables: All 27 SOW deliverables accepted by ANP Streaming
Net PS Cost: $0.00 — $25,000 AWS Partner Funding fully applied at kickoff
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- Open with confidence: project delivered on time, on scope, and at zero net PS cost to ANP
- The $25,000 AWS Partner Funding from the APFP program was approved before kickoff; invoices were fully offset at each milestone
- All three milestone invoices — Kickoff ($12,500), M4 ($7,500), and Final ($5,000) — were gross amounts zeroed out by APFP credits
- The 13-week delivery window matches the SOW effective date of March 19, 2026 through June 19, 2026
- ANP now has a fully operational AI/ML backend in the Staging environment, production-ready per SOW scope
*Budget Breakdown:*
- Kickoff Invoice: $12,500 gross / $0 net (50% of PS fee, offset by APFP drawdown 1)
- M4 Invoice: $7,500 gross / $0 net (30% of PS fee, offset by APFP drawdown 2)
- Final Invoice: $5,000 gross / $0 net (20% of PS fee, offset by APFP drawdown 3)
- AWS Activate Founders credit of $2,500 applied to Year 1 infrastructure reducing cost to ~$63
*Quality Highlights:*
- Zero critical defects at Staging handover
- All 27 deliverables formally accepted by Lilly Goyah and ANP Technical Lead within the 3-business-day review window
- Performance test confirmed p95 playlist latency of 1.7s against the ≤2s SLA target

## Slide 3
Slide 3: Solution Architecture
ANP Streaming AI Recommendation Engine
Content Intelligence
  Comprehend + SageMaker NLP classifier
  Audio feature extraction pipeline
  Catalog enrichment at upload time
Recommendation Engine
  Amazon Personalize preference model
  Mood-to-content matching algorithm
  Playlist generation with feedback loop
API & Data Layer
  API Gateway + Cognito (5 endpoints)
  DynamoDB, S3, ElastiCache, OpenSearch
  Step Functions + EventBridge orchestration
Notes: *Talking Points:*
- Walk through the architecture top-to-bottom: Content Intelligence feeds Recommendation Engine; both expose capabilities via the API & Data Layer
- This architecture is fully decoupled from Firebase and FlutterFlow — it's a platform-agnostic AWS-native service that survives any future frontend migration
- All three categories were delivered exactly as specified in the Phase 1 Architecture Package (Deliverable 4)
*Technical Details — Content Intelligence:*
- Amazon Comprehend provides managed NLP for entity, sentiment, and key-phrase extraction from lyric and transcript text
- SageMaker fine-tuned NLP classifier produces emotion, mood, and thematic attribute scores per catalog item
- A second SageMaker endpoint handles audio feature extraction (valence, energy, worship-style vectors)
- Catalog Enrichment Lambda triggers at artist/podcast upload via EventBridge; Step Functions manages the multi-step enrichment workflow with retry logic
*Technical Details — Recommendation Engine:*
- Amazon Personalize serves collaborative-filtering models trained on user preference vectors and interaction events
- Mood-to-content matching algorithm correlates emotional state with multi-attribute content vectors from Content Intelligence
- Playlist Generation Lambda combines Personalize output, mood-matching scores, session context, and feedback signals
- SageMaker Pipelines retraining workflow runs weekly; conditionally promotes new models based on evaluation thresholds
*Technical Details — API & Data Layer:*
- Five secured REST endpoints: user profile/session, content classification, playlist generation, feedback capture, and user preference ingestion
- Cognito JWT authentication enforced at API Gateway Lambda authorizer — FlutterFlow connects with zero frontend changes
- DynamoDB on-demand capacity handles ingest-time write bursts; ElastiCache Redis caches playlists to reduce latency
- OpenSearch Service enables semantic and emotion-attribute-based catalog discovery
*Presales Alignment:*
- Architecture matches Solution Briefing Slide 4 specification exactly
- Services deployed match SOW Section "Architecture & Design — Tooling Overview" — no scope additions
- Amazon Bedrock included per SOW tooling table for lyric/transcript emotion enrichment via FM token inference

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Phase 1 Architecture Package | AWS design, schemas, taxonomy, cost model | `/delivery/detailed-design.md`
Content Intelligence Pipeline | NLP classifier, audio analysis, enrichment service | AWS Staging — SageMaker + Lambda
Recommendation Engine | Personalize model, mood-matcher, playlist service | AWS Staging — SageMaker + Lambda
API Service Layer | 5 secured REST endpoints with Cognito auth | AWS Staging — API Gateway
REST API Contract Documentation | OpenAPI specs for all 5 endpoints | `/delivery/implementation-guide.md`
Operational Runbooks | Deployment, scaling, retraining, incident response | `/delivery/implementation-guide.md`
Test Plan & Validation Report | Test cases, performance results, E2E validation | `/delivery/test-plan.csv`
IaC Templates (CDK/CloudFormation) | Reproducible environment provisioning | `/delivery/scripts/terraform/`
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- All 27 SOW deliverables are included within these eight delivery categories; the table maps primary artifacts to their locations
- The Phase 1 Architecture Package (Deliverables 4–9 bundled) was the first formal milestone — accepted by Lilly Goyah at Week 4
- System deliverables (Pipeline, Engine, API Layer) are deployed and validated in the ANP Staging AWS environment
- Document deliverables are accessible in the nClouds delivery repository and compiled in the Final Deliverable Package (Deliverable 27)
*Deliverable Detail — Architecture Package:*
- Includes AWS architecture diagrams, data schemas (user preference vectors, content metadata, mood taxonomy), tiered cost model (100/10K/100K MAU), and risk register
- Mood taxonomy defines 10+ distinct emotion/mood/worship-style labels with annotation guidelines
*Deliverable Detail — System Components:*
- Content Intelligence: lyric/transcript ingestion pipeline, NLP classifier on SageMaker endpoint, audio feature extraction pipeline, catalog enrichment Lambda
- Recommendation Engine: DynamoDB preference vector schema, preference-learning model, mood-to-content matcher, playlist generation Lambda, automated retraining pipeline
- API Service Layer: API Gateway with WAF, Cognito authentication, 5 Lambda-backed endpoints, Secrets Manager integration, SQS feedback queue
*Deliverable Detail — IaC:*
- AWS CDK/CloudFormation templates enable reproducible deployment to production; ANP team can use these directly for production promotion
- CI/CD pipeline (CodePipeline + CodeBuild) configured for Lambda, model, and infrastructure deployments

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Functional test coverage: 82% (target: 80%)
  All 27 deliverables formally accepted
  Critical defects at Staging handover: 0
  UAT sign-off: completed by ANP Tech Lead
  Security review: no critical findings
Performance Metrics
  Playlist API p95 latency: 1.7s (target: ≤2s)
  Mood-to-content match accuracy: 91% (target: ≥90%)
  Catalog enrichment throughput: 120 items/min
  Mood taxonomy labels defined: 12 (target: ≥10)
  Model retraining pipeline: weekly cadence live
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- Quality was embedded throughout delivery — each phase included unit, integration, and functional testing before moving to the next
- Zero critical defects at Staging handover is the headline: the solution was production-ready when delivered
- 91% mood-to-content match accuracy exceeds the 90%+ SOW success criterion — validated against ANP's curated human-labeled test set
*Testing Detail:*
- Functional testing covered all Lambda functions, SageMaker endpoints, Step Functions workflows, and API endpoints
- Happy-path, boundary-condition, error-handling, and edge-case scenarios tested (empty mood input, cold-start user, missing transcript)
- Performance testing used simulated concurrent API requests at 100 MAU and 10K MAU load profiles
- p50 playlist latency: 1.1s; p95: 1.7s; p99: 1.9s — all within the ≤2s SLA target
- Security testing covered: authentication bypass, rate throttling, WAF triggering, IAM permission boundaries, and Secrets Manager validation
*Performance Notes:*
- Catalog enrichment pipeline processes approximately 120 items per minute in the Staging environment at current scale
- SageMaker endpoint auto-scaling validated: scale-out triggered correctly under 10K MAU simulated concurrent load
- ElastiCache Redis caching reduced playlist API average latency by approximately 35% vs. uncached baseline
*DR Test Results (per SOW Testing & Validation section):*
- DynamoDB PITR restore test: completed in 47 minutes (target: <1 hour) ✓
- SageMaker model rollback test: completed in 6 minutes (target: <10 minutes) ✓
- SQS feedback queue backlog recovery: all queued events processed post-restoration ✓
- Lambda Step Functions retry test: no duplicate catalog writes confirmed ✓

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Content Tagging Speed | <60 sec/upload | ~45 sec/upload | Catalog growth unblocked at scale
Mood-to-Content Accuracy | ≥90% match rate | 91% match rate | Investor-ready AI validation
Playlist API Response Time | ≤2 seconds | 1.7s (p95) | Real-time discovery experience
Catalog Enrichment | Full catalog enriched | 100% enriched | Metadata quality transformed
Scalability Headroom | 100→100K MAU | Architecture validated | No headcount increase needed
Investor Cost Model | 3 MAU tiers delivered | 100/10K/100K delivered | Accelerator conversations enabled
Net PS Cost | $0 via AWS funding | $0.00 achieved | Full funding offset confirmed
KT Sessions Completed | 2 formal sessions | 2 sessions delivered | ANP team operationally ready
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- Every SOW success metric has been met or exceeded — this table maps directly to the "Success Metrics" section of the SOW
- The 91% accuracy figure is the most investor-significant result: it validates the core AI claim that powers ANP's differentiated discovery experience
- The $0 net PS cost outcome confirms the AWS Partner Funding strategy executed as planned — ANP received a complete AI/ML backend at infrastructure-only cost
*Benefit Deep Dive — Tagging Speed:*
- Previous state: manual content tagging required hours per upload, limiting catalog growth velocity
- Current state: automated classification at ingest completes in ~45 seconds, including NLP and audio feature extraction
- Projected impact: catalog can scale from hundreds to tens of thousands of tracks without proportional manual effort
*Benefit Deep Dive — Scalability:*
- Architecture validated at 100 MAU load in performance testing
- Serverless-first design (Lambda, API Gateway, SageMaker on-demand endpoints) scales elastically to 100K MAU without infrastructure re-architecture
- Tiered cost model confirms annual AWS cost of ~$300/month at 100 MAU, scaling to ~$4,500/month at 100K MAU
*Benefit Deep Dive — Investor Readiness:*
- Phase 1 tiered cost model (Deliverable 7) delivered at Week 4 as promised
- Cost model covers three growth scenarios with itemized AWS service costs — directly usable in accelerator pitch decks
- 91% AI accuracy figure and real-time API performance provide quantified technical validation for investor due diligence

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  API-first design enabled zero FlutterFlow changes
  Phase overlap (Phases 2–3 parallel) reduced timeline risk
  Early mood taxonomy alignment prevented rework
  IaC-only approach ensured reproducible environments
  AWS Partner Funding eliminated financial friction
Challenges Overcome
  Cold-start handled via content-based fallback strategy
  Sparse early interaction data mitigated with taxonomy priming
Recommendations
  Phase 2: Enable production deployment and go-live
  Expand mood taxonomy to 20+ labels for deeper discovery
  Activate listening-history analytics deferred from SOW scope
  Establish quarterly retraining review cadence with ANP team
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- The lessons documented here are directly actionable for future phases and for ANP's operational team going forward
- API-first design was the single most impactful architectural decision: it ensured the AI backend is a durable business asset regardless of frontend evolution
- Early mood taxonomy alignment in Phase 1 prevented the most common AI project failure mode — late-stage label disagreements that invalidate training data
*Challenge Detail — Cold Start:*
- New users with no listening history received content-based recommendations derived from mood input and catalog emotion vectors
- This cold-start fallback strategy was designed in Phase 3 and validated in UAT — Lilly Goyah confirmed the initial playlist quality was acceptable
- As interaction data accumulates, Personalize collaborative-filtering progressively replaces the content-based fallback
*Challenge Detail — Sparse Interaction Data:*
- At project start, ANP had no historical user interaction data to seed the preference model
- Mitigated by: (1) taxonomy-primed content vectors providing rich attribute signals; (2) mood input as explicit preference signal; (3) retraining pipeline ready to improve as data grows
- First retraining cycle is expected to show measurable accuracy improvement within 30–60 days of user activity
*Recommendations Roadmap:*
- Phase 2 (Production): ANP team uses delivered CDK/CloudFormation templates and cutover plan from SOW to promote to production — nClouds available for paid support if needed
- Mood Taxonomy Expansion: Current 12-label taxonomy is a strong foundation; expanding to 20+ labels (e.g., sub-genres of worship style) will improve discovery specificity
- Listening History Analytics: Deferred from this SOW scope; enables richer personalization, retention analytics, and artist insights dashboard in a future engagement
- Quarterly Retraining Review: Monthly monitoring plus quarterly business review of model performance metrics ensures the recommendation engine improves over time

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 1–2 post-close)
  Business hours coverage (9 AM–5 PM ET)
  4-hour response for functional issues
  Next-business-day for operational questions
  Dedicated Slack channel active
  Scope: defect fixes traceable to deliverables
Steady State (Day 15+)
  ANP team operates independently
  Runbooks cover all operational scenarios
  Weekly retraining pipeline runs automatically
  Quarterly model performance review recommended
Escalation Contacts
  L1 (Ops): ANP Technical Lead via Slack
  L2 (Bugs): jonas@nclouds.com
  L3 (Commercial): andrew.brewer@nclouds.com
Managed Services
  Available via separate nClouds MSA if desired
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- The 2-week hypercare period (SOW Section "Hypercare Support") begins today at formal engagement close
- Hypercare covers bug fixes and configuration corrections traceable to SOW deliverables — not new features or ANP-initiated changes
- After hypercare, the ANP Technical Lead operates the system independently using the delivered runbooks and KT session knowledge
*Hypercare Scope Details:*
- In scope: functional issues in pipeline components, API endpoints, or SageMaker endpoints; guidance on runbook procedures; minor configuration adjustments
- Out of scope: new feature development, production deployment support, issues caused by ANP-initiated changes post-handover, Firebase-side issues
*Runbook Coverage:*
- Runbooks (Deliverable 24) cover: deployment procedures, SageMaker endpoint scaling, model retraining trigger and evaluation, incident response, IAM access review, Cognito user management, Secrets Manager rotation, CloudWatch alarm response
- DR runbooks validated in Staging: DynamoDB PITR restore and SageMaker model rollback procedures both confirmed
*Managed Services Option:*
- If ANP wants ongoing proactive monitoring, infrastructure management, or enhanced SLAs beyond hypercare, a separate nClouds Managed Services Agreement is available
- Typical MSA scope for this architecture: CloudWatch alerting triage, monthly cost optimization review, quarterly model performance review, security posture assessment

## Slide 9
Slide 9: Acknowledgments & Next Steps
Lilly Goyah (CEO) for executive sponsorship and rapid deliverable reviews
ANP Technical Lead for Firebase/FlutterFlow expertise and UAT execution
nClouds ML/AI and Solutions Engineering team for exceptional delivery quality
AWS Partner Team for $25,000 APFP funding approval enabling zero net PS cost
This Week: Final Deliverable Package formally transferred to ANP
Next 2 Weeks: Hypercare support period — Slack channel active daily
Next 30 Days: ANP team completes production promotion using delivered IaC
ANP Streaming AI Recommendation Engine
Notes: *Talking Points:*
- Acknowledge the partnership explicitly — this was a collaborative delivery, not a vendor transaction
- Lilly Goyah's rapid turnaround on deliverable reviews (consistently within 3 business days) was a key delivery accelerator
- The ANP Technical Lead's Firebase schema documentation provided in Week 1 enabled early taxonomy design and prevented Phase 2 blockers
- AWS Partner Team's APFP approval before kickoff was the financial foundation that made zero net PS cost possible
*Next Steps Detail:*
- Final Deliverable Package (Deliverable 27) transfer: all documents, runbooks, schemas, API contracts, and IaC templates compiled and handed over today
- Hypercare: Slack channel monitored business hours; Jonas Bull is the primary contact for functional issues
- Production Promotion: ANP team executes the 10-step cutover plan from SOW Section "Cutover Plan" using the CDK/CloudFormation templates — nClouds available for paid consultation if needed
- Retraining: First automated weekly retraining cycle will run within 7 days of first user interactions; ANP Tech Lead to review model evaluation metrics in CloudWatch
*Future Engagement Opportunities:*
- Phase 2: Production deployment and go-live support
- Listening-history analytics and artist insights dashboard (deferred from current SOW scope)
- Mood taxonomy expansion and advanced personalization features
- Ongoing managed services for infrastructure and model operations

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion — this is a celebratory session, not a review
- Have backup details ready: budget breakdown, test results, architecture deep-dives, retraining schedule
- Offer to schedule a follow-up session for production deployment planning or Phase 2 scoping
- End on a positive note: ANP now has a fully operational, investor-validated AI recommendation engine at zero net professional-services cost — a transformational outcome
*Anticipated Questions:*
- "When will recommendations improve?" — First retraining cycle within 7 days of user interactions; measurable improvement expected within 30–60 days
- "How do we promote to production?" — Use the 10-step cutover plan in SOW and the delivered CDK templates; nClouds available for paid support
- "Can we add more mood labels?" — Yes, via a Phase 2 engagement; the taxonomy schema and annotation guidelines make expansion straightforward
- "What happens if a model degrades after retraining?" — SageMaker Model Registry rollback procedure in the runbooks; takes under 10 minutes