## Slide 1
Project Closeout
AWS Agentic Pre-Sales Orchestration Platform
Amatra EO Framework Practice — Project Manager | 2026-04-30

## Slide 2
Slide 2: Executive Summary
Project Duration: 12 weeks (Q2 2026), on schedule
Budget: $432,475 net professional services, on budget
Go-Live Date: End of April 2026 (hard deadline met)
Quality: Zero critical defects at production go-live
Effort Reduction: 90% per-engagement time savings achieved
Validation Pass Rate: ≥ 95% first-attempt across all 12 artifact types
Per-Solution Cost: < $5 Bedrock model spend at 200 solutions/month
API Availability: ≥ 99.5% across all 11 Lambda routes
Executive Demo: Delivered to Sarah Lin (CRO) on schedule
ROI Timeline: Consultant capacity payback within 6 months
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Open with confidence — platform delivered on time, on budget, to every presales commitment
- Emphasise the 90% effort reduction: senior-consultant time drops from 6–10 hours to under 1 hour per engagement
- The hard Q2 2026 executive demonstration deadline was the defining success criterion — it was met
- All five agents are live in Bedrock AgentCore Runtime; all 12 artifact types pass format-check and LLM quality validation
- Per-solution Bedrock model spend < $5 was validated in load testing at 200 solutions/month steady-state
*Budget Details:*
- Professional Services list price $452,475 minus $20,000 partner credits = $432,475 net
- Year 1 cloud infrastructure $49,427 net after $15,000 AWS MAP and Bedrock PoC credits
- Total Year 1 investment $493,602 — within the approved $350K–$500K envelope
- 3-year TCO $690,500 vs. manual baseline of ~$1.2M (10 hrs × $200/hr × 600 engagements/year)
*Quality Summary:*
- Format-check and LLM quality-check loop tested against all 12 EO Framework artifact types
- Up to 3 automatic retries per artifact; graded delivery policy surfaces partial results
- Zero quota bypass incidents confirmed through security testing (atomic DynamoDB counters validated)
- Green CloudWatch metrics baseline confirmed; zero critical alarms at go-live

## Slide 3
Slide 3: Solution Architecture
AWS Agentic Pre-Sales Orchestration Platform
Identity & API Layer
  Cognito JWT (1-hr tokens, 30-day refresh)
  API Gateway HTTP API v2 (11 routes)
  DynamoDB atomic quota enforcement
Agent Orchestration Layer
  5 Strands agents on Bedrock AgentCore
  Claude Sonnet 4.6 generation engine
  Claude Haiku 4.5 validation engine
Data & Delivery Layer
  S3 artifact store (12 artifact types)
  eof-tools ECR image (30 converters)
  GitHub PAT automated commit pipeline
Notes: *Talking Points:*
- Architecture follows the "validate first, generate at scale" philosophy defined in the Solution Briefing
- Three logical layers map directly to the presales architecture: Identity/API, Orchestration/Generation, Data/Delivery
- All services are exactly those committed in the SOW — no scope additions were made
*Layer Details:*
- Identity & API: Cognito issues JWTs validated by API Gateway on every request; DynamoDB counters enforce 10/user/month and 1,000/global/month quotas atomically
- Agent Orchestration: Agent 0 (Input Validator) gates generation; Pre-Sales Generator, Delivery Generator, and Code Generator run in parallel domains; EO Validator applies format-check + LLM quality scoring with up to 3 retries
- Data & Delivery: Raw MD/CSV artifacts stored in S3 under {solution_id}/raw/; eof-tools baked into ECR image converts to DOCX/PPTX/XLSX; GitHub PAT pipeline commits all artifacts with structured commit messages
*Presales Alignment:*
- Services match Solution Briefing Slide 4 exactly: Bedrock AgentCore, Sonnet 4.6, Haiku 4.5, API Gateway, Cognito, DynamoDB, S3, ECR, CloudWatch, CloudTrail, GitHub
- No net-new services added beyond SOW scope
- Single-region us-west-2 footprint isolated from us-east-1 as committed

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Architecture Decision Record | Current-state & target architecture | `/delivery/detailed-design/`
AWS Landing Zone (IaC) | VPC, IAM, S3, CloudTrail, KMS | `/delivery/scripts/terraform/`
Five-Agent Strands Graph | AgentCore Runtime — all agents live | `/delivery/scripts/agents/`
Pip-Installable CLI | 14 subcommands for consultants | `/delivery/scripts/cli/`
Terraform IaC Bundle | Full infra with `terraform validate` gate | `/delivery/scripts/terraform/`
Test Plan & Results | Unit, E2E, load, security, UAT | `/delivery/test-plan/`
Operational Runbooks | Quota reset, agent failure, GitHub push | `/delivery/runbook/`
As-Built Documentation | Architecture diagrams, config inventory | `/delivery/detailed-design/`
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- All 27 formal SOW deliverables have been completed and accepted by Marcus Patel and Daniel Park
- The table highlights the 8 most strategic artifacts — the full deliverable register is in the Project Closeout Report (Deliverable 27)
- Terraform IaC covers all 17 Lambda functions, API Gateway, Cognito, DynamoDB, S3, ECR, CloudWatch, and GuardDuty
- CLI pip package published and verified installable by all Amatra consultants with corporate email access
*Deliverable Highlights:*
- ADR covers all major architecture decisions: multi-agent graph design, AgentCore Runtime choice, quota model, eof-tools baking strategy
- Five-Agent Strands Graph: Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator — all registered in Bedrock AgentCore Runtime
- Runbooks cover: quota resets, agent failure recovery, Bedrock throttle handling, GitHub push failures, DynamoDB PITR restore
- Knowledge transfer sessions (CLI/API — 4 hrs; Agent Operations — 3 hrs) recorded and provided as reference assets
*Full SOW Deliverable Status:*
- Deliverables 1–27: All accepted per SOW acceptance authority table
- Formal acceptance signatures obtained from Marcus Patel (primary), Daniel Park (infrastructure/ops), and Sarah Lin (executive milestone)
- CTO sign-off on Cognito user pool and production deployment obtained in Week 11 as planned

## Slide 5
Slide 5: Quality & Performance
Validation Metrics
  Artifact pass rate: 97% (target: ≥ 95%)
  Format-check: 100% of 12 artifact types
  Retry ceiling respected: ≤ 3 retries/artifact
  Critical defects at go-live: 0
  Security findings (critical/high): 0 open
Performance Metrics
  End-to-end generation: 48 min (target: ≤ 60 min)
  Per-solution Bedrock cost: $4.20 (target: < $5)
  API availability: 99.7% (target: ≥ 99.5%)
  Quota bypass incidents: 0 (target: 0)
  CloudWatch critical alarms at go-live: 0
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Every SOW success metric was met or exceeded — share the comparison table with Marcus Patel for formal acceptance documentation
- 97% first-attempt validation pass rate exceeds the ≥ 95% SOW target; graded delivery policy ensures consultants receive partial results even when a subset requires retry
- 48-minute end-to-end generation confirms the sub-60-minute value proposition that eliminates 6–10 hours of manual effort
*Detailed Metrics:*
- Load test executed at 200 solutions/month (≈10 concurrent peak); all performance targets met
- P99 API Gateway response latency: 2.1s (SOW target ≤ 3s)
- DynamoDB atomic quota operation latency: 32ms P99 (SOW target < 50ms)
- Lambda cold-start recovery: < 3s to first successful invocation
- PITR restore test: 3.5 hours (SOW RTO target: 4 hours) ✓
*Security Test Summary:*
- JWT auth penetration: all expired/tampered/unsigned tokens rejected with 401
- Quota bypass via race condition: atomic DynamoDB counters prevented all bypass attempts
- GitHub PAT not exposed in Lambda logs, env vars, or API responses ✓
- IAM Access Analyzer: no overly permissive policies detected
- ECR Inspector scan: zero critical/high CVEs at go-live
*Presales Alignment:*
- Validation pass rate ≥ 95% — SOW Section "Success Metrics" ✓
- API availability ≥ 99.5% — SOW Section "Success Metrics" ✓
- Per-solution Bedrock spend < $5 — SOW Section "Success Metrics" ✓

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Per-Engagement Effort | 90% reduction | 90% reduction | 6–10 hrs → under 1 hr
Artifact Generation Time | ≤ 60 min end-to-end | 48 min | 20% faster than target
Validation Pass Rate | ≥ 95% first attempt | 97% | Quality consistency delivered
Bedrock Cost per Solution | < $5.00 | $4.20 | 16% under cost ceiling
API Availability | ≥ 99.5% monthly | 99.7% | Exceeds SLA commitment
Pipeline Throughput | 200 solutions/month | Validated at 200/mo | Parallel generation enabled
Quota Enforcement | Zero bypass incidents | Zero bypass incidents | Full cost governance live
Audit Trail Coverage | 100% API calls logged | 100% CloudTrail + DynamoDB | SOC 2 readiness achieved
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Every quantified benefit target from the SOW was met or exceeded — present this as a full-scorecard moment
- The 90% effort reduction is the headline: senior consultants who spent 6–10 hours per presales pack now spend under 1 hour on review and approval
- Parallel pipeline throughput unlocks revenue growth without headcount growth — the core value proposition from the Solution Briefing
*ROI Calculation:*
- Manual baseline cost: 120 consultants × 5 presales packs/month × 8 hrs avg × $200/hr = $960,000/month in consultant time
- Automated cost: 120 consultants × 5 packs/month × 1 hr review × $200/hr + $5 Bedrock/pack = $121,800/month
- Monthly savings: ~$838,200 (approximate; based on full utilisation scenario)
- Net Year 1 professional services investment ($432,475) is recovered in well under 1 month of full-scale operation
- 3-year TCO of $690,500 vs. manual baseline of $1.2M+ supports the presales ROI claim of payback within 6 months
*Benefit Details:*
- Audit trail: CloudTrail Management + Data Events on S3 + DynamoDB audit_events table (90-day TTL) + GitHub commit history — full SOC 2 evidence chain
- Cost governance: per-phase token usage visible in CLI `status` subcommand and admin `/usage` API endpoint; DynamoDB records input/output tokens and estimated cost per artifact
- Quality consistency: deterministic format-check eliminates ad-hoc quality drift; LLM quality scoring via Haiku 4.5 provides semantic validation layer

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Foundation-first phasing de-risked identity early
  Incremental agent shipping reduced integration risk
  eof-tools baked in ECR eliminated runtime deps
  Graded delivery policy improved consultant UX
  AWS partner credits reduced Year 1 spend by $35K
Challenges Overcome
  AgentCore Runtime quota required AWS SA pre-approval
  eof-tools image build time optimised via layer caching
Recommendations
  Phase 2: multi-region HA for DR and latency
  Expand to additional artifact types as scope grows
  Implement advanced Bedrock model routing/A/B
  Add browser-based UI for non-CLI users
  Evaluate KMS-CMK for DynamoDB encryption
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Lessons learned are documented in full in the Phase Retrospective section of the Project Closeout Report (Deliverable 27)
- The foundation-first approach (Phase 1 delivering working auth before any AI complexity) was the single most effective risk-mitigation decision of the engagement
- Graded artifact delivery policy — surfacing completed artifacts even when a subset requires retry — was a late-phase UX improvement that significantly improved pilot consultant feedback
*Challenge Details:*
- AgentCore Runtime quota: AWS Bedrock AgentCore was still approaching GA during Phase 1; vendor team engaged AWS Solutions Architect in Week 1 to pre-approve Runtime quota. Mitigation: quota approved by Week 4 with no phase slip.
- eof-tools ECR image build: initial multi-stage build produced a 4.2 GB image causing slow Lambda cold starts. Mitigation: Docker layer caching strategy and selective module inclusion reduced image to 1.8 GB; cold-start recovery < 3s.
*Recommendation Details:*
- Phase 2 — Multi-region HA: us-east-1 replica with Route 53 failover; estimated 4-week effort; addresses DR gap identified in PITR test
- Additional artifact types: currently 12 EO Framework types; Phase 2 backlog identifies 4 candidate types (change-log, executive-summary, migration-plan, cost-optimisation-report)
- Advanced model routing: A/B testing between Sonnet 4.6 and future Claude models; estimated cost reduction 10–15% at scale
- Browser UI: Streamlit or React frontend surfacing CLI functionality; removes barrier for non-technical consultant onboarding
- KMS-CMK DynamoDB: recommended for production data sensitivity upgrade; minimal cost impact (~$30/month); required for SOC 2 Type II full certification

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 13–16)
  Dedicated vendor team on Slack channel
  Business hours coverage (9am–6pm PT)
  P1 response: 2-hour SLA (platform down)
  P2 response: 4-hour SLA (single artifact failing)
  P3 response: next business day
Steady State (Week 17+)
  Monthly CloudWatch performance review
  Quarterly business review with Sarah Lin
  Phase 2 planning workshop at Week 14
  Separate MSA for managed services
Escalation Contacts
  L1: #amatra-platform-hypercare (Slack)
  L2: pm@amatra.com | techsupport@amatra.com
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Four-week hypercare is included in this engagement at no additional cost (covered in professional services fees)
- Hypercare scope covers: Bedrock quota issue resolution, agent failure triage, GitHub push failures, CloudWatch alarm investigation, Cognito user management
- Hypercare does NOT cover net-new feature development, additional artifact types, or multi-region changes — these require Phase 2 scope
*Hypercare Details:*
- P1 (platform down / quota enforcement broken): 2-hour response, senior engineer on-call
- P2 (single artifact type failing validation): 4-hour response, agent specialist assigned
- P3 (cosmetic / documentation issues): next business day
- Vendor team access to production environment is fully revoked at hypercare conclusion (Week 16)
- All access changes logged in CloudTrail and DynamoDB audit_events
*Steady State Transition:*
- Week 14: Phase 2 planning workshop recommended — multi-region HA, additional artifact types, advanced model routing
- Week 17+: PREDICTif's Amatra team operates platform independently using runbooks and KT session recordings
- Managed services beyond Week 16 require a separate MSA; vendor team to provide MSA scope at Week 14 workshop
- Monthly performance reviews cover: CloudWatch metrics, per-solution Bedrock cost trend, quota utilisation, validation pass rates
*Support Contacts (Full List):*
- Slack: #amatra-platform-hypercare (vendor engineering team on-call during business hours)
- Project Manager: pm@amatra.com | +1-800-AMATRA-1
- Technical Lead: techsupport@amatra.com
- After-hours P1 escalation: on-call rotation shared in hypercare kickoff Slack message

## Slide 9
Slide 9: Acknowledgments & Next Steps
Sarah Lin (CRO) for executive sponsorship and go-live approval
Marcus Patel for requirements leadership and UAT sign-off
Daniel Park for infrastructure acceptance and runbook review
PREDICTif CTO for Cognito sign-off on the critical path
This Week: Final documentation and CLI package handover
Next 30 Days: Hypercare support with Slack on-call coverage
Week 14: Phase 2 planning workshop (multi-region, new artifacts)
AWS Agentic Pre-Sales Orchestration Platform
Notes: *Talking Points:*
- Success was a team effort — the on-time, on-budget delivery reflects equal commitment from both sides of the partnership
- Marcus Patel's availability for weekly checkpoint reviews and rapid UAT feedback was essential to maintaining the 12-week timeline
- CTO sign-off obtained by Week 11 — no critical-path slip; this was the single highest-risk dependency in the engagement
*Specific Recognition:*
- Sarah Lin: approved Phase 1 kickoff quickly; co-signed executive demonstration milestone at Week 12; championed the 90% effort-reduction metric as the board-level success story
- Marcus Patel: provided 5 representative client briefs for agent prompt tuning by Week 6 as required; led UAT in Week 11 with thorough scenario coverage; signed off all 27 deliverables within SLA
- Daniel Park: delivered eof-tools library to vendor team by Week 5 as per SOW dependency; accepted all infrastructure and operational deliverables on schedule; validated runbook completeness
- PREDICTif CTO: unblocked Cognito user pool provisioning in Week 11; production deployment proceeded without delay
*Next Steps Timeline:*
- This week: CLI pip package published; all 27 deliverable artifacts committed to GitHub; closeout report finalised
- Next 30 days (Weeks 13–16): Hypercare support per SLA; daily Slack channel monitored; vendor team available for agent triage
- Week 14: Phase 2 planning workshop — recommended agenda: multi-region HA scope, additional artifact types, advanced model routing, browser UI, SOC 2 Type II gap assessment
- Ongoing (Week 17+): Monthly CloudWatch performance review; quarterly business review with Sarah Lin; Phase 2 SOW to be agreed based on Week 14 workshop output

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion — the team is prepared for deep-dive technical questions on any of the five agents, quota enforcement, or the eof-tools integration
- Have backup detail available: load test raw data, CloudWatch dashboard screenshots, security test report summary, full 27-deliverable acceptance log
- Offer to schedule follow-up sessions for specific topics: Phase 2 scoping, managed services terms, SOC 2 gap assessment
- End on a positive note — the platform is live, generating real artifacts for Amatra consultants, and delivering on every commitment made in the presales engagement
- Remind the room: Phase 2 planning workshop is recommended for Week 14 — the momentum from this delivery is the right time to lock in the next phase while the team context is fresh
*Anticipated Questions:*
- Q: What happens if AgentCore Runtime has an outage? A: Lambda functions retry with exponential backoff; DynamoDB PITR recovers state; RTO validated at 3.5 hours against 4-hour target
- Q: Can we add more artifact types ourselves? A: Yes — agent prompt templates are version-controlled in S3 and GitHub; the KT Session 2 recording covers how to add new artifact types; Phase 2 scope includes formal additional artifact type development
- Q: What does Phase 2 cost? A: To be scoped in Week 14 workshop; preliminary estimate is a smaller engagement than Phase 1 given the platform foundation is in place; multi-region HA is the largest single work package
- Q: Is the $4.20 per-solution Bedrock cost guaranteed? A: Validated at 200 solutions/month load test; actual cost will vary with brief complexity and retry frequency; admin `/usage` endpoint provides real-time cost visibility per solution