## Cover
Project Plan
Generated: | June 10, 2026
Solution: | Tmp9Hirua6E
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 — Discovery & Assessment | Project Kickoff | 1 day | 2026-01-05 | 2026-01-05 | None | Project Manager | Not Started
Phase 1 — Discovery & Assessment | AWS Account Provisioning & Access Setup | 2 days | 2026-01-06 | 2026-01-07 | Project Kickoff | Senior Cloud Engineer | Not Started
Phase 1 — Discovery & Assessment | Current State Assessment — Legacy EC2 Monolith | 4 days | 2026-01-08 | 2026-01-13 | AWS Account Provisioning & Access Setup | Solution Architect | Not Started
Phase 1 — Discovery & Assessment | Stakeholder Interviews — Pre-Sales & Delivery Teams | 3 days | 2026-01-08 | 2026-01-12 | Project Kickoff | Project Manager | Not Started
Phase 1 — Discovery & Assessment | Functional Requirements Gathering (7+ Artifact Types) | 5 days | 2026-01-13 | 2026-01-19 | Stakeholder Interviews — Pre-Sales & Delivery Teams | Solution Architect | Not Started
Phase 1 — Discovery & Assessment | Amazon Bedrock Feasibility Assessment | 3 days | 2026-01-13 | 2026-01-15 | AWS Account Provisioning & Access Setup | ML/AI Engineer | Not Started
Phase 1 — Discovery & Assessment | Okta Identity Inventory & Cognito Migration Strategy | 4 days | 2026-01-14 | 2026-01-19 | AWS Account Provisioning & Access Setup | Security Engineer | Not Started
Phase 1 — Discovery & Assessment | SOC 2 & GDPR Requirements Assessment | 3 days | 2026-01-16 | 2026-01-20 | Stakeholder Interviews — Pre-Sales & Delivery Teams | Security Engineer | Not Started
Phase 1 — Discovery & Assessment | Discovery & Assessment Report (Phase 1 Go/No-Go) | 3 days | 2026-01-21 | 2026-01-23 | Functional Requirements Gathering (7+ Artifact Types) | Solution Architect | Not Started
Phase 1 — Discovery & Assessment | Phase 1 Go/No-Go Review with CTO | 1 day | 2026-01-27 | 2026-01-27 | Discovery & Assessment Report (Phase 1 Go/No-Go) | Project Manager | Not Started
Phase 2 — Architecture Design & Planning | End-to-End Serverless Architecture Design | 5 days | 2026-02-02 | 2026-02-06 | Phase 1 Go/No-Go Review with CTO | Solution Architect | Not Started
Phase 2 — Architecture Design & Planning | Cognito User Pool & Identity Federation Design | 3 days | 2026-02-05 | 2026-02-09 | End-to-End Serverless Architecture Design | Security Engineer | Not Started
Phase 2 — Architecture Design & Planning | Bedrock Prompt Template Design (7+ Artifact Types) | 5 days | 2026-02-09 | 2026-02-13 | End-to-End Serverless Architecture Design | ML/AI Engineer | Not Started
Phase 2 — Architecture Design & Planning | Terraform Module Structure & IaC Design | 4 days | 2026-02-09 | 2026-02-12 | End-to-End Serverless Architecture Design | Senior Cloud Engineer | Not Started
Phase 2 — Architecture Design & Planning | Security & Compliance Design (SOC 2 Controls) | 4 days | 2026-02-10 | 2026-02-13 | Cognito User Pool & Identity Federation Design | Security Engineer | Not Started
Phase 2 — Architecture Design & Planning | CI/CD Pipeline Design (GitHub Actions) | 3 days | 2026-02-12 | 2026-02-16 | Terraform Module Structure & IaC Design | DevOps Engineer | Not Started
Phase 2 — Architecture Design & Planning | CloudWatch Observability Design | 2 days | 2026-02-16 | 2026-02-17 | End-to-End Serverless Architecture Design | DevOps Engineer | Not Started
Phase 2 — Architecture Design & Planning | Architecture Decision Records (ADRs) | 3 days | 2026-02-17 | 2026-02-19 | Bedrock Prompt Template Design (7+ Artifact Types) | Solution Architect | Not Started
Phase 2 — Architecture Design & Planning | Detailed Architecture Design Document | 4 days | 2026-02-19 | 2026-02-24 | Architecture Decision Records (ADRs) | Solution Architect | Not Started
Phase 2 — Architecture Design & Planning | Design Review & Approval with CTO and Security Lead | 2 days | 2026-02-25 | 2026-02-26 | Detailed Architecture Design Document | Project Manager | Not Started
Phase 3 — Development & Build | AWS Foundation Provisioning via Terraform (Dev) | 5 days | 2026-03-02 | 2026-03-06 | Design Review & Approval with CTO and Security Lead | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | Cognito User Pool Provisioning & Okta Migration | 7 days | 2026-03-05 | 2026-03-13 | AWS Foundation Provisioning via Terraform (Dev) | Security Engineer | Not Started
Phase 3 — Development & Build | REST API Build — API Gateway & Lambda | 8 days | 2026-03-09 | 2026-03-18 | AWS Foundation Provisioning via Terraform (Dev) | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | Async Job Orchestration — Step Functions & SQS | 7 days | 2026-03-16 | 2026-03-24 | REST API Build — API Gateway & Lambda | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | Bedrock Integration & Prompt Engineering (7+ Types) | 10 days | 2026-03-19 | 2026-04-01 | Async Job Orchestration — Step Functions & SQS | ML/AI Engineer | Not Started
Phase 3 — Development & Build | Artifact Template Automation Pipeline | 8 days | 2026-04-02 | 2026-04-13 | Bedrock Integration & Prompt Engineering (7+ Types) | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | Admin Console & Usage-Limit Governance API | 5 days | 2026-04-07 | 2026-04-13 | Cognito User Pool Provisioning & Okta Migration | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | CI/CD Pipeline Build — GitHub Actions | 5 days | 2026-04-14 | 2026-04-20 | Terraform Module Structure & IaC Design | DevOps Engineer | Not Started
Phase 3 — Development & Build | CloudWatch Observability Stack Deployment | 4 days | 2026-04-20 | 2026-04-23 | CI/CD Pipeline Build — GitHub Actions | DevOps Engineer | Not Started
Phase 3 — Development & Build | Security Hardening & SOC 2 Controls Implementation | 7 days | 2026-04-20 | 2026-04-28 | Admin Console & Usage-Limit Governance API | Security Engineer | Not Started
Phase 3 — Development & Build | Legacy EC2 Monolith Decommission Planning | 3 days | 2026-04-27 | 2026-04-29 | Security Hardening & SOC 2 Controls Implementation | Senior Cloud Engineer | Not Started
Phase 3 — Development & Build | Configuration Documentation | 5 days | 2026-05-04 | 2026-05-08 | CloudWatch Observability Stack Deployment | Technical Writer | Not Started
Phase 4 — Testing & Validation | Test Plan Development | 4 days | 2026-05-11 | 2026-05-14 | Configuration Documentation | QA Engineer | Not Started
Phase 4 — Testing & Validation | Functional & Integration Testing | 8 days | 2026-05-15 | 2026-05-26 | Test Plan Development | QA Engineer | Not Started
Phase 4 — Testing & Validation | Async Job Performance & Load Testing | 4 days | 2026-05-22 | 2026-05-27 | Functional & Integration Testing | QA Engineer | Not Started
Phase 4 — Testing & Validation | Security & Compliance Testing | 5 days | 2026-05-27 | 2026-06-02 | Functional & Integration Testing | Security Engineer | Not Started
Phase 4 — Testing & Validation | Artifact Quality Validation & Bedrock Prompt Tuning | 5 days | 2026-05-28 | 2026-06-03 | Async Job Performance & Load Testing | ML/AI Engineer | Not Started
Phase 4 — Testing & Validation | Cognito & Authentication Testing | 3 days | 2026-06-01 | 2026-06-03 | Security & Compliance Testing | Security Engineer | Not Started
Phase 4 — Testing & Validation | Disaster Recovery & Resilience Testing | 3 days | 2026-06-04 | 2026-06-08 | Security & Compliance Testing | Senior Cloud Engineer | Not Started
Phase 4 — Testing & Validation | UAT Coordination & Execution | 7 days | 2026-06-09 | 2026-06-17 | Artifact Quality Validation & Bedrock Prompt Tuning | QA Engineer | Not Started
Phase 4 — Testing & Validation | SOC 2 Evidence Package Assembly | 4 days | 2026-06-15 | 2026-06-18 | Security & Compliance Testing | Security Engineer | Not Started
Phase 4 — Testing & Validation | Go-Live Readiness Sign-Off | 2 days | 2026-06-22 | 2026-06-23 | UAT Coordination & Execution | Project Manager | Not Started
Phase 5 — Deployment Hypercare & Close | Go-Live Planning & Rollback Procedure Documentation | 3 days | 2026-06-24 | 2026-06-26 | Go-Live Readiness Sign-Off | Project Manager | Not Started
Phase 5 — Deployment Hypercare & Close | Staging Environment Full-Stack Validation | 4 days | 2026-06-29 | 2026-07-02 | Go-Live Planning & Rollback Procedure Documentation | Senior Cloud Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | Production Deployment Phase 1 — Pre-Sales MVP | 2 days | 2026-09-28 | 2026-09-30 | Staging Environment Full-Stack Validation | Senior Cloud Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | Okta-to-Cognito DNS/SSO Final Cutover | 2 days | 2026-09-30 | 2026-10-01 | Production Deployment Phase 1 — Pre-Sales MVP | Security Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | Admin & Pre-Sales Consultant Training Sessions | 3 days | 2026-10-05 | 2026-10-07 | Okta-to-Cognito DNS/SSO Final Cutover | Technical Writer | Not Started
Phase 5 — Deployment Hypercare & Close | Legacy EC2 Monolith Decommission | 2 days | 2026-10-12 | 2026-10-13 | Admin & Pre-Sales Consultant Training Sessions | Senior Cloud Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | Production Deployment Phase 2 — Delivery & Terraform | 2 days | 2026-12-11 | 2026-12-15 | Legacy EC2 Monolith Decommission | Senior Cloud Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | Delivery Team Enablement Session | 1 day | 2026-12-16 | 2026-12-16 | Production Deployment Phase 2 — Delivery & Terraform | Technical Writer | Not Started
Phase 5 — Deployment Hypercare & Close | Operational Runbooks Development | 5 days | 2026-12-14 | 2026-12-18 | Production Deployment Phase 2 — Delivery & Terraform | Technical Writer | Not Started
Phase 5 — Deployment Hypercare & Close | As-Built Architecture Documentation & API Reference | 5 days | 2026-12-16 | 2026-12-22 | Production Deployment Phase 2 — Delivery & Terraform | Technical Writer | Not Started
Phase 5 — Deployment Hypercare & Close | Hypercare Support — Platform Monitoring & Issue Resolution | 8 weeks | 2026-10-01 | 2026-11-25 | Production Deployment Phase 1 — Pre-Sales MVP | Project Manager | Not Started
Phase 5 — Deployment Hypercare & Close | Final SOC 2 Evidence Package Delivery | 3 days | 2027-01-05 | 2027-01-07 | As-Built Architecture Documentation & API Reference | Security Engineer | Not Started
Phase 5 — Deployment Hypercare & Close | General Availability — All ~120 Users Onboarded | 2 days | 2027-01-12 | 2027-01-13 | Final SOC 2 Evidence Package Delivery | Project Manager | Not Started
Phase 5 — Deployment Hypercare & Close | Hypercare Report & Optimisation Roadmap | 3 days | 2027-01-14 | 2027-01-16 | General Availability — All ~120 Users Onboarded | Project Manager | Not Started
Phase 5 — Deployment Hypercare & Close | Project Closeout — Retrospective & Final Report to CTO | 2 days | 2027-01-19 | 2027-01-20 | Hypercare Report & Optimisation Roadmap | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Project Kickoff Complete | 2026-01-05 | Phase 1 — Discovery & Assessment | All stakeholders aligned on scope and governance; project charter acknowledged by CTO and VP Engineering | Project Manager | Not Started
MS-002 | Discovery & Assessment Complete | 2026-01-27 | Phase 1 — Discovery & Assessment | Assessment Report delivered; Phase 1 go/no-go approved by CTO; Okta inventory complete, Bedrock feasibility confirmed | Solution Architect | Not Started
MS-003 | Architecture Approved | 2026-02-26 | Phase 2 — Architecture Design & Planning | Detailed Architecture Design Document and ADRs approved by CTO and Security & Compliance Lead; Terraform module structure signed off by VP Engineering | Solution Architect | Not Started
MS-004 | Dev Platform Built | 2026-05-08 | Phase 3 — Development & Build | All platform components deployed and integrated in Dev environment; CI/CD pipeline operational; Configuration Documentation delivered | Senior Cloud Engineer | Not Started
MS-005 | Testing Complete | 2026-06-23 | Phase 4 — Testing & Validation | All functional, integration, performance, security, and UAT phases passed; SOC 2 evidence package assembled; Go-Live Sign-Off received from CTO and Head of Solutions | QA Engineer | Not Started
MS-006 | Phase 1 Pre-Sales MVP Go-Live | 2026-09-30 | Phase 5 — Deployment Hypercare & Close | Pre-Sales MVP live in Production by 30 Sep 2026; Okta-to-Cognito cutover complete; ≥95% of users successfully logged in within 48 hours | Senior Cloud Engineer | Not Started
MS-007 | Legacy EC2 Monolith Decommissioned | 2026-10-13 | Phase 5 — Deployment Hypercare & Close | EC2 monolith retired with zero data loss; all data archived; decommission certificate issued to VP Engineering | Senior Cloud Engineer | Not Started
MS-008 | Phase 2 Delivery & Terraform Go-Live | 2026-12-15 | Phase 5 — Deployment Hypercare & Close | Delivery artifact automation and Terraform generation live in Production by 15 Dec 2026; delivery team enablement sessions complete | Senior Cloud Engineer | Not Started
MS-009 | General Availability | 2027-01-13 | Phase 5 — Deployment Hypercare & Close | All ~120 internal users onboarded; admin usage controls active; CloudWatch dashboards and alarms operational; ≥90% QA first-pass rate confirmed | Project Manager | Not Started
MS-010 | Hypercare Complete & Project Closed | 2027-01-20 | Phase 5 — Deployment Hypercare & Close | 8-week hypercare concluded; Optimisation Roadmap delivered; as-built documentation and SOC 2 evidence package accepted by CTO; handover to steady-state operations confirmed | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Architect | Vendor Dev | Vendor Security | Vendor QA | Client CTO | Client VP Eng | Client Sec Lead
Project Governance & Status Reporting | R | C | I | I | I | I | C | I
Project Kickoff & Charter | A | R | C | I | I | C | C | I
Discovery & Requirements Gathering | A | R | C | C | I | C | C | C
Current State Assessment — Legacy Monolith | C | R | C | C | I | I | C | I
Amazon Bedrock Feasibility Assessment | I | A | R | I | C | I | C | I
Okta Identity Inventory & Migration Strategy | C | C | R | A | I | I | C | R
SOC 2 & GDPR Requirements Assessment | C | C | I | A | I | I | I | R
Discovery & Assessment Report | A | R | C | C | I | C | C | C
End-to-End Serverless Architecture Design | C | A | C | C | I | I | C | I
Cognito User Pool & Identity Federation Design | C | R | C | A | I | I | C | C
Bedrock Prompt Template Design | I | A | R | I | C | I | I | I
Terraform Module Structure & IaC Design | I | C | A | I | I | I | C | I
Security & Compliance Design | C | C | I | A | I | I | I | C
CI/CD Pipeline Design | I | C | A | I | I | I | C | I
Detailed Architecture Design Document | C | A | C | C | I | I | C | I
Architecture Decision Records | I | A | R | C | I | I | C | I
Design Review & Approval | A | C | I | C | I | C | R | C
AWS Foundation Provisioning via Terraform | I | C | A | C | I | I | C | I
Cognito User Pool Provisioning & Okta Migration | I | C | R | A | C | I | C | R
REST API Build — API Gateway & Lambda | I | C | A | I | C | I | C | I
Async Job Orchestration — Step Functions & SQS | I | A | R | I | C | I | C | I
Bedrock Integration & Prompt Engineering | I | A | R | I | C | I | I | I
Artifact Template Automation Pipeline | I | C | A | I | C | I | C | I
Admin Console & Usage-Limit Governance API | I | C | A | C | I | I | C | I
CI/CD Pipeline Build — GitHub Actions | I | C | A | I | I | I | C | I
CloudWatch Observability Stack Deployment | I | C | A | I | I | I | C | I
Security Hardening & SOC 2 Controls Implementation | C | C | R | A | C | I | I | R
Legacy EC2 Monolith Decommission Planning | C | C | R | I | I | I | A | I
Configuration Documentation | C | C | C | I | I | I | A | I
Test Plan Development | C | C | C | I | A | I | C | I
Functional & Integration Testing | C | C | C | I | A | I | C | I
Security & Compliance Testing | I | I | C | R | A | I | I | R
Artifact Quality Validation & Bedrock Prompt Tuning | I | R | C | I | A | C | I | I
Async Job Performance & Load Testing | C | C | C | I | A | I | C | I
Disaster Recovery & Resilience Testing | I | C | R | C | A | I | I | I
UAT Coordination & Execution | A | C | C | I | C | C | R | I
SOC 2 Evidence Package Assembly | C | I | I | R | A | I | I | R
Go-Live Readiness Sign-Off | A | C | C | C | C | C | R | C
Staging Environment Full-Stack Validation | C | C | R | C | A | I | C | I
Production Deployment Phase 1 — Pre-Sales MVP | C | C | R | C | A | A | R | C
Okta-to-Cognito DNS/SSO Final Cutover | I | C | R | A | C | I | C | R
Legacy EC2 Monolith Decommission Execution | C | C | R | C | I | I | A | I
Production Deployment Phase 2 — Delivery & Terraform | C | C | R | C | A | I | A | C
Admin & Consultant Training Delivery | A | C | C | I | I | I | C | I
Hypercare & Incident Response | A | C | R | C | I | I | C | I
Operational Runbooks | C | R | C | C | I | I | A | I
As-Built Architecture Documentation & API Reference | C | A | C | C | I | I | C | I
Final SOC 2 Evidence Package Delivery | C | I | I | R | A | I | I | A
Optimisation Roadmap | A | R | C | I | I | C | C | I
Project Closeout & BAU Transition | A | C | C | I | I | C | C | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | C A: Responsible - Does the work
A | C A: Accountable - Ultimate ownership
C | C A: Consulted - Provides input
I | C A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders — CTO; VP Engineering; Head of Solutions; Security & Compliance Lead; all vendor team leads | Launch engagement and align on scope; RACI; governance; communication cadence; and Phase 1 priorities | Project Manager | 2026-01-05 (full day)
Weekly Status Call | Weekly | VP Engineering; Head of Solutions; Vendor PM; Solution Architect; ML/AI Engineer | Review progress against plan; surface blockers and decisions; update risk register; confirm next week's priorities | Project Manager | Mondays 10:00am CT
Phase 1 Go/No-Go Review | Once | CTO; VP Engineering; Security & Compliance Lead; Vendor PM; Solution Architect | Review Discovery & Assessment Report findings and approve Phase 2 start | Project Manager | 2026-01-27 (2 hours)
Architecture Design Review | Once | CTO; Security & Compliance Lead; VP Engineering; Solution Architect; Security Engineer | Review and approve Detailed Architecture Design Document and ADRs before development begins | Solution Architect | 2026-02-25 (3 hours)
Phase Gate Review | End of each phase | CTO; VP Engineering; Head of Solutions; Vendor PM | Review phase completion criteria and deliverable acceptance; approve start of next phase | Project Manager | Weeks 4, 8, 20, 26
Bi-Weekly Technical Sync | Bi-weekly | VP Engineering; Senior Cloud Engineer; DevOps Engineer; Solution Architect | Review infrastructure build progress; resolve technical blockers; validate environment configuration | Solution Architect | Wednesdays 2:00pm CT
Security & Compliance Review | Monthly | Security & Compliance Lead; Security Engineer; Vendor PM | Review SOC 2 control implementation status; assess compliance gaps; update evidence log | Security Engineer | Last Thursday of month 11:00am CT
UAT Kickoff & Coordination | Once | Head of Solutions; UAT participants (5–10 pre-sales consultants); QA Engineer | Brief UAT participants on scope; distribute test scenarios; confirm scheduling and feedback process | QA Engineer | 2026-06-09 (2 hours)
Go-Live Readiness Review | Once | CTO; VP Engineering; Head of Solutions; Security & Compliance Lead; Vendor PM | Present UAT results; SOC 2 evidence status; and go-live readiness checklist for formal production approval | Project Manager | 2026-06-22 (2 hours)
Phase 1 Go-Live Communications | Once | All ~120 Amatra internal users | Notify users of Phase 1 Pre-Sales MVP go-live; provide login instructions and support contacts | Project Manager | 2026-09-30
Phase 2 Delivery Team Enablement | Once | Head of Solutions; Delivery Consulting Team Lead; Vendor PM; Technical Writer | Confirm Phase 2 artifact type readiness; walkthrough delivery team training materials and handover process | Project Manager | 2026-12-16 (2 hours)
Hypercare Incident Escalation | As required | VP Engineering; Security & Compliance Lead; Vendor PM; Senior Cloud Engineer | Notify and coordinate resolution of Severity 1 and 2 incidents during hypercare period | Project Manager | Within 1 business hour of detection
Monthly Hypercare Health Check | Monthly during hypercare | VP Engineering; Head of Solutions; Vendor PM; ML/AI Engineer | Review platform health metrics; Bedrock prompt tuning results; open issues; adoption statistics | Project Manager | First Monday of month 10:00am CT
Project Closeout & Retrospective | Once | CTO; VP Engineering; Head of Solutions; Security & Compliance Lead; all vendor team leads | Formal project closure; lessons learned; final report acceptance; BAU handover confirmation | Project Manager | 2027-01-19 (3 hours)