## Cover
Project Plan
Generated: | June 04, 2026
Solution: | Tmp9Kixgwr6
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 — Foundation & Security | Project Kickoff Meeting | 1 day | 2026-02-02 | 2026-02-02 | None | Project Manager | Not Started
Phase 1 — Foundation & Security | Kickoff Minutes & Scope Confirmation | 1 day | 2026-02-03 | 2026-02-03 | Project Kickoff Meeting | Technical Writer | Not Started
Phase 1 — Foundation & Security | Current State Assessment (eof-tools module map) | 5 days | 2026-02-04 | 2026-02-10 | Kickoff Minutes & Scope Confirmation | Solution Architect | Not Started
Phase 1 — Foundation & Security | Cloud Readiness & AI/ML Capability Assessment | 5 days | 2026-02-04 | 2026-02-10 | Kickoff Minutes & Scope Confirmation | Solution Architect | Not Started
Phase 1 — Foundation & Security | Requirements Finalisation (CLI / API / Agents / Cognito) | 5 days | 2026-02-04 | 2026-02-10 | Kickoff Minutes & Scope Confirmation | Project Manager | Not Started
Phase 1 — Foundation & Security | Detailed Architecture Design (multi-agent graph / Cognito / DynamoDB) | 10 days | 2026-02-11 | 2026-02-20 | Current State Assessment (eof-tools module map) | Solution Architect | Not Started
Phase 1 — Foundation & Security | Risk Register & Phased Delivery Plan | 3 days | 2026-02-11 | 2026-02-13 | Requirements Finalisation (CLI / API / Agents / Cognito) | Project Manager | Not Started
Phase 1 — Foundation & Security | CTO Architecture Review & Sign-Off Gate | 3 days | 2026-02-18 | 2026-02-20 | Detailed Architecture Design (multi-agent graph / Cognito / DynamoDB) | Solution Architect | Not Started
Phase 1 — Foundation & Security | AWS Foundation Infrastructure Provisioning (Cognito / DynamoDB / S3 / IAM / API GW) | 7 days | 2026-02-23 | 2026-03-01 | CTO Architecture Review & Sign-Off Gate | Senior Solutions Engineer | Not Started
Phase 1 — Foundation & Security | Cognito Post-Confirmation Lambda & DynamoDB Quota Schema | 5 days | 2026-02-23 | 2026-02-27 | CTO Architecture Review & Sign-Off Gate | Senior Solutions Engineer | Not Started
Phase 2 — Agent Build & Integration | Input Validator Agent (Agent 0) Development & Unit Testing | 5 days | 2026-03-02 | 2026-03-06 | AWS Foundation Infrastructure Provisioning (Cognito / DynamoDB / S3 / IAM / API GW) | Senior ML/AI Engineer | Not Started
Phase 2 — Agent Build & Integration | Pre-Sales Generator Agent (5-artifact workflow) Development & Unit Testing | 7 days | 2026-03-09 | 2026-03-17 | Input Validator Agent (Agent 0) Development & Unit Testing | Senior ML/AI Engineer | Not Started
Phase 2 — Agent Build & Integration | Delivery Generator Agent (6-artifact workflow) Development & Unit Testing | 7 days | 2026-03-16 | 2026-03-24 | Pre-Sales Generator Agent (5-artifact workflow) Development & Unit Testing | Senior ML/AI Engineer | Not Started
Phase 2 — Agent Build & Integration | Code Generator Agent (Terraform IaC + terraform validate gate) Development & Unit Testing | 5 days | 2026-03-23 | 2026-03-27 | Delivery Generator Agent (6-artifact workflow) Development & Unit Testing | Senior ML/AI Engineer | Not Started
Phase 2 — Agent Build & Integration | EO Validator Agent (format-check + Haiku 4.5 + 3-retry logic) Development & Unit Testing | 5 days | 2026-03-23 | 2026-03-27 | Code Generator Agent (Terraform IaC + terraform validate gate) Development & Unit Testing | Senior ML/AI Engineer | Not Started
Phase 2 — Agent Build & Integration | Docker Image Pipeline (multi-stage Dockerfile / ECR push / AgentCore registration) | 5 days | 2026-03-23 | 2026-03-27 | EO Validator Agent (format-check + Haiku 4.5 + 3-retry logic) Development & Unit Testing | DevOps Engineer | Not Started
Phase 2 — Agent Build & Integration | Pip-Installable CLI Development (14 subcommands / JWT auth) | 7 days | 2026-03-09 | 2026-03-17 | AWS Foundation Infrastructure Provisioning (Cognito / DynamoDB / S3 / IAM / API GW) | Senior Solutions Engineer | Not Started
Phase 2 — Agent Build & Integration | Lambda Route Handlers — All 11 Routes (JWT-protected) | 7 days | 2026-03-09 | 2026-03-17 | AWS Foundation Infrastructure Provisioning (Cognito / DynamoDB / S3 / IAM / API GW) | Senior Solutions Engineer | Not Started
Phase 2 — Agent Build & Integration | GitHub Artifact Commit Pipeline (PAT-based) | 3 days | 2026-03-18 | 2026-03-20 | Lambda Route Handlers — All 11 Routes (JWT-protected) | Senior Solutions Engineer | Not Started
Phase 2 — Agent Build & Integration | CloudWatch Observability Implementation (token metrics / dashboards / alarms) | 5 days | 2026-03-23 | 2026-03-27 | GitHub Artifact Commit Pipeline (PAT-based) | DevOps Engineer | Not Started
Phase 2 — Agent Build & Integration | Security Hardening (Secrets Manager / WAF / CloudTrail / KMS) | 5 days | 2026-03-23 | 2026-03-27 | Lambda Route Handlers — All 11 Routes (JWT-protected) | Security Engineer | Not Started
Phase 2 — Agent Build & Integration | Platform Integration End-to-End Smoke Test | 3 days | 2026-03-30 | 2026-04-01 | CloudWatch Observability Implementation (token metrics / dashboards / alarms) | QA Engineer | Not Started
Phase 3 — Validation & Go-Live | Comprehensive Test Plan Authoring | 3 days | 2026-04-06 | 2026-04-08 | Platform Integration End-to-End Smoke Test | QA Engineer | Not Started
Phase 3 — Validation & Go-Live | Unit & Integration Testing — All 12 Artifact Types | 5 days | 2026-04-07 | 2026-04-13 | Comprehensive Test Plan Authoring | QA Engineer | Not Started
Phase 3 — Validation & Go-Live | API Route Testing — All 11 Lambda Routes | 3 days | 2026-04-07 | 2026-04-09 | Unit & Integration Testing — All 12 Artifact Types | QA Engineer | Not Started
Phase 3 — Validation & Go-Live | Performance & Quota Contention Testing | 3 days | 2026-04-09 | 2026-04-13 | API Route Testing — All 11 Lambda Routes | QA Engineer | Not Started
Phase 3 — Validation & Go-Live | Security Testing (JWT bypass / WAF / IAM / Secrets Manager) | 3 days | 2026-04-09 | 2026-04-13 | API Route Testing — All 11 Lambda Routes | Security Engineer | Not Started
Phase 3 — Validation & Go-Live | CloudWatch Green Baseline Validation | 2 days | 2026-04-14 | 2026-04-15 | Performance & Quota Contention Testing | DevOps Engineer | Not Started
Phase 3 — Validation & Go-Live | UAT Coordination with Marcus Patel — Pre-Sales Engineering | 3 days | 2026-04-14 | 2026-04-16 | Unit & Integration Testing — All 12 Artifact Types | Project Manager | Not Started
Phase 3 — Validation & Go-Live | Production Deployment via Terraform (CTO sign-off gate) | 1 day | 2026-04-20 | 2026-04-20 | UAT Coordination with Marcus Patel — Pre-Sales Engineering | DevOps Engineer | Not Started
Phase 3 — Validation & Go-Live | CLI Package Published to PyPI | 1 day | 2026-04-20 | 2026-04-20 | Production Deployment via Terraform (CTO sign-off gate) | Senior Solutions Engineer | Not Started
Phase 3 — Validation & Go-Live | Executive Demonstration Delivered to Sarah Lin (CRO) | 1 day | 2026-04-21 | 2026-04-21 | Production Deployment via Terraform (CTO sign-off gate) | Project Manager | Not Started
Phase 3 — Validation & Go-Live | Knowledge Transfer Sessions (Pre-Sales Engineering + Delivery Operations) | 3 days | 2026-04-21 | 2026-04-23 | Executive Demonstration Delivered to Sarah Lin (CRO) | Solution Architect | Not Started
Phase 3 — Validation & Go-Live | As-Built Documentation & API/CLI Reference Delivery | 2 days | 2026-04-21 | 2026-04-22 | Executive Demonstration Delivered to Sarah Lin (CRO) | Technical Writer | Not Started
Phase 3 — Validation & Go-Live | Operational Runbooks Delivery | 2 days | 2026-04-21 | 2026-04-22 | Executive Demonstration Delivered to Sarah Lin (CRO) | Technical Writer | Not Started
Phase 3 — Validation & Go-Live | Optimisation Recommendations & Phase 2 Roadmap | 2 days | 2026-04-22 | 2026-04-23 | As-Built Documentation & API/CLI Reference Delivery | Solution Architect | Not Started
Phase 3 — Validation & Go-Live | Formal Project Acceptance & Closeout Report | 1 day | 2026-04-24 | 2026-04-24 | Optimisation Recommendations & Phase 2 Roadmap | Project Manager | Not Started
Hypercare | Hypercare Week 1 — Production Monitoring & Incident Response | 5 days | 2026-04-27 | 2026-05-01 | Formal Project Acceptance & Closeout Report | Senior ML/AI Engineer | Not Started
Hypercare | Hypercare Week 2 — Agent Prompt Tuning & Quota Adjustment | 5 days | 2026-05-04 | 2026-05-08 | Hypercare Week 1 — Production Monitoring & Incident Response | Senior ML/AI Engineer | Not Started
Hypercare | Hypercare Week 3 — Defect Remediation & Platform Stabilisation | 5 days | 2026-05-11 | 2026-05-15 | Hypercare Week 2 — Agent Prompt Tuning & Quota Adjustment | Senior ML/AI Engineer | Not Started
Hypercare | Hypercare Week 4 — BAU Transition & Hypercare Closeout | 5 days | 2026-05-18 | 2026-05-22 | Hypercare Week 3 — Defect Remediation & Platform Stabilisation | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Kickoff Complete | 2026-02-02 | Phase 1 — Foundation & Security | Scope confirmed; architecture design initiated; CTO sign-off process commenced; kickoff minutes distributed | Project Manager | Not Started
MS-002 | Architecture Approved | 2026-02-20 | Phase 1 — Foundation & Security | Multi-agent graph design and AWS foundation design approved by CTO and Marcus Patel; risk register baselined | Solution Architect | Not Started
MS-003 | Foundation Live | 2026-03-01 | Phase 1 — Foundation & Security | Cognito auth flow operational; API Gateway scaffold responding; DynamoDB quota schema deployed in us-west-2; accepted by Marcus Patel | Senior Solutions Engineer | Not Started
MS-004 | All Agents Registered | 2026-03-27 | Phase 2 — Agent Build & Integration | All five Strands agents unit-tested and registered with Bedrock AgentCore Runtime; Docker image published to ECR | Senior ML/AI Engineer | Not Started
MS-005 | Platform Integration Complete | 2026-04-01 | Phase 2 — Agent Build & Integration | CLI pip-installable and passing local integration tests; all 11 Lambda routes responding to authenticated requests; GitHub commit pipeline validated end-to-end | Senior Solutions Engineer | Not Started
MS-006 | Validation Green | 2026-04-15 | Phase 3 — Validation & Go-Live | All 12 artifact types passing end-to-end validation; 95%+ first-attempt pass rate; green CloudWatch metrics baseline confirmed | QA Engineer | Not Started
MS-007 | Go-Live | 2026-04-21 | Phase 3 — Validation & Go-Live | Production deployment complete with CTO sign-off; executive demonstration delivered to Sarah Lin (CRO); all smoke tests passing | Project Manager | Not Started
MS-008 | Handover Complete | 2026-04-24 | Phase 3 — Validation & Go-Live | All documentation delivered; knowledge transfer sessions completed; formal project acceptance sign-off obtained from Sarah Lin | Project Manager | Not Started
MS-009 | Hypercare End | 2026-05-22 | Hypercare | Four-week hypercare support period complete; no open Severity 1 or Severity 2 defects; platform transitions to BAU under Daniel Park | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Arch | Vendor Eng | Vendor QA | Client IT Lead | Client Sec | CTO
Project Governance & Status Reporting | A | C | R | I | C | I | I
Architecture Design & CTO Review | C | A | R | I | C | C | I
AWS Foundation Infrastructure Provisioning | C | A | R | I | C | I | I
Cognito Auth & API Gateway Configuration | C | A | R | I | C | C | I
Agent Development — All 5 Strands Agents | I | A | R | C | I | I | I
eof-Tools Docker Image Pipeline & ECR | I | A | R | C | I | I | I
CLI Development — 14 Subcommands | I | A | R | C | I | I | I
Lambda Route Handler Development — 11 Routes | I | A | R | C | I | I | I
DynamoDB Quota Enforcement Implementation | C | A | R | C | I | I | I
GitHub Artifact Commit Pipeline | I | A | R | C | I | I | I
CloudWatch Observability Implementation | C | A | R | C | I | I | I
Security Hardening & Compliance Controls | C | C | R | C | C | A | I
Test Plan Authoring | C | C | R | A | I | I | I
Unit & Integration Testing — All 12 Artifact Types | C | C | R | A | I | I | I
API Route & Quota Contention Testing | C | I | R | A | I | I | I
Security Testing | C | C | R | A | C | C | I
UAT Coordination & Acceptance | A | C | C | R | C | I | I
Production Deployment & CTO Sign-Off Gate | C | A | R | I | I | I | I
CLI Package Publication | I | A | R | I | I | I | I
Operational Runbooks Authoring | A | C | R | I | C | I | I
As-Built Architecture Documentation & API Reference | C | A | R | I | I | I | I
Knowledge Transfer Session Delivery | A | R | C | I | C | I | I
Optimisation Recommendations & Phase 2 Roadmap | C | A | R | I | I | I | I
Formal Project Acceptance & Closeout | A | C | R | C | C | I | I
Hypercare Incident Management | A | C | R | C | I | I | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | Responsible - Does the work
A | Accountable - Ultimate ownership
C | Consulted - Provides input
I | Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | Sarah Lin; Marcus Patel; Daniel Park; CTO; Vendor delivery team | Launch project; align on scope; confirm RACI; establish governance cadence; initiate CTO sign-off process | Project Manager | 2026-02-02 09:00 PT
Weekly Status Call | Weekly | Marcus Patel; Project Manager; Vendor team leads | Review progress against plan; surface blockers and decisions; update risk register | Project Manager | Mondays 10:00 PT
Architecture Design Review | Once | CTO; Marcus Patel; Solution Architect; Security Engineer | Review and approve multi-agent graph design; Cognito user pool configuration; DynamoDB schema; AWS foundation design | Solution Architect | 2026-02-18 10:00 PT
Steering Committee Review | Monthly | Sarah Lin (CRO); Marcus Patel; Daniel Park; Project Manager | Executive-level review of project progress; budget status; risk escalations; milestone sign-off authority | Project Manager | Monthly — first Monday 09:00 PT
Phase 1 Gate Review | Once | Marcus Patel; Project Manager; Solution Architect | Confirm Phase 1 completion criteria met; approve Phase 2 start; review Foundation Live milestone sign-off | Project Manager | 2026-03-01 10:00 PT
Phase 2 Gate Review | Once | Marcus Patel; Daniel Park; Project Manager; Solution Architect | Confirm all five agents registered; CLI and Lambda routes integrated; platform smoke test passed; approve Phase 3 start | Project Manager | 2026-04-03 10:00 PT
UAT Briefing & Walkthrough | Once | Marcus Patel; representative Pre-Sales consultants; QA Engineer | Walk through UAT scenarios; confirm acceptance criteria; schedule UAT execution sessions | Project Manager | 2026-04-06 10:00 PT
Go-Live Readiness Review | Once | Marcus Patel; Daniel Park; CTO; Sarah Lin; Project Manager; Solution Architect | Present test results; confirm all go-live readiness criteria met; obtain CTO sign-off for production deployment | Project Manager | 2026-04-17 10:00 PT
Executive Demonstration | Once | Sarah Lin (CRO); Marcus Patel; Project Manager; Solution Architect | Live demonstration of end-to-end presales bundle generation via CLI; showcase 12 artifact types and CloudWatch metrics | Project Manager | 2026-04-21 09:00 PT
Knowledge Transfer Sessions | Once (Week 12) | Marcus Patel; Daniel Park; Pre-Sales Engineering team; Delivery Operations team | Platform architecture walk-through; CLI and API usage hands-on; operations runbooks; admin API and quota reporting | Solution Architect | 2026-04-21 to 2026-04-23
Hypercare Incident Escalation | As required | Marcus Patel or Daniel Park; Project Manager; Senior ML/AI Engineer | Notify and resolve Severity 1 incidents during hypercare period; assess impact; communicate workaround | Senior ML/AI Engineer | Within 2 business hours of detection
Hypercare Weekly Check-In | Weekly (Weeks 13-16) | Marcus Patel; Daniel Park; Project Manager | Review open defects; confirm platform health; track quota utilisation; discuss BAU transition readiness | Project Manager | Mondays 10:00 PT
Project Closeout & BAU Handover | Once | Sarah Lin; Marcus Patel; Daniel Park; Project Manager | Formal project closure confirmation; 90% effort-reduction metric validation; BAU operations transfer to Daniel Park's team | Project Manager | 2026-05-22 10:00 PT