## Cover
Project Plan
Generated: | June 10, 2026
Solution: | Tmpqz8Q6Wcz
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff & Stakeholder Alignment | 1 day | 2026-07-01 | 2026-07-01 | None | Project Manager | Not Started
Phase 1 | AWS Account Provisioning & IAM Access | 3 days | 2026-07-02 | 2026-07-04 | Project Kickoff & Stakeholder Alignment | VP Engineering | Not Started
Phase 1 | Okta User Directory Export | 3 days | 2026-07-02 | 2026-07-04 | Project Kickoff & Stakeholder Alignment | Security & Compliance Lead | Not Started
Phase 1 | Historical Client Briefs Collection | 5 days | 2026-07-02 | 2026-07-08 | Project Kickoff & Stakeholder Alignment | Head of Solutions | Not Started
Phase 1 | Discovery & Current State Assessment | 10 days | 2026-07-06 | 2026-07-17 | AWS Account Provisioning & IAM Access | Lead Solutions Architect | Not Started
Phase 1 | Legacy Template Inventory & Export | 5 days | 2026-07-06 | 2026-07-10 | Historical Client Briefs Collection | Lead Solutions Architect | Not Started
Phase 1 | Detailed Architecture Design & ADRs | 15 days | 2026-07-20 | 2026-08-07 | Discovery & Current State Assessment | Lead Solutions Architect | Not Started
Phase 1 | AWS Landing Zone & Environment Setup | 10 days | 2026-07-20 | 2026-07-31 | AWS Account Provisioning & IAM Access | Senior Solutions Engineer | Not Started
Phase 1 | CI/CD Pipeline Setup (GitHub Actions) | 5 days | 2026-08-03 | 2026-08-07 | AWS Landing Zone & Environment Setup | Cloud/DevOps Engineer | Not Started
Phase 1 | Architecture Design Review & Approval Gate | 5 days | 2026-08-10 | 2026-08-14 | Detailed Architecture Design & ADRs | Project Manager | Not Started
Phase 1 | Okta-to-Cognito Identity Migration | 10 days | 2026-08-10 | 2026-08-21 | Architecture Design Review & Approval Gate | Senior Solutions Engineer | Not Started
Phase 1 | Async Job Orchestration (Step Functions + SQS) | 10 days | 2026-08-10 | 2026-08-21 | Architecture Design Review & Approval Gate | Senior Solutions Engineer | Not Started
Phase 1 | Bedrock Integration Layer (Phase 1 Artifacts) | 15 days | 2026-08-17 | 2026-09-04 | Architecture Design Review & Approval Gate | ML/AI Engineer | Not Started
Phase 1 | API Gateway & Lambda REST API Layer | 10 days | 2026-08-17 | 2026-08-28 | Architecture Design Review & Approval Gate | Senior Solutions Engineer | Not Started
Phase 1 | Security Hardening & SOC 2 Controls Phase 1 | 10 days | 2026-08-24 | 2026-09-04 | Okta-to-Cognito Identity Migration | Security Engineer | Not Started
Phase 1 | Pre-Sales Artifact Pipeline (4 Artifact Types) | 10 days | 2026-09-01 | 2026-09-11 | Bedrock Integration Layer (Phase 1 Artifacts), API Gateway & Lambda REST API Layer | ML/AI Engineer | Not Started
Phase 1 | Phase 1 Functional & Integration Testing | 7 days | 2026-09-07 | 2026-09-15 | Pre-Sales Artifact Pipeline (4 Artifact Types), Security Hardening & SOC 2 Controls Phase 1 | QA Engineer | Not Started
Phase 1 | Phase 1 UAT — Pre-Sales Artifacts | 7 days | 2026-09-14 | 2026-09-22 | Phase 1 Functional & Integration Testing | Head of Solutions | Not Started
Phase 1 | Pre-Sales Consultant Training Materials | 5 days | 2026-09-14 | 2026-09-18 | Phase 1 Functional & Integration Testing | Technical Writer | Not Started
Phase 1 | Phase 1 Go-Live Readiness Review & CTO Approval | 3 days | 2026-09-23 | 2026-09-25 | Phase 1 UAT — Pre-Sales Artifacts | Project Manager | Not Started
Phase 1 | Phase 1 Production Deployment (MVP Go-Live) | 1 day | 2026-09-30 | 2026-09-30 | Phase 1 Go-Live Readiness Review & CTO Approval | Senior Solutions Engineer | Not Started
Phase 2 | Delivery Artifact Pipeline Design | 5 days | 2026-10-01 | 2026-10-07 | Phase 1 Production Deployment (MVP Go-Live) | Lead Solutions Architect | Not Started
Phase 2 | Legacy Template Pipeline (Word/Excel/PPT) | 15 days | 2026-10-08 | 2026-10-26 | Delivery Artifact Pipeline Design | Senior Solutions Engineer | Not Started
Phase 2 | Bedrock Integration Layer (Phase 2 Artifacts) | 15 days | 2026-10-08 | 2026-10-26 | Delivery Artifact Pipeline Design | ML/AI Engineer | Not Started
Phase 2 | Delivery Artifact Pipeline (3 Additional Types) | 10 days | 2026-10-27 | 2026-11-06 | Legacy Template Pipeline (Word/Excel/PPT), Bedrock Integration Layer (Phase 2 Artifacts) | Senior Solutions Engineer | Not Started
Phase 2 | Per-User & Global Usage Limit Controls | 7 days | 2026-10-27 | 2026-11-04 | Delivery Artifact Pipeline Design | ML/AI Engineer | Not Started
Phase 2 | QA Validation Layer & Pass-Rate Dashboard | 10 days | 2026-11-02 | 2026-11-13 | Delivery Artifact Pipeline (3 Additional Types) | QA Engineer | Not Started
Phase 2 | CloudWatch Monitoring & SLA Dashboards | 7 days | 2026-11-09 | 2026-11-17 | QA Validation Layer & Pass-Rate Dashboard | Cloud/DevOps Engineer | Not Started
Phase 2 | SOC 2 Type II Controls Evidence Package | 10 days | 2026-11-09 | 2026-11-20 | Security Hardening & SOC 2 Controls Phase 1 | Security Engineer | Not Started
Phase 2 | Phase 2 Functional & Compliance Testing | 7 days | 2026-11-16 | 2026-11-24 | QA Validation Layer & Pass-Rate Dashboard, SOC 2 Type II Controls Evidence Package | QA Engineer | Not Started
Phase 2 | Phase 2 UAT — Delivery Artifacts | 7 days | 2026-11-23 | 2026-12-01 | Phase 2 Functional & Compliance Testing | VP Engineering | Not Started
Phase 2 | Delivery Team & Administrator Training | 3 days | 2026-11-30 | 2026-12-02 | Phase 2 UAT — Delivery Artifacts | Technical Writer | Not Started
Phase 2 | Phase 2 Go-Live Readiness Review & CTO Approval | 3 days | 2026-12-07 | 2026-12-09 | Phase 2 UAT — Delivery Artifacts | Project Manager | Not Started
Phase 2 | Phase 2 Production Deployment | 1 day | 2026-12-15 | 2026-12-15 | Phase 2 Go-Live Readiness Review & CTO Approval | Senior Solutions Engineer | Not Started
Phase 3 | GA Rollout Planning & User Cohort Scheduling | 5 days | 2026-12-16 | 2026-12-22 | Phase 2 Production Deployment | Project Manager | Not Started
Phase 3 | Bedrock Prompt Optimisation (Production Data) | 14 days | 2026-12-16 | 2027-01-02 | Phase 2 Production Deployment | ML/AI Engineer | Not Started
Phase 3 | Lambda & DynamoDB Performance Optimisation | 7 days | 2026-12-23 | 2027-01-02 | Bedrock Prompt Optimisation (Production Data) | Cloud/DevOps Engineer | Not Started
Phase 3 | All-User Onboarding & GA Rollout (~120 Users) | 10 days | 2027-01-04 | 2027-01-15 | GA Rollout Planning & User Cohort Scheduling | Project Manager | Not Started
Phase 3 | Train-the-Trainer Session (Head of Solutions) | 1 day | 2027-01-11 | 2027-01-11 | All-User Onboarding & GA Rollout (~120 Users) | Lead Solutions Architect | Not Started
Phase 3 | Optimisation Recommendations Report | 5 days | 2027-01-11 | 2027-01-15 | Lambda & DynamoDB Performance Optimisation, All-User Onboarding & GA Rollout (~120 Users) | Lead Solutions Architect | Not Started
Phase 3 | Operations Runbooks & Configuration Docs | 5 days | 2027-01-11 | 2027-01-15 | All-User Onboarding & GA Rollout (~120 Users) | Technical Writer | Not Started
Phase 3 | SOC 2 Final Evidence Package & Sign-Off | 3 days | 2027-01-18 | 2027-01-20 | SOC 2 Type II Controls Evidence Package | Security Engineer | Not Started
Phase 3 | Final Project Closeout Report & Retrospective | 3 days | 2027-01-25 | 2027-01-27 | SOC 2 Final Evidence Package & Sign-Off, Optimisation Recommendations Report | Project Manager | Not Started
Phase 3 | Engagement Formally Closed | 1 day | 2027-01-31 | 2027-01-31 | Final Project Closeout Report & Retrospective | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Kickoff Complete | 2026-07-01 | Phase 1 | CTO, VP Engineering, and Head of Solutions aligned on scope, success criteria, and governance model; project charter acknowledged | Project Manager | Not Started
MS-002 | Architecture Approved | 2026-08-14 | Phase 1 | Detailed architecture design, ADRs, and data models reviewed and approved by CTO and VP Engineering; no open blocking concerns | Lead Solutions Architect | Not Started
MS-003 | Infrastructure Foundation Live | 2026-09-04 | Phase 1 | AWS landing zone, Cognito migration, CI/CD pipeline, and async orchestration operational in Staging; all smoke tests passing | Senior Solutions Engineer | Not Started
MS-004 | Phase 1 MVP Go-Live | 2026-09-30 | Phase 1 | Pre-sales artifact pipeline (4 types) live in production; pre-sales consultants able to submit briefs and receive generated artifacts; CTO written approval received | Project Manager | Not Started
MS-005 | Phase 1 Hypercare End | 2026-11-25 | Phase 1 | 8-week Phase 1 hypercare complete; platform stable; zero open P1 defects; usage metrics baselined | Project Manager | Not Started
MS-006 | Phase 2 Go-Live | 2026-12-15 | Phase 2 | Full 7-type artifact pipeline live in production; QA validation layer active with ≥90% pass rate; SOC 2 compliance controls evidenced; CTO written approval received | Project Manager | Not Started
MS-007 | Phase 2 Hypercare End | 2027-01-12 | Phase 2 | 4-week Phase 2 hypercare complete; delivery team using platform in production; no open P1 defects | Project Manager | Not Started
MS-008 | GA Rollout Complete | 2027-01-20 | Phase 3 | All ~120 internal users onboarded and authenticated; Bedrock prompts optimised; all training sessions complete and recorded | Project Manager | Not Started
MS-009 | Project Close | 2027-01-31 | Phase 3 | SOC 2 evidence package delivered and signed off; operations runbooks transferred; project retrospective complete; engagement formally closed with CTO | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Arch | Vendor Eng | Vendor QA | Client CTO | Client VP Eng | Head of Solutions | Sec & Compliance
Project Governance & Reporting | A | C | I | I | C | C | I | I
Discovery & Current State Assessment | C | A | R | I | C | C | C | C
Architecture Design & ADRs | I | A | R | I | C | C | I | C
AWS Landing Zone & Environment Setup | C | C | R | I | I | A | I | C
CI/CD Pipeline Setup | C | C | R | C | I | A | I | I
Bedrock Integration Layer | C | A | R | I | I | C | C | I
Async Job Orchestration (Step Functions + SQS) | C | A | R | I | I | C | I | I
API Gateway & Lambda REST API Layer | C | C | R | I | I | A | I | I
Okta-to-Cognito Identity Migration | C | C | R | I | I | C | I | A
Legacy Template Pipeline | C | C | R | C | I | C | A | I
Security Hardening & SOC 2 Controls | I | C | R | C | I | C | I | A
QA Validation Layer | C | C | R | A | I | C | C | I
Pre-Sales Artifact Pipeline | C | C | R | I | I | C | A | I
Delivery Artifact Pipeline | C | C | R | I | I | A | C | I
Functional & Integration Testing | C | C | R | A | I | C | C | C
UAT — Pre-Sales Artifacts | C | I | I | C | I | I | A | I
UAT — Delivery Artifacts | C | I | I | C | I | A | C | I
Phase Gate Approvals | C | C | I | I | A | C | C | C
Production Deployments | A | C | R | C | I | C | I | C
Training Delivery | A | C | R | I | I | C | C | I
Hypercare Support | A | C | R | I | I | C | C | I
SOC 2 Evidence Package & Compliance Sign-Off | C | C | R | C | I | I | I | A
Optimisation & Project Closeout | A | R | C | I | C | C | I | I
CloudWatch Monitoring & SLA Dashboards | C | C | R | I | I | A | I | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | A A A C A C: Responsible - Does the work
A | A A A C A C: Accountable - Ultimate ownership
C | A A A C A C: Consulted - Provides input
I | A A A C A C: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff Workshop | Once | All stakeholders; EO Framework and Amatra teams | Launch project, align on scope, RACI, and governance; confirm success criteria | Project Manager | 2026-07-01
Weekly Status Call | Weekly | Cloud CoE Lead; VP Engineering; EO Framework team leads | Review progress against plan, discuss blockers and decisions, update risk register | Project Manager | Mondays 10:00 CT
Architecture Review Workshop | Once | VP Engineering; Head of Solutions; CTO; Lead Solutions Architect | Review and approve Detailed Architecture Design, ADRs, and data models | Lead Solutions Architect | 2026-08-10 (half-day)
Phase 1 Design Walkthrough | Once | VP Engineering; Security & Compliance Lead; EO Framework architects | Walk through security design and SOC 2 control mapping for Phase 1 scope | Lead Solutions Architect | 2026-08-14 (2 hours)
Phase Gate Review — Phase 1 | Once | CTO; VP Engineering; Head of Solutions; Project Manager | Review Phase 1 completion criteria, UAT sign-off, and approve Phase 1 production deployment | Project Manager | 2026-09-25 (1 hour)
Hypercare Incident Escalation | As required | VP Engineering; Security & Compliance Lead; Project Manager | Notify and resolve P1 incidents during hypercare periods | Project Manager | Within 2 business hours of detection
Phase Gate Review — Phase 2 | Once | CTO; VP Engineering; Head of Solutions; Security & Compliance Lead; Project Manager | Review Phase 2 completion, compliance evidence, UAT sign-off, and approve Phase 2 production deployment | Project Manager | 2026-12-09 (1 hour)
GA Readiness Review | Once | CTO; VP Engineering; Head of Solutions; Project Manager | Present GA rollout plan and confirm all ~120 users can be onboarded safely before 2027-01-31 | Project Manager | 2027-01-04 (1 hour)
Monthly Steering Committee | Monthly | CTO; VP Engineering; Head of Solutions; Project Manager | Review phase milestones and budget burn; escalate risks to executive sponsor | Project Manager | First Monday of each month 14:00 CT
Project Closeout Meeting | Once | CTO; VP Engineering; Head of Solutions; Security & Compliance Lead; EO Framework leads | Formal project closure; present final deliverables and SOC 2 evidence; confirm BAU handover | Project Manager | 2027-01-31 (1 hour)