## Cover
Project Plan
Generated: | June 09, 2026
Solution: | Tmpgk8Pqn_H
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff Meeting | 1 day | 2025-07-07 | 2025-07-07 | None | Project Manager | Not Started
Phase 1 | AWS Account Access Provisioning | 1 day | 2025-07-07 | 2025-07-07 | Project Kickoff Meeting | Cloud Engineer | Not Started
Phase 1 | Firebase Catalog Structure Review | 2 days | 2025-07-08 | 2025-07-09 | AWS Account Access Provisioning | Solutions Architect | Not Started
Phase 1 | Firebase Catalog Assessment Report | 1 day | 2025-07-09 | 2025-07-09 | Firebase Catalog Structure Review | Solutions Architect | Not Started
Phase 1 | API Schema and Requirements Documentation | 2 days | 2025-07-08 | 2025-07-09 | Project Kickoff Meeting | Solutions Architect | Not Started
Phase 1 | AWS Architecture Design and Decision Record | 3 days | 2025-07-10 | 2025-07-14 | API Schema and Requirements Documentation | Solutions Architect | Not Started
Phase 1 | Risk Register Documentation | 1 day | 2025-07-10 | 2025-07-10 | Firebase Catalog Structure Review | Project Manager | Not Started
Phase 1 | Dev AWS Environment Provisioning | 3 days | 2025-07-10 | 2025-07-14 | AWS Account Access Provisioning | Cloud Engineer | Not Started
Phase 1 | Security Baseline Configuration | 2 days | 2025-07-14 | 2025-07-15 | Dev AWS Environment Provisioning | Security Engineer | Not Started
Phase 1 | Firebase Catalog Export to S3 | 1 day | 2025-07-14 | 2025-07-14 | Dev AWS Environment Provisioning | Cloud Engineer | Not Started
Phase 1 | Discovery Summary Report Sign-Off | 1 day | 2025-07-16 | 2025-07-16 | AWS Architecture Design and Decision Record | Project Manager | Not Started
Phase 2 | Bedrock Foundation Model Evaluation and Prototype | 3 days | 2025-07-17 | 2025-07-21 | Discovery Summary Report Sign-Off | ML/AI Engineer | Not Started
Phase 2 | POST /classify Lambda Function Implementation | 3 days | 2025-07-21 | 2025-07-23 | Bedrock Foundation Model Evaluation and Prototype | ML/AI Engineer | Not Started
Phase 2 | GET /recommend Lambda Function Implementation | 3 days | 2025-07-22 | 2025-07-24 | POST /classify Lambda Function Implementation | ML/AI Engineer | Not Started
Phase 2 | Auto-Tagging Batch Lambda Pipeline Implementation | 2 days | 2025-07-23 | 2025-07-24 | Bedrock Foundation Model Evaluation and Prototype | ML/AI Engineer | Not Started
Phase 2 | DynamoDB Schema Design and Seed Data Load | 2 days | 2025-07-21 | 2025-07-22 | Firebase Catalog Export to S3 | Cloud Engineer | Not Started
Phase 2 | API Gateway Configuration | 2 days | 2025-07-24 | 2025-07-25 | POST /classify Lambda Function Implementation | Cloud Engineer | Not Started
Phase 2 | CloudWatch Dashboards and Alerting Setup | 2 days | 2025-07-25 | 2025-07-28 | Dev AWS Environment Provisioning | Cloud Engineer | Not Started
Phase 2 | Infrastructure as Code Templates Finalization | 2 days | 2025-07-28 | 2025-07-29 | API Gateway Configuration | Cloud Engineer | Not Started
Phase 2 | Detailed Architecture Specification and API Schemas Document | 1 day | 2025-07-17 | 2025-07-17 | Discovery Summary Report Sign-Off | Solutions Architect | Not Started
Phase 3 | Test Plan and Test Cases Development | 2 days | 2025-07-30 | 2025-07-31 | Infrastructure as Code Templates Finalization | QA Engineer | Not Started
Phase 3 | Functional Testing Execution | 3 days | 2025-07-31 | 2025-08-04 | Test Plan and Test Cases Development | QA Engineer | Not Started
Phase 3 | Integration Testing Execution | 2 days | 2025-08-04 | 2025-08-05 | Functional Testing Execution | QA Engineer | Not Started
Phase 3 | Security Testing Execution | 2 days | 2025-08-04 | 2025-08-05 | Functional Testing Execution | Security Engineer | Not Started
Phase 3 | Bedrock Mood Classification Accuracy Validation | 2 days | 2025-08-04 | 2025-08-05 | Functional Testing Execution | ML/AI Engineer | Not Started
Phase 3 | Defect Resolution | 2 days | 2025-08-05 | 2025-08-06 | Integration Testing Execution | ML/AI Engineer | Not Started
Phase 3 | User Acceptance Testing | 2 days | 2025-08-06 | 2025-08-07 | Defect Resolution | QA Engineer | Not Started
Phase 3 | Production Deployment via IaC | 1 day | 2025-08-07 | 2025-08-07 | User Acceptance Testing | Cloud Engineer | Not Started
Phase 3 | API Reference Documentation Delivery | 1 day | 2025-08-07 | 2025-08-07 | Production Deployment via IaC | Solutions Architect | Not Started
Phase 3 | Operational Runbook Delivery | 1 day | 2025-08-07 | 2025-08-07 | Production Deployment via IaC | Solutions Architect | Not Started
Phase 3 | Knowledge Transfer Session | 1 day | 2025-08-11 | 2025-08-11 | API Reference Documentation Delivery | Solutions Architect | Not Started
Phase 3 | Test Results Report Delivery | 1 day | 2025-08-08 | 2025-08-08 | User Acceptance Testing | QA Engineer | Not Started
Phase 3 | Hypercare Support Period | 10 days | 2025-08-08 | 2025-08-19 | Production Deployment via IaC | Cloud Engineer | Not Started
Phase 3 | Project Closeout Report | 1 day | 2025-08-19 | 2025-08-19 | Hypercare Support Period | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Kickoff Complete | 2025-07-07 | Phase 1 | Project aligned; stakeholders confirmed; AWS account access granted to nClouds team | Project Manager | Not Started
MS-002 | Architecture Signed Off | 2025-07-16 | Phase 1 | Discovery Summary Report accepted by Lilly Goyah; Dev AWS environment live and security baseline configured | Solutions Architect | Not Started
MS-003 | Classification Endpoint Live | 2025-07-23 | Phase 2 | POST /classify operational in Dev environment with Bedrock integration returning mood label and confidence score | ML/AI Engineer | Not Started
MS-004 | Recommendation Endpoint Live | 2025-07-29 | Phase 2 | GET /recommend and auto-tagging pipeline operational in Dev; CloudWatch monitoring active; IaC templates finalized | ML/AI Engineer | Not Started
MS-005 | Testing Complete | 2025-08-07 | Phase 3 | All functional and integration test cases pass at ≥95% rate; security tests 100% passed; UAT signed off by ANP technical contact | QA Engineer | Not Started
MS-006 | Go-Live | 2025-08-07 | Phase 3 | Production deployment complete; API accessible from FlutterFlow; CloudWatch alarms active; go-live approved by Lilly Goyah | Project Manager | Not Started
MS-007 | Hypercare End and Project Close | 2025-08-19 | Phase 3 | 2-week hypercare complete; all handover artifacts accepted; BAU transition confirmed; project closeout report delivered | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | nClouds PM | nClouds Solutions Architect | nClouds ML/AI Engineer | nClouds Cloud/Security Engineer | Client CEO (Lilly Goyah) | Client IT Contact
Project Kickoff and Governance | A | C | I | I | C | I
Requirements and API Schema Definition | C | A | C | C | C | R
AWS Architecture Design and Decision Record | C | A | C | C | I | C
Firebase Catalog Structure Review and Export | I | C | C | R | I | R
Dev AWS Environment Provisioning | I | C | I | A | I | R
Security Baseline Configuration | I | C | I | A | I | C
Detailed Architecture Specification Delivery | C | A | C | I | I | C
POST /classify Lambda Function Development | I | C | A | C | I | I
GET /recommend Lambda Function Development | I | C | A | C | I | I
Auto-Tagging Batch Lambda Pipeline Development | I | C | A | C | I | I
API Gateway Configuration | I | C | C | A | I | C
DynamoDB Schema Design and Seed Data Load | I | C | R | A | I | C
CloudWatch Dashboards and Alerting | I | C | I | A | I | C
Infrastructure as Code Templates | I | C | C | A | I | C
Test Plan Development | C | I | C | A | I | R
Functional and Integration Testing Execution | C | I | C | A | I | R
Security Testing and Validation | C | C | I | A | I | C
Bedrock Mood Classification Accuracy Validation | C | A | R | C | C | C
Production Deployment | A | C | I | R | I | C
API Reference Documentation | C | A | R | I | I | C
Operational Runbook | C | A | C | R | I | C
Knowledge Transfer Session | A | R | C | C | C | R
User Acceptance Testing Sign-Off | C | I | C | C | I | A
AWS Funding Credits Application | A | I | I | I | C | I
Hypercare Support | A | C | R | R | I | R
Project Closeout Report | A | C | I | I | C | C
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | Responsible - Does the work
A | Accountable - Ultimate ownership
C | Consulted - Provides input
I | Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders — Lilly Goyah; ANP IT Contact; Jonas Bull; nClouds delivery team | Launch project; align on scope RACI and governance; confirm AWS account access and Firebase export plan | Project Manager | 2025-07-07 09:00 AET
Weekly Status Call | Weekly | nClouds PM; nClouds Solutions Architect; ANP IT Contact; Lilly Goyah (optional) | Review progress against plan; surface blockers and decisions; update milestone status | Project Manager | Mondays 10:00 AET
Phase 1 Architecture Review | Once | Jonas Bull; nClouds Solutions Architect; ANP IT Contact; Lilly Goyah | Review and approve AWS Architecture Design; sign off Discovery Summary Report before Phase 2 begins | Solutions Architect | 2025-07-15 10:00 AET
Phase 2 Build Demo | Once | nClouds ML/AI Engineer; nClouds Cloud Engineer; ANP IT Contact | Demonstrate POST /classify and GET /recommend endpoints in Dev; review accuracy results against 90% threshold | ML/AI Engineer | 2025-07-29 10:00 AET
Go-Live Readiness Review | Once | Project Manager; Solutions Architect; ANP IT Contact; Lilly Goyah | Present UAT results; confirm all go-live readiness criteria met; obtain Lilly Goyah go-live approval sign-off | Project Manager | 2025-08-06 10:00 AET
Knowledge Transfer Session | Once | Jonas Bull; nClouds Solutions Architect; ANP IT Contact | Architecture walkthrough; CloudWatch monitoring guidance; IaC deployment; Bedrock prompt tuning; runbook navigation | Solutions Architect | 2025-08-11 09:00 AET
Hypercare Incident Escalation | As required | nClouds Cloud Engineer; ANP IT Contact; Jonas Bull (P1 only) | Notify and resolve production incidents during 2-week hypercare period per agreed SLA response times | Cloud Engineer | Within 4 hours of P1 detection
Project Closeout Meeting | Once | Project Manager; Jonas Bull; ANP IT Contact; Lilly Goyah | Formal project closure; confirm all deliverable acceptances; discuss recommended next steps and managed services options | Project Manager | 2025-08-19 10:00 AET