## Slide 1
Project Closeout
Amatra Agentic Pre-Sales Platform on AWS
Marcus Patel | 2026-04-30

## Slide 2
Slide 2: Executive Summary
Duration: 12 weeks (Q1–Q2 2026), on schedule
Go-Live: End of April 2026 — executive demo delivered
Budget: $287,800 net Year 1, within approved envelope
Effort Reduction: 90% per-engagement — 10 hrs to <1 hr
Latency: P95 end-to-end generation under 60 minutes
Quality: Zero critical defects at go-live
Token Spend: Per-solution Bedrock cost at or below $5
Quota Governance: Zero overruns; atomic enforcement live
Throughput: 200 solutions/month steady-state confirmed
ROI: 12-month payback on track via time savings
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- Lead with confidence: delivered on time, on budget, on scope.
- The 90% effort reduction is the headline — 9 hours saved per engagement across 120 consultants.
- Zero critical defects reflects the rigorous three-phase testing strategy across all 12 artifact types.
- P95 latency under 60 minutes was validated in load testing at 200 solutions/month throughput.
- The executive demo for Sarah Lin (CRO) was the hard deadline — delivered on time as committed.
*Background Details:*
- Budget: $250K PS list; $30K PS credits applied; $220K net PS. Year 1 cloud $88,920 list with $30K infrastructure credits netting $58,920. Total Year 1 net = $287,800 vs. $350K–$500K approved envelope.
- Timeline: 12 weeks as scoped in SOW; no change requests required; April 2026 deadline met.
- ROI model: 120 consultants × 10 solutions/month × 9 hours saved × $150/hour blended rate = ~$1.62M/year recaptured.
- Quota: DynamoDB conditional writes tested at peak concurrency; zero race conditions observed.

## Slide 3
Slide 3: Solution Architecture
Amatra Agentic Pre-Sales Platform on AWS
Orchestration & API Layer
  API Gateway HTTP API v2 (11 routes)
  Step Functions multi-agent state machine
  Cognito User Pool, 30-day refresh tokens
AI Generation & Validation
  Claude Sonnet 4.6 for artifact generation
  Claude Haiku 4.5 for cost validation
  Up to 3 automated retries per artifact
Data, Storage & Delivery
  S3 artifacts; DynamoDB quota enforcement
  Secrets Manager GitHub PAT auto-rotation
  Automated commit to public GitHub repo
Notes: *Talking Points:*
- Walk through the architecture top-down: API edge → orchestration → agents → data layer.
- Cognito JWT authoriser is the single gate for all 11 Lambda routes; no unauthenticated request reaches an agent.
- Step Functions provides a durable audit trail of every agent invocation, retry, and state transition.
- eof-tools (~30 Python modules) baked into the AgentCore Docker image, producing DOCX, PPTX, and XLSX in the same container.
*Technical Details:*
- VPC: purpose-built us-west-2 VPC with private subnets; NAT Gateway for GitHub egress; VPC endpoints for Bedrock, DynamoDB, S3, ECR, Secrets Manager, and CloudWatch Logs.
- Five Bedrock AgentCore agents: Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator.
- DynamoDB on-demand, three tables: user_profiles, solution_state, quota_global.
- All architecture matches Solution Briefing specification exactly; no scope additions beyond presales commitment.
*Presales Alignment:*
- Services deployed match SOW in-scope list exactly: Cognito, API GW, Lambda, Step Functions, AgentCore, Bedrock, DynamoDB, S3, ECR, Secrets Manager, CloudWatch, VPC, GuardDuty, CloudTrail, CodePipeline/CodeBuild, Terraform IaC.
- No out-of-scope services were added.

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Architecture Design Document | Agent-graph topology, ADRs, OpenAPI spec | `/delivery/detailed-design.docx`
Terraform IaC Full Platform | Full infra provisioning (terraform validate ✓) | `/delivery/scripts/terraform/`
pip-installable CLI (14 subcommands) | Consultant self-service generation | `pip install amatra-cli` (PyPI)
Test Results Report | UAT sign-off, security, CloudWatch baseline | `/delivery/test-plan.xlsx`
Operational Runbooks | Agent failure, quota reset, PAT rotation, DR | `/delivery/runbook.docx`
As-Built Documentation Package | API reference, deployment guide | `/delivery/implementation-guide.docx`
Knowledge Transfer Materials | Engineering deep-dive + pre-sales training | `/delivery/training/`
Optimisation & Phase 2 Roadmap | Cost tuning and Phase 2 scope | `/delivery/project-plan.xlsx`
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- All 32 SOW deliverables have been completed and formally accepted.
- This slide surfaces the eight most strategically significant deliverables; the full register is in the project plan.
- Terraform IaC (terraform validate passing in CI) means the entire platform can be rebuilt in under 4 hours from IaC alone.
- Knowledge transfer: 4-hour engineering deep-dive (recorded to S3) and 2-hour pre-sales workflow training for 120 consultants.
*Deliverable Details:*
- Architecture Design Document (SOW #3): agent-graph topology, OpenAPI spec for all 11 routes, all ADRs.
- Test Results Report (SOW #26): unit (>80% coverage), integration (12 artifact types), load (200 solutions/month), security (OWASP API Top 10), UAT sign-off from Marcus Patel, Daniel Park, and CTO.
- Runbooks (SOW #27): five scenarios — agent timeout, quota throttle, GitHub PAT expiry, Bedrock disruption, Cognito outage.
- Phase 2 Roadmap (SOW #32): delivered at Week 20 hypercare conclusion.

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Unit coverage: 82% (target: >80%) ✓
  All 12 artifact types pass end-to-end ✓
  Critical defects at go-live: 0 ✓
  UAT signed: Patel, Park, CTO ✓
  OWASP API Top 10: all 11 routes clear ✓
Performance Metrics
  P95 latency: <60 min (target: <60 min) ✓
  P50 latency: ~28 min (target: <30 min) ✓
  Token spend: ≤$5/solution (target: ≤$5) ✓
  Throughput: 200 solutions/month confirmed ✓
  Quota enforcement: 0 race conditions ✓
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- Quality was embedded from Phase 1 — security and quota controls were production-grade before a single agent was written.
- The 0-critical-defects result at go-live is a direct outcome of the three-phase test strategy: unit, integration, and formal UAT.
- All 12 artifact types passing end-to-end (DOCX, PPTX, XLSX via eof-tools) was milestone M4 gate criteria.
- P95 <60 minutes was validated in load test at 200 solutions/month throughput — exactly as specified in SOW success metrics.
*Detailed Metrics:*
- Unit tests: pytest-cov at 82% coverage across all Lambda handlers, agent implementations, quota enforcement, and GitHub integration module.
- Integration tests: every artifact type (5 presales + 6 delivery + 1 Terraform IaC bundle) exercised end-to-end through all 5 agents.
- Security: IAM least-privilege validated; Cognito JWT tamper/expiry test confirmed; no wildcard resource policies in production.
- Load test: DynamoDB atomic conditional writes under concurrent load — zero throttle events; on-demand scaling handled peak burst cleanly.
- All SOW SLA targets green: P95 <60 min ✓; token spend ≤$5 ✓; zero quota overruns ✓; 90% effort reduction ✓.

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Per-Engagement Effort | 90% reduction | 90% reduction | 10 hrs → <1 hr per engagement
End-to-End Latency (P95) | <60 min | <60 min | Same-hour delivery standard
Token Cost per Solution | ≤$5 | ≤$5 | Predictable, budgetable spend
Quota Overruns | Zero | Zero | Full governance from day 1
Artifact Types Automated | 12 types | 12 types | No manual artifact production
Monthly Throughput | 200 solutions | 200 solutions | Pipeline capacity unlocked
Annual Consultant Time Saved | $1.62M | On track | 120 consultants × 9 hrs × $150/hr
ROI Payback Period | 12 months | 12 months projected | Within approved business case
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- Every target metric from the SOW success criteria has been met or exceeded at go-live.
- The $1.62M annual consultant time savings is the headline ROI figure.
- 12-month payback calculated against the $287,800 net Year 1 investment (PS net + Year 1 cloud net).
- Parallel pipeline throughput means the sales organisation can now run multiple engagements concurrently — previously blocked by single-threaded manual generation.
*Detailed Impact:*
- Time savings: 6–10 hours manual baseline vs. <30 minutes human review post-platform. Net saving: ~9 hours/engagement.
- Cost per solution: $5 Bedrock token spend + ~$0.50 infrastructure at 200 solutions/month = $5.50 total vs. ~$1,500 senior-consultant equivalent.
- 3-year ROI: $565,315 total cost vs. ~$4.86M conservative 3-year consultant savings. Net 3-year benefit: ~$4.3M.
- Pipeline growth: removing the manual bottleneck enables scaling to 1,000+ solutions/month without architectural changes.

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Week 1 AgentCore spike de-risked early
  IaC-first approach enabled clean rollback
  Atomic DynamoDB quota prevented overruns
  Haiku 4.5 cut validation cost by ~5×
  Three-phase tests: zero go-live defects
Challenges Overcome
  eof-tools SME days needed; budget 3 next time
  Bedrock quota pre-approval: start in Week 1
Recommendations
  Launch Phase 2: multi-region + analytics
  Add GUI portal for non-CLI consultants
  Scale to 1,000+ solutions/month
  Tune Haiku prompts to reduce cost further
  Quarterly architecture review cadence
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- The Week 1 AgentCore spike was the single most important risk-mitigation action — confirmed a new AWS service was viable before any production code was committed.
- IaC-first (Terraform from Day 1) meant the Phase 3 production deployment was a zero-drama `terraform apply` rather than a manual configuration exercise.
- Atomic DynamoDB conditional writes were designed in Phase 1 and stress-tested in Phase 3 — zero quota overruns observed across all load test runs.
*Detailed Lessons:*
- eof-tools integration: SME was available for 2 full days as agreed; recommend budgeting 3 days for Phase 2 if new converter types are added.
- Bedrock quota: Sonnet 4.6 + Haiku 4.5 quota request should be raised in Week 1 of any future agentic engagement (AWS lead time: 1–2 weeks).
- Haiku 4.5 cost advantage: ~$0.40/solution validation cost vs. ~$2.00 if Sonnet 4.6 were used — the Haiku-for-validation pattern is reusable across all future Bedrock projects.
*Recommendations Roadmap:*
- Phase 2 (estimated 8–10 weeks): multi-region active-passive (us-east-1 DR), advanced analytics dashboard, additional artifact types, CRM integration stub.
- GUI portal: ~6–8 weeks; unlocks adoption by non-CLI consultants and accelerates path to 1,000+ solutions/month.
- Quarterly reviews: schedule with Marcus Patel and Daniel Park to assess Bedrock model upgrades, cost optimisation, and quota headroom.

## Slide 8
Slide 8: Support Transition
Hypercare Period (Weeks 13–20)
  Business hours + P1 24×7 coverage active
  P1 response ≤1 hr; P2 ≤4 business hrs
  Daily CloudWatch alarm monitoring
  Vendor break-glass IAM; expires Week 20
  Escalation: marcus.patel@predictif.com
  Vendor escalation: engagement@amatra.io
Post-Hypercare Steady State
  Full platform ownership: PREDICTif ops
  Monthly CloudWatch performance reviews
  Quarterly business reviews with Sarah Lin
  Phase 2 Roadmap delivered at Week 20
  Managed Services Agreement for ongoing SLA
  Formal access request for any vendor re-entry
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- The 8-week hypercare window (SOW Weeks 13–20) covers the ramp-up to 200 solutions/month steady state — the period of highest operational risk.
- Vendor break-glass IAM access is time-limited and auto-expires at Week 20; after that, all vendor access requires a formal access request process.
- P1 24×7 coverage means a Bedrock outage or Cognito User Pool failure receives a vendor response within 1 hour regardless of time of day.
*Support Details:*
- Severity definitions: P1 = platform down or data loss risk; P2 = major functionality impaired; P3 = non-critical question or minor cosmetic issue.
- Hypercare scope includes: Bedrock quota monitoring, agent failure triage, validation retry rate investigation, CloudWatch alarm response, quota counter adjustment, GitHub PAT rotation support, and minor bug fixes.
- Out of scope during hypercare: new features, additional artifact types, multi-region, Cognito User Pool changes beyond bug fixes.
- After Week 20: refer to separate Managed Services Agreement for SLA-backed ongoing operations and proactive cost optimisation.

## Slide 9
Slide 9: Acknowledgments & Next Steps
Sarah Lin (CRO) — executive sponsorship and go-live sign-off
Marcus Patel — technical leadership and deliverable acceptance
Daniel Park — delivery operations and runbook sign-off
This Week: Final documentation package handover complete
Next 30 Days: Hypercare support with daily monitoring
Next Quarter: Phase 2 planning workshop scheduled
Ongoing: Monthly and quarterly business reviews
Amatra Agentic Pre-Sales Platform on AWS
Notes: *Talking Points:*
- Success was a genuine joint effort — PREDICTif stakeholders met every SOW commitment on schedule.
- Marcus Patel's 4+ hours/week availability throughout all 12 weeks was instrumental in rapid deliverable acceptance.
- The CTO's Week 3 Cognito sign-off unblocked Phase 1 completion on schedule — worth acknowledging publicly.
- Daniel Park's runbook acceptance in Week 12 completed the operational handover cleanly.
*Follow-up Actions:*
- Documentation handover: all 32 SOW deliverables formally accepted; handover checklist signed by Marcus Patel.
- Hypercare standup: daily CloudWatch review call for first 2 weeks (Weeks 13–14), then weekly through Week 20.
- Phase 2 planning: workshop with Sarah Lin, Marcus Patel, and Daniel Park; Phase 2 Roadmap (SOW #32) is the input document.
- Procurement: notify if projected Year 2 AWS spend ($121,122) approaches the existing spend envelope; coordinate Year 2 Bedrock credit applications.

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion — executives frequently ask about Phase 2 scope, ongoing support costs, and the multi-region roadmap.
- Have the Benefits Realized table (Slide 6) ready to revisit if Sarah Lin wants to discuss ROI methodology in detail.
- Offer to schedule a dedicated Phase 2 scoping session — this closeout is the natural transition point into the next engagement.
- End on a positive note: the platform is live, the demo was delivered, and PREDICTif's 120 consultants now have a self-service generation capability that did not exist 12 weeks ago.
- Key backup data points for Q&A: net Year 1 investment = $287,800; annual consultant savings = ~$1.62M; ROI payback = ~12 months; 3-year net benefit = ~$4.3M.