## Cover
Project Plan
Generated: | August 17, 2026
Solution: | Tmpy52K93Pk
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 — Foundation & Governance | Project Kickoff | 1 day | 2025-03-03 | 2025-03-03 | None | Project Manager | Not Started
Phase 1 — Foundation & Governance | Management Account Access Provisioning | 1 day | 2025-03-04 | 2025-03-04 | Project Kickoff | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | Stakeholder RACI Confirmation | 2 days | 2025-03-03 | 2025-03-04 | Project Kickoff | Project Manager | Not Started
Phase 1 — Foundation & Governance | Discovery Interviews and Requirements Gathering | 5 days | 2025-03-04 | 2025-03-07 | Management Account Access Provisioning | Solution Architect | Not Started
Phase 1 — Foundation & Governance | Compliance Framework Confirmation | 5 days | 2025-03-04 | 2025-03-07 | Discovery Interviews and Requirements Gathering | Solution Architect | Not Started
Phase 1 — Foundation & Governance | Discovery Report | 5 days | 2025-03-10 | 2025-03-14 | Compliance Framework Confirmation | Solution Architect | Not Started
Phase 1 — Foundation & Governance | Phase 1 Architecture Design Document | 5 days | 2025-03-17 | 2025-03-21 | Discovery Report | Solution Architect | Not Started
Phase 1 — Foundation & Governance | AWS Control Tower Deployment | 3 days | 2025-03-17 | 2025-03-19 | Phase 1 Architecture Design Document | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | OU Structure and SCP/RCP Implementation | 3 days | 2025-03-19 | 2025-03-21 | AWS Control Tower Deployment | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | IAM Identity Center Configuration | 2 days | 2025-03-21 | 2025-03-25 | OU Structure and SCP/RCP Implementation | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | Centralised Logging — Log Archive and Audit Accounts | 2 days | 2025-03-21 | 2025-03-25 | OU Structure and SCP/RCP Implementation | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | AWS Config Deployment — Both Regions | 2 days | 2025-03-24 | 2025-03-26 | Centralised Logging — Log Archive and Audit Accounts | Cloud Engineer | Not Started
Phase 1 — Foundation & Governance | Architecture Design Review and Sign-Off | 2 days | 2025-03-26 | 2025-03-28 | Phase 1 Architecture Design Document | Project Manager | Not Started
Phase 2 — Networking & Connectivity | Transit Gateway Deployment — us-east-1 and us-east-2 | 3 days | 2025-03-31 | 2025-04-02 | Architecture Design Review and Sign-Off | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | Hub VPCs and NAT Gateway Configuration | 2 days | 2025-04-02 | 2025-04-04 | Transit Gateway Deployment — us-east-1 and us-east-2 | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | VPC IPAM Configuration | 2 days | 2025-04-02 | 2025-04-04 | Transit Gateway Deployment — us-east-1 and us-east-2 | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | AWS Network Firewall Deployment | 4 days | 2025-04-07 | 2025-04-10 | Hub VPCs and NAT Gateway Configuration | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | Spoke VPC Terraform Modules | 3 days | 2025-04-11 | 2025-04-15 | VPC IPAM Configuration | Solutions Engineer | Not Started
Phase 2 — Networking & Connectivity | Site-to-Site VPN Configuration | 3 days | 2025-04-14 | 2025-04-16 | Hub VPCs and NAT Gateway Configuration | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | Network Flow Testing and Validation | 3 days | 2025-04-17 | 2025-04-21 | Site-to-Site VPN Configuration; Spoke VPC Terraform Modules | Cloud Engineer | Not Started
Phase 2 — Networking & Connectivity | Network Testing Report | 2 days | 2025-04-22 | 2025-04-24 | Network Flow Testing and Validation | Solution Architect | Not Started
Phase 3 — Security Automation & Handover | Security Hub and FSBP Conformance Deployment | 3 days | 2025-04-28 | 2025-04-30 | Network Testing Report | Security Engineer | Not Started
Phase 3 — Security Automation & Handover | GuardDuty Organisation-Wide Deployment | 2 days | 2025-04-28 | 2025-04-30 | Network Testing Report | Security Engineer | Not Started
Phase 3 — Security Automation & Handover | AWS Config Rules and Conformance Packs | 3 days | 2025-04-30 | 2025-05-02 | GuardDuty Organisation-Wide Deployment | Security Engineer | Not Started
Phase 3 — Security Automation & Handover | CloudTrail Lake Configuration | 2 days | 2025-04-30 | 2025-05-02 | Security Hub and FSBP Conformance Deployment | Security Engineer | Not Started
Phase 3 — Security Automation & Handover | AFT Pipeline Deployment and Validation | 4 days | 2025-05-05 | 2025-05-08 | AWS Config Rules and Conformance Packs | Cloud Engineer | Not Started
Phase 3 — Security Automation & Handover | Two Workload Accounts Vended via AFT | 2 days | 2025-05-09 | 2025-05-12 | AFT Pipeline Deployment and Validation | Cloud Engineer | Not Started
Phase 3 — Security Automation & Handover | CI/CD Pipeline Finalisation | 3 days | 2025-05-09 | 2025-05-13 | AFT Pipeline Deployment and Validation | Solutions Engineer | Not Started
Phase 3 — Security Automation & Handover | Cost Explorer and AWS Budgets Configuration | 1 day | 2025-05-09 | 2025-05-09 | Two Workload Accounts Vended via AFT | Solutions Engineer | Not Started
Phase 3 — Security Automation & Handover | Centralised CloudWatch Dashboards and SNS Alerting | 2 days | 2025-05-09 | 2025-05-12 | Two Workload Accounts Vended via AFT | Solutions Engineer | Not Started
Phase 3 — Security Automation & Handover | Test Plan Execution — SCP and Guardrail Testing | 3 days | 2025-05-12 | 2025-05-14 | CI/CD Pipeline Finalisation; Two Workload Accounts Vended via AFT | QA Engineer | Not Started
Phase 3 — Security Automation & Handover | Account Vending Validation — Three Consecutive Runs | 1 day | 2025-05-14 | 2025-05-14 | Test Plan Execution — SCP and Guardrail Testing | QA Engineer | Not Started
Phase 3 — Security Automation & Handover | User Acceptance Testing | 2 days | 2025-05-15 | 2025-05-16 | Account Vending Validation — Three Consecutive Runs | Project Manager | Not Started
Phase 3 — Security Automation & Handover | Test Results Report | 1 day | 2025-05-19 | 2025-05-19 | User Acceptance Testing | QA Engineer | Not Started
Phase 3 — Security Automation & Handover | Operational Runbooks Development | 5 days | 2025-05-12 | 2025-05-16 | CI/CD Pipeline Finalisation | Technical Writer | Not Started
Phase 3 — Security Automation & Handover | As-Built Architecture Document | 3 days | 2025-05-14 | 2025-05-16 | Operational Runbooks Development | Technical Writer | Not Started
Phase 3 — Security Automation & Handover | Administrator and Security Team Training | 3 days | 2025-05-19 | 2025-05-21 | As-Built Architecture Document | Cloud Engineer | Not Started
Phase 3 — Security Automation & Handover | Production Go-Live | 1 day | 2025-05-22 | 2025-05-22 | Test Results Report; Administrator and Security Team Training | Project Manager | Not Started
Hypercare | Hypercare Support Weeks 13 to 16 | 20 days | 2025-05-26 | 2025-06-13 | Production Go-Live | Cloud Engineer | Not Started
Hypercare | Optimization Recommendations Report | 5 days | 2025-06-09 | 2025-06-13 | Hypercare Support Weeks 13 to 16 | Solution Architect | Not Started
Hypercare | Hypercare Support Closeout Report | 1 day | 2025-06-16 | 2025-06-16 | Optimization Recommendations Report | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Kickoff Complete | 2025-03-03 | Phase 1 — Foundation & Governance | All stakeholders identified; RACI confirmed; requirements baseline documented | Project Manager | Not Started
MS-002 | Discovery Report Accepted | 2025-03-14 | Phase 1 — Foundation & Governance | Current state documented; OU design confirmed; compliance frameworks identified; report accepted by Client IT Owner | Solution Architect | Not Started
MS-003 | Architecture Approved | 2025-03-28 | Phase 1 — Foundation & Governance | Phase 1 Architecture Design Document signed off by Client Executive Sponsor; Control Tower live; OU hierarchy, SCPs, IAM Identity Center, and centralised logging operational | Project Manager | Not Started
MS-004 | Governance Foundation Live | 2025-03-28 | Phase 1 — Foundation & Governance | Control Tower ACTIVE in us-east-1 and us-east-2; seven-OU hierarchy deployed; all SCPs and RCPs enforced; Log Archive, Audit, and IAM Identity Center SSO operational | Cloud Engineer | Not Started
MS-005 | Network Foundation Live | 2025-04-24 | Phase 2 — Networking & Connectivity | TGW hub-spoke operational in both regions; Network Firewall deployed; IPAM configured; NAT Gateway egress active; VPN to on-premises established; Network Testing Report accepted | Solution Architect | Not Started
MS-006 | Security Automation Complete | 2025-05-16 | Phase 3 — Security Automation & Handover | Security Hub FSBP active in all accounts and both regions; GuardDuty org-wide; Config rules deployed; CloudTrail Lake configured; AFT pipeline validated; two workload accounts vended | Cloud Engineer | Not Started
MS-007 | Go-Live | 2025-05-22 | Phase 3 — Security Automation & Handover | All success metrics validated; UAT signed off by Client Executive Sponsor and Client IT Owner; zero critical Security Hub findings; AFT <30 min confirmed; production go-live confirmed | Project Manager | Not Started
MS-008 | Hypercare End | 2025-06-16 | Hypercare | 4-week hypercare concluded; Optimization Recommendations Report delivered; Hypercare Closeout Report accepted by Client Executive Sponsor; BAU handover confirmed | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Arch | Vendor Eng | Vendor QA | Client Exec | Client IT | Client Sec | Client SME
Project Kickoff and RACI Finalisation | A | C | I | I | C | R | C | C
Discovery and Requirements Gathering | C | A | R | I | I | C | C | R
Phase 1 Architecture Design Document | I | A | R | C | I | C | C | C
Architecture Design Review Sign-Off | C | R | C | I | A | C | C | I
AWS Control Tower Deployment | C | C | A | I | I | C | I | I
OU Structure and SCP/RCP Implementation | C | C | R | I | I | C | A | C
IAM Identity Center Configuration | C | C | R | I | I | A | C | C
Centralised Logging — CloudTrail and Config | C | C | R | I | I | C | A | I
Transit Gateway and Networking Build | C | C | A | I | I | C | I | C
Network Firewall and IPAM Configuration | C | C | A | I | I | C | C | I
Site-to-Site VPN to On-Premises | C | C | R | I | I | A | I | C
Network Testing Report | C | R | R | A | I | C | I | I
AFT Pipeline Setup and Validation | C | C | A | R | I | C | I | I
Security Hub and GuardDuty Deployment | C | C | R | I | I | C | A | I
AWS Config Rules and Conformance Packs | C | C | R | C | I | C | A | I
CloudTrail Lake Configuration | C | C | R | I | I | C | A | I
CI/CD Pipeline Finalisation | C | C | A | C | I | C | I | I
Test Plan Development | C | C | C | A | I | C | I | I
SCP and Guardrail Testing | I | C | R | C | I | C | A | I
Account Vending Validation | C | C | R | A | I | C | C | I
Network Flow Testing | I | C | R | A | I | C | I | I
Security Posture Validation | I | C | R | C | I | C | A | I
User Acceptance Testing | R | C | C | C | A | C | C | R
Go-Live Planning and Cutover | A | C | R | C | C | C | C | I
Operational Runbooks Development | C | C | R | I | I | C | C | A
Administrator and Security Team Training | C | C | R | I | I | A | C | C
Two Workload Accounts Vended via AFT | C | C | R | A | I | C | I | I
As-Built Architecture Document | C | A | R | I | I | C | C | I
Hypercare Support | R | C | A | I | I | C | C | I
Budget Monitoring and Cost Governance | A | I | I | I | C | R | I | C
Change Control Management | A | C | C | I | C | R | C | I
Optimization Recommendations Report | C | A | R | I | C | C | I | I
Project Closeout and BAU Transition | A | C | C | I | C | R | C | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | A C C C C R A A C A: Responsible - Does the work
A | A C C C C R A A C A: Accountable - Ultimate ownership
C | A C C C C R A A C A: Consulted - Provides input
I | A C C C C R A A C A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff Workshop | Once | All stakeholders — Vendor and Client teams; Executive Sponsor; Cloud IT Owner; Security Lead; SMEs | Launch project; align on scope; confirm RACI; agree governance cadence and tools | Project Manager | 2025-03-03 (4 hours)
Weekly Status Call | Weekly | Cloud IT Owner; Security Lead; Vendor PM; Vendor Arch; Vendor Eng leads | Review progress against plan; discuss blockers; track risks and decisions | Project Manager | Mondays 10:00 AM ET
Architecture Design Review Workshop | Once | Client Executive Sponsor; Client IT Owner; Client Security Lead; Vendor PM; Vendor Arch | Review and approve Phase 1 Architecture Design Document; agree go/no-go for deployment | Solution Architect | 2025-03-26 (3 hours)
Phase Gate Review — Phase 1 | Once | Client Executive Sponsor; Client IT Owner; Vendor PM; Vendor Arch | Review Phase 1 completion criteria; confirm governance foundation live; approve Phase 2 start | Project Manager | 2025-03-28 (1 hour)
Phase Gate Review — Phase 2 | Once | Client Executive Sponsor; Client IT Owner; Client Networking Lead; Vendor PM; Vendor Arch | Review Phase 2 completion criteria; confirm network foundation live; approve Phase 3 start | Project Manager | 2025-04-25 (1 hour)
Design Q&A and Technical Sync | Bi-weekly | Client IT Owner; Client Security Lead; Vendor Arch; Vendor Eng leads | Resolve open technical design questions; review configuration decisions; confirm approach | Solution Architect | Wednesdays 2:00 PM ET
Risk and Issue Review | Weekly | Vendor PM; Client IT Owner; Client Executive Sponsor (escalation) | Review risk register; track open issues; agree mitigation actions and owners | Project Manager | Fridays 11:00 AM ET
Security Review Sync | Weekly | Client Security Lead; Vendor Arch; Vendor Security Eng | Review SCP design; confirm compliance framework inputs; validate security posture progress | Security Engineer | Tuesdays 11:00 AM ET
UAT Session | Once | Client IT Owner; Client Security Lead; Client SMEs; Vendor PM; Vendor Eng; Vendor QA | Client performs end-to-end platform walkthrough; validate all success criteria against acceptance checklist | Project Manager | 2025-05-15 (4 hours)
Go-Live Readiness Review | Once | Client Executive Sponsor; Client IT Owner; Client Security Lead; Vendor PM; Vendor Arch | Present UAT results and go-live readiness checklist; obtain go-live approval sign-off | Project Manager | 2025-05-21 (1 hour)
Administrator Training — Infrastructure Track | Once | Client IT Owner; Client Platform Administrators; Vendor Eng | Control Tower operations; AFT account vending; day-2 operations and Cost Explorer | Cloud Engineer | 2025-05-19 (6 hours — 3 × 2-hour sessions)
Security Team Training — Security Track | Once | Client Security Lead; Client Security Team; Vendor Security Eng | Security Hub triage; GuardDuty investigation; CloudTrail Lake queries and runbook walkthrough | Security Engineer | 2025-05-20 (6 hours — 3 × 2-hour sessions)
Hypercare Incident Escalation | As required | Client IT Owner; Vendor PM; Vendor Eng on-call | Notify and resolve P1 incidents during hypercare period; confirm resolution and prevention | Cloud Engineer | Within 2 business hours of detection
Hypercare Weekly Check-In | Weekly during hypercare | Client IT Owner; Client Security Lead; Vendor PM; Vendor Eng | Review hypercare issues and resolutions; track any open P2/P3 items; confirm operational readiness | Project Manager | Mondays 10:00 AM ET (Weeks 13-16)
Project Closeout and Handover | Once | Client Executive Sponsor; Client IT Owner; Vendor PM; Vendor Arch | Formal project closure; BAU handover confirmation; deliver Optimization Recommendations Report | Project Manager | 2025-06-16 (1 hour)