## Cover
Project Plan
Generated: | June 30, 2026
Solution: | Tmp69J9L8V7
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 — Discovery & Architecture | Project Kickoff and RACI Alignment | 1 day | 2026-05-04 | 2026-05-04 | None | Amatra PM | Not Started
Phase 1 — Discovery & Architecture | Clinical Workflow Discovery Sessions | 3 days | 2026-05-05 | 2026-05-07 | Project Kickoff and RACI Alignment | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | Epic FHIR R4 and Mirth Connect Topology Assessment | 3 days | 2026-05-05 | 2026-05-07 | Project Kickoff and RACI Alignment | Amatra Engineer | Not Started
Phase 1 — Discovery & Architecture | AWS Organization and Landing Zone Documentation | 2 days | 2026-05-07 | 2026-05-08 | Epic FHIR R4 and Mirth Connect Topology Assessment | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | HIPAA BAA and PHI Data-Handling Requirements Workshop | 2 days | 2026-05-11 | 2026-05-12 | Project Kickoff and RACI Alignment | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | ML Feature Requirements Workshop — Sepsis Model | 2 days | 2026-05-11 | 2026-05-12 | Clinical Workflow Discovery Sessions | Amatra Engineer | Not Started
Phase 1 — Discovery & Architecture | Azure AD Federation Requirements Capture | 1 day | 2026-05-12 | 2026-05-12 | HIPAA BAA and PHI Data-Handling Requirements Workshop | Amatra Engineer | Not Started
Phase 1 — Discovery & Architecture | Current State Assessment Report | 5 days | 2026-05-12 | 2026-05-18 | Clinical Workflow Discovery Sessions | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | Epic FHIR R4 and Mirth Connect Integration Specification | 5 days | 2026-05-19 | 2026-05-25 | Epic FHIR R4 and Mirth Connect Topology Assessment | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | HIPAA PHI Data-Handling Requirements Document | 3 days | 2026-05-19 | 2026-05-21 | HIPAA BAA and PHI Data-Handling Requirements Workshop | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | HLD and LLD Architecture Documents | 5 days | 2026-05-26 | 2026-06-01 | Current State Assessment Report | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | Security Architecture Document | 5 days | 2026-05-26 | 2026-06-01 | HIPAA PHI Data-Handling Requirements Document | Amatra Architect | Not Started
Phase 1 — Discovery & Architecture | Data Flow Diagrams and FHIR Resource Mapping Specification | 4 days | 2026-05-26 | 2026-05-29 | Epic FHIR R4 and Mirth Connect Integration Specification | Amatra Engineer | Not Started
Phase 1 — Discovery & Architecture | Approved Architecture Assessment Report | 3 days | 2026-06-01 | 2026-06-03 | HLD and LLD Architecture Documents | Amatra Architect | Not Started
Phase 2 — Environment Build & Data Pipeline | IaC Modules — All 4 Environments Provisioned | 10 days | 2026-06-08 | 2026-06-19 | Approved Architecture Assessment Report | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Transit Gateway and PrivateLink Connectivity Configuration | 5 days | 2026-06-22 | 2026-06-26 | IaC Modules — All 4 Environments Provisioned | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Azure AD SAML 2.0 Federation with Amazon Cognito | 5 days | 2026-06-22 | 2026-06-26 | IaC Modules — All 4 Environments Provisioned | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | KMS CMK Key Policies and PHI Encryption Implementation | 5 days | 2026-06-22 | 2026-06-26 | IaC Modules — All 4 Environments Provisioned | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | HIPAA Audit Logging Implementation | 3 days | 2026-06-29 | 2026-07-01 | KMS CMK Key Policies and PHI Encryption Implementation | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | CI/CD Pipelines with Blue/Green Deployment | 5 days | 2026-06-29 | 2026-07-03 | IaC Modules — All 4 Environments Provisioned | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Amazon HealthLake FHIR Data Store Provisioning | 5 days | 2026-06-29 | 2026-07-03 | IaC Modules — All 4 Environments Provisioned | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Kinesis Data Streams Ingestion Pipeline Build | 10 days | 2026-07-06 | 2026-07-17 | Transit Gateway and PrivateLink Connectivity Configuration | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Epic FHIR R4 Connector Development | 10 days | 2026-07-06 | 2026-07-17 | Azure AD SAML 2.0 Federation with Amazon Cognito | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | HL7 v2.3 Mirth Connect Adapter Development | 10 days | 2026-07-06 | 2026-07-17 | Transit Gateway and PrivateLink Connectivity Configuration | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | SageMaker Feature Store Pipelines Build | 7 days | 2026-07-20 | 2026-07-28 | Kinesis Data Streams Ingestion Pipeline Build | Amatra Engineer | Not Started
Phase 2 — Environment Build & Data Pipeline | Data Ingestion Pipeline End-to-End Validation | 3 days | 2026-07-29 | 2026-07-31 | SageMaker Feature Store Pipelines Build | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | Sepsis Risk Prediction Model Development and Training | 20 days | 2026-06-22 | 2026-07-17 | Approved Architecture Assessment Report | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | SHAP Explainability Pipeline Development | 10 days | 2026-07-20 | 2026-07-31 | Sepsis Risk Prediction Model Development and Training | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | Amazon Bedrock Clinical Narrative Integration | 10 days | 2026-08-03 | 2026-08-14 | SHAP Explainability Pipeline Development | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | Alert Routing Service Build | 7 days | 2026-08-03 | 2026-08-11 | Amazon Bedrock Clinical Narrative Integration | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | 30-Day Readmission Prediction Model Development | 20 days | 2026-08-17 | 2026-09-11 | Sepsis Risk Prediction Model Development and Training | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | Rapid-Response Early Deterioration Model Development | 20 days | 2026-08-17 | 2026-09-11 | Sepsis Risk Prediction Model Development and Training | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | Clinical Staff Dashboard Development | 20 days | 2026-08-17 | 2026-09-11 | Alert Routing Service Build | Amatra Engineer | Not Started
Phase 3 — ML Model Development & Integration | QuickSight Outcomes and Model Monitoring Dashboards | 10 days | 2026-09-14 | 2026-09-25 | 30-Day Readmission Prediction Model Development | Amatra Engineer | Not Started
Phase 4 — Testing & Validation | Test Plan Development and Approval | 5 days | 2026-09-07 | 2026-09-11 | Data Ingestion Pipeline End-to-End Validation | Amatra QA | Not Started
Phase 4 — Testing & Validation | Functional Testing — Data Ingestion and Feature Store | 5 days | 2026-09-14 | 2026-09-18 | Test Plan Development and Approval | Amatra QA | Not Started
Phase 4 — Testing & Validation | Functional Testing — ML Inference Endpoints | 5 days | 2026-09-14 | 2026-09-18 | Test Plan Development and Approval | Amatra QA | Not Started
Phase 4 — Testing & Validation | Integration Testing — Epic FHIR R4 End-to-End | 5 days | 2026-09-21 | 2026-09-25 | Functional Testing — Data Ingestion and Feature Store | Amatra QA | Not Started
Phase 4 — Testing & Validation | Integration Testing — HL7 v2.3 Mirth Connect Adapter | 5 days | 2026-09-21 | 2026-09-25 | Functional Testing — Data Ingestion and Feature Store | Amatra QA | Not Started
Phase 4 — Testing & Validation | End-to-End Latency Load Test | 3 days | 2026-09-28 | 2026-09-30 | Integration Testing — Epic FHIR R4 End-to-End | Amatra QA | Not Started
Phase 4 — Testing & Validation | Multi-Region Failover Test | 3 days | 2026-09-28 | 2026-09-30 | Integration Testing — Epic FHIR R4 End-to-End | Amatra QA | Not Started
Phase 4 — Testing & Validation | Sepsis Model Accuracy Validation | 3 days | 2026-10-01 | 2026-10-05 | End-to-End Latency Load Test | Amatra QA | Not Started
Phase 4 — Testing & Validation | HIPAA Security Controls Validation | 3 days | 2026-10-01 | 2026-10-05 | Multi-Region Failover Test | Amatra QA | Not Started
Phase 4 — Testing & Validation | External Penetration Testing Coordination | 5 days | 2026-10-01 | 2026-10-07 | HIPAA Security Controls Validation | Amatra Engineer | Not Started
Phase 4 — Testing & Validation | Pilot Facility UAT Execution | 5 days | 2026-10-08 | 2026-10-14 | Sepsis Model Accuracy Validation | Amatra QA | Not Started
Phase 4 — Testing & Validation | Defect Triage and Critical Issue Resolution | 3 days | 2026-10-15 | 2026-10-19 | Pilot Facility UAT Execution | Amatra Engineer | Not Started
Phase 4 — Testing & Validation | Go-Live Readiness Review and CMO/CIO Sign-Off | 2 days | 2026-10-20 | 2026-10-21 | Defect Triage and Critical Issue Resolution | Amatra PM | Not Started
Phase 5 — Production Rollout & Hypercare | Phase 1 Production Go-Live — Sepsis Model and Pipeline | 1 day | 2026-10-31 | 2026-10-31 | Go-Live Readiness Review and CMO/CIO Sign-Off | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Phase 1 Post-Go-Live 48-Hour Shadow Validation | 2 days | 2026-11-01 | 2026-11-02 | Phase 1 Production Go-Live — Sepsis Model and Pipeline | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Phase 2 Production Deployment — Readmission and Rapid-Response | 1 day | 2027-02-28 | 2027-02-28 | 30-Day Readmission Prediction Model Development | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Per-Facility Cohort Rollout Execution — All 18 Hospitals | 60 days | 2027-03-01 | 2027-05-23 | Phase 2 Production Deployment — Readmission and Rapid-Response | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Clinical Train-the-Trainer Enablement Program Delivery | 30 days | 2027-03-01 | 2027-04-09 | Phase 2 Production Deployment — Readmission and Rapid-Response | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Architecture and Operations Knowledge Transfer Sessions | 10 days | 2027-05-26 | 2027-06-06 | Per-Facility Cohort Rollout Execution — All 18 Hospitals | Amatra Architect | Not Started
Phase 5 — Production Rollout & Hypercare | Final As-Built Documentation and IaC Repository Handover | 10 days | 2027-05-26 | 2027-06-06 | Architecture and Operations Knowledge Transfer Sessions | Amatra Architect | Not Started
Phase 5 — Production Rollout & Hypercare | Operational Runbooks Delivery | 7 days | 2027-05-26 | 2027-06-03 | Architecture and Operations Knowledge Transfer Sessions | Amatra Architect | Not Started
Phase 5 — Production Rollout & Hypercare | Enterprise General Availability — All 18 Hospitals | 1 day | 2027-06-30 | 2027-06-30 | Per-Facility Cohort Rollout Execution — All 18 Hospitals | Amatra PM | Not Started
Phase 5 — Production Rollout & Hypercare | 8-Week Hypercare Support Period | 56 days | 2027-07-01 | 2027-08-25 | Enterprise General Availability — All 18 Hospitals | Amatra Engineer | Not Started
Phase 5 — Production Rollout & Hypercare | Project Closure Outcomes Report | 5 days | 2027-08-18 | 2027-08-22 | 8-Week Hypercare Support Period | Amatra PM | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Project Kickoff Complete | 2026-05-04 | Phase 1 — Discovery & Architecture | All stakeholders aligned; project charter and RACI accepted by CIO and CMO | Amatra PM | Not Started
MS-002 | Discovery and Assessment Complete | 2026-06-03 | Phase 1 — Discovery & Architecture | Assessment Report approved by CMO and CIO; Architecture go/no-go confirmed | Amatra Architect | Not Started
MS-003 | Architecture Approved | 2026-06-05 | Phase 1 — Discovery & Architecture | HLD, LLD, Security Architecture, and FHIR mapping documents signed off by CIO and CISO | Amatra Architect | Not Started
MS-004 | Infrastructure Ready | 2026-06-19 | Phase 2 — Environment Build & Data Pipeline | All 4 environments provisioned via IaC; connectivity to Mirth Connect validated | Amatra Engineer | Not Started
MS-005 | Data Pipeline Live | 2026-07-31 | Phase 2 — Environment Build & Data Pipeline | Real-time FHIR and HL7 ingestion flowing end-to-end to HealthLake and Feature Store; synthetic PHI validated | Amatra Engineer | Not Started
MS-006 | Phase 1 Go-Live — Sepsis Model | 2026-10-31 | Phase 5 — Production Rollout & Hypercare | Sepsis model live in production at pilot facility; AUROC ≥ 0.85 confirmed; CMO/CIO sign-off obtained | Amatra Engineer | Not Started
MS-007 | Phase 2 Deployment — Readmission and Rapid-Response | 2027-02-28 | Phase 5 — Production Rollout & Hypercare | Readmission and rapid-response models in production; clinical dashboard live with RBAC; Bedrock narratives enabled | Amatra Engineer | Not Started
MS-008 | Test Sign-Off | 2026-10-21 | Phase 4 — Testing & Validation | Test Results Report approved; CISO and CMO/CIO go-live clearance granted; all Critical/High defects resolved | Amatra QA | Not Started
MS-009 | Enterprise General Availability | 2027-06-30 | Phase 5 — Production Rollout & Hypercare | Full 18-hospital rollout complete; all facilities clinically active; per-facility UAT sign-offs obtained | Amatra PM | Not Started
MS-010 | Hypercare Period End and Project Closure | 2027-08-25 | Phase 5 — Production Rollout & Hypercare | 8-week hypercare concluded; outcomes report delivered to CMO and CIO; BAU transition confirmed | Amatra PM | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Amatra PM | Amatra Architect | Amatra Engineer | Amatra QA | Client CIO | Client CMO | Client CISO
Project Governance and Status Reporting | A | C | I | I | R | C | I
Clinical Requirements and Feature Definition | C | R | C | I | I | A | I
AWS Architecture Design | C | A | R | I | C | I | C
Security and HIPAA Compliance Design | C | R | C | I | C | I | A
Infrastructure Provisioning — IaC All 4 Environments | I | C | A | I | R | I | C
Epic FHIR R4 Connector Development | I | C | A | C | R | I | I
HL7 v2.3 Mirth Connect Adapter Development | I | C | A | C | R | I | I
Kinesis Data Pipeline Build and Validation | I | C | A | C | I | I | C
Amazon HealthLake FHIR Store Configuration | I | C | A | I | R | I | C
Azure AD and Cognito SSO Integration | I | C | A | C | I | I | R
PHI Audit Logging and KMS Encryption Implementation | I | C | R | C | C | I | A
CI/CD and DevOps Pipeline Build | I | C | A | C | R | I | I
Sepsis Risk Model Development and Training | I | A | R | C | I | C | I
Sepsis Model Clinical Accuracy Validation | C | C | R | C | I | A | I
SHAP Explainability Pipeline Development | I | A | R | C | I | C | I
Amazon Bedrock Clinical Narrative Integration | I | A | R | C | I | C | I
Readmission Prediction Model Development | I | A | R | C | I | C | I
Rapid-Response Deterioration Model Development | I | A | R | C | I | C | I
Clinical Staff Dashboard Development | I | C | A | C | R | C | I
Alert Routing and Notification System Build | I | C | A | C | R | I | I
Test Plan Development and Approval | C | C | R | A | C | I | C
Functional and Integration Testing Execution | C | C | R | A | C | I | C
Performance and Load Testing | C | C | R | A | I | I | C
HIPAA Security Controls Validation | C | C | R | C | C | I | A
External Penetration Testing Coordination | C | C | R | C | I | I | A
SOC 2 Type II Evidence Collection | I | C | R | C | I | I | A
User Acceptance Testing — Pilot Facility | C | I | C | R | C | A | I
Go-Live Readiness Sign-Off | A | C | C | C | R | R | R
Phase 1 Production Go-Live Execution | A | C | R | C | R | C | I
Phased Facility Rollout — All 18 Hospitals | A | C | R | C | R | C | I
Per-Facility UAT Sign-Off | C | I | C | R | C | A | I
Clinical Train-the-Trainer Enablement Delivery | R | A | R | I | C | C | I
Architecture and Operations Knowledge Transfer | R | A | R | I | C | I | I
Operational Runbooks Delivery | A | R | R | C | I | I | I
Final As-Built Documentation and IaC Handover | A | R | R | C | I | I | I
Hypercare Incident Response and Resolution | A | C | R | I | R | C | I
Project Closure and Outcomes Report | A | C | I | I | R | R | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | Responsible - Does the work
A | Accountable - Ultimate ownership
C | Consulted - Provides input
I | Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff Meeting | Once | All stakeholders — Amatra delivery team and MedCore CIO/CMO/CISO/Clinical Informatics Lead/EHR Integration Lead | Align on scope, RACI, governance model, and project charter; confirm access dependencies and BAA timeline | Amatra PM | 2026-05-04 — Full Day
Weekly Status Call | Weekly | Amatra PM; MedCore CIO; Clinical Informatics Lead; EHR Integration Lead | Review progress against plan; surface blockers; confirm decisions and action owners | Amatra PM | Mondays 10:00 AM ET
Clinical Discovery Workshop | Once per discovery session (Weeks 1–4) | Amatra Architect; MedCore CMO; Clinical Informatics Lead; Nursing staff and hospitalists | Capture clinical workflow requirements, risk threshold targets, and alert design preferences | Amatra Architect | Tuesdays 1:00 PM ET
Architecture and Security Review | Once (Week 7) | Amatra Architect; MedCore CIO; CISO; EHR Integration Lead | Review and approve HLD, LLD, Security Architecture, and FHIR mapping documents | Amatra Architect | 2026-06-01 (3 hours)
Phase Gate Review | End of each phase | Amatra PM; MedCore CIO; CMO; CISO | Review phase completion criteria and formally approve next phase commencement | Amatra PM | 2026-06-05, 2026-10-21, 2027-02-28, 2027-06-30
Bi-Weekly Technical Stand-Up | Bi-weekly | Amatra Engineers and Architects; MedCore IT/Cloud Engineering and EHR Integration Lead | Deep-dive on technical progress; resolve integration blockers; review environment access status | Amatra Architect | Wednesdays 2:00 PM ET
Model Performance Review | Monthly during Phase 3 | Amatra ML Engineers; MedCore Clinical Informatics Lead; CMO representative | Review model training progress; validate feature definitions; confirm accuracy benchmarks against AUROC targets | Amatra Engineer | First Friday of each month 10:00 AM ET
UAT Kick-Off and Facilitation | Once per facility cohort (Week 24 for pilot) | Amatra PM; MedCore Clinical Informatics Lead; Nursing and physician UAT participants; Amatra QA | Facilitate structured clinical workflow walk-throughs; capture UAT scoring rubric results and sign-off | Amatra PM | 2026-10-08 (Pilot Facility — Full Day)
Go-Live Readiness Briefing | Once before each go-live | Amatra PM and Tech Lead; MedCore CIO; CMO; CISO | Present UAT results and go-live readiness checklist for formal CMO and CIO approval | Amatra PM | 2026-10-20 (Phase 1), 2027-02-25 (Phase 2), 2027-06-27 (GA)
Critical Incident Escalation | As required during hypercare | Amatra Senior Support Engineer; Amatra Lead Architect; MedCore CIO; CISO | Notify and coordinate resolution of Priority 1 incidents during 8-week post-GA hypercare period | Amatra Engineer | Within 1 hour of incident detection
Knowledge Transfer Sessions | 4 half-day sessions (Weeks 40–44) | Amatra Architect and Engineers; MedCore IT team; Data Engineering team | Deliver technical track KT: IaC walkthrough, SageMaker operations, Kinesis/MSK troubleshooting, incident response | Amatra Architect | Tuesdays and Thursdays — Weeks 40–44
Project Closeout Meeting | Once (August 2027) | All stakeholders — Amatra delivery team; MedCore CIO; CMO; CISO; Clinical Informatics Lead | Formal project closure; present KPI baseline vs. actual outcomes report; confirm BAU transition and handover | Amatra PM | 2027-08-22 (2 hours)