## Cover
Level of Effort
Generated: | June 05, 2026
Solution: | Tmpoorv_975
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Consultants | Single team of 5-10 consultants | ~120 consultants (US & CA) | Up to 10 users | 10-50 users | 50+ users | PREDICTif has 120 distributed consultants needing concurrent access
Regions / Geographies | Single AWS region | us-west-2 (primary; isolated from us-east-1 workloads) | 1 region | 2 regions | 3+ regions | Fresh footprint in us-west-2 to isolate PoC blast radius
AI Agents / Pipelines | Single agent workflow | 5 agents per solution (Input Validator + 4 generators) | 1-2 agents | 3-4 agents | 5+ agents | Input Validator; Pre-Sales; Delivery; Code; EO Validator agents
Artifacts per Solution | 3 artifacts | 12 artifacts (5 presales + 6 delivery + 1 automation bundle) | Up to 5 | 6-9 | 10-12 | Full bundle: DOCX + PPTX + XLSX + Terraform IaC per solution
Integration Points | 1 integration | 5 integrations (Bedrock; Cognito; DynamoDB; S3; GitHub) | 1-2 | 3-4 | 5+ | API Gateway HTTP v2; Lambda; Cognito; DynamoDB; GitHub PAT; S3
Environments | Dev only | 3 environments (dev / staging / prod) | 1 (dev) | 2 (dev + staging) | 3 (dev + staging + prod) | Prod requires CTO sign-off and Cognito User Pool review
Compliance / Governance | No quota enforcement | Per-user monthly quotas + global pool (1000 sol/mo) | None | Per-user only | Per-user (10/mo) + global (1000/mo), atomic DynamoDB enforcement
Monthly Solution Throughput | Ad hoc (manual) | 200 solutions/month steady-state target | <10/mo | 10-100/mo | 100-1000+/mo | Platform must scale linearly; per-solution target <$5 Bedrock spend
SLA / Availability Target | Best effort | End-to-end in under 1 hour; PoC live by end of April 2026 | Best effort | 99% uptime | 99.9% uptime | Hard deadline: Q2 2026 executive sponsor demo

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1 | Baseline stakeholder interviews; requirements gathering; current-state review of legacy CLI workflow
Planning | planning_factor | 1.2 | Elevated for multi-agent graph design; AWS AgentCore + Strands framework; Cognito + API Gateway architecture planning
Development | development_factor | 1.3 | Elevated for 5-agent pipeline; 14-subcommand CLI; 11 Lambda routes; eof-tools container integration; Terraform IaC
Testing | testing_factor | 1.1 | Covers format-check + LLM quality-check validation loops; Terraform validate gate; 12 artifact type coverage
Deployment | deployment_factor | 1 | Baseline for production deployment; GitHub integration; hypercare; knowledge transfer
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Project kickoff meeting with Sarah Lin (CRO) and Marcus Patel (Dir Pre-Sales); agenda and minutes | Project Manager | 8 | 1 | 8 | 175 |  | None | Include CTO briefing on Cognito User Pool scope
Discovery | Current State Assessment | Document legacy CLI workflow: Claude Code CLI; OneDrive storage; manual GitHub push; 6-10 hr/engagement baseline | Solution Architect | 16 | 1 | 16 | 225 |  | Kickoff | Baseline for 90% effort-reduction KPI
Discovery | Requirements Gathering | Stakeholder interviews: Marcus Patel (technical); Daniel Park (delivery ops); CTO (Cognito sign-off); budget owner | Solution Architect | 24 | 1 | 24 | 225 |  | Current State Assessment | Capture all 14 CLI subcommands and 11 API routes
Discovery | Architecture Feasibility | Assess Bedrock AgentCore Runtime; Strands Agents framework; Claude Sonnet 4.6 + Haiku 4.5 model selection | Solution Architect | 24 | 1 | 24 | 225 |  | Requirements Gathering | Validate AgentCore Runtime GA availability in us-west-2
Discovery | Gap Analysis | Identify gaps: no central orchestration; no audit trail; no quota enforcement; no automated retry in legacy system | Solutions Engineer | 16 | 1 | 16 | 200 |  | Current State Assessment | Map gaps to Phase 1-3 delivery milestones
Discovery | Cloud Readiness Assessment | Review existing us-east-1 AWS account; plan fresh us-west-2 footprint; IAM boundary design; blast-radius analysis | Cloud Engineer | 16 | 1 | 16 | 200 |  | Architecture Feasibility | Confirm procurement trigger if new spend exceeds existing envelope
Discovery | Risk Assessment | Identify top risks: hard April deadline; Cognito CTO sign-off; Bedrock quota limits; GitHub PAT rotation; eof-tools compatibility | Project Manager | 8 | 1 | 8 | 175 |  | Gap Analysis | Risk register feeds Phase 3 contingency buffer
Discovery | Assessment Report | Document findings; recommended architecture; phased delivery plan aligned to 12-week schedule | Technical Writer | 16 | 1 | 16 | 125 |  | Risk Assessment | Distribute to Sarah Lin; Marcus Patel; Daniel Park
Planning | Detailed Architecture Design | Multi-agent graph design: Agent 0 (Input Validator); Pre-Sales Generator; Delivery Generator; Code Generator; EO Validator | Solution Architect | 40 | 1.2 | 48 | 225 |  | Assessment Report | Strands agent-graph topology; inter-agent message contracts
Planning | AWS Landing Zone Setup | us-west-2 account structure: VPC; IAM roles; S3 bucket policies; CloudTrail; Cost Allocation Tags; resource boundaries | Cloud Engineer | 32 | 1.2 | 38 | 200 |  | Detailed Architecture Design | Isolated from us-east-1 managed-services workloads
Planning | Cognito User Pool Design | Amazon Cognito User Pool: 30-day refresh tokens; post-confirmation trigger Lambda; DynamoDB user profile eager-write | Security Engineer | 24 | 1.2 | 29 | 200 |  | AWS Landing Zone Setup | CTO sign-off gate before implementation
Planning | API Gateway & Lambda Design | HTTP API v2: 11 routes; JWT authoriser; Lambda proxy integrations; per-route throttling; per-user quota enforcement | Solutions Engineer | 32 | 1.2 | 38 | 200 |  | Cognito User Pool Design | Includes admin usage endpoint and CLI auth flow
Planning | DynamoDB Schema Design | Tables: user profiles; solution state; per-user quota counters; global pool counter; atomic conditional writes | Solutions Engineer | 16 | 1.2 | 19 | 200 |  | API Gateway & Lambda Design | Atomic quota enforcement design (10 sol/user/mo; 1000 global/mo)
Planning | Container Image Architecture | eof-tools (~30 Python modules) baked into AgentCore container image; Docker layer strategy; ECR repository design | DevOps Engineer | 24 | 1.2 | 29 | 200 |  | DynamoDB Schema Design | Validate eof-tools converter library compatibility with container runtime
Planning | Security Baseline Design | IAM least-privilege policies; Secrets Manager for GitHub PAT; KMS key policy; CloudWatch log encryption; VPC endpoints | Security Engineer | 16 | 1.2 | 19 | 200 |  | Container Image Architecture | Aligns with CTO security review requirements
Planning | Monitoring & Observability Design | CloudWatch dashboards: per-phase token usage; per-solution latency; validation retry rates; quota utilisation metrics | DevOps Engineer | 16 | 1.2 | 19 | 200 |  | Security Baseline Design | Token usage must surface in CLI status command and admin API
Planning | Design Documentation | Architecture diagrams; ADRs; data-flow diagrams; API contract specs (OpenAPI); agent-graph topology document | Technical Writer | 24 | 1.2 | 29 | 125 |  | Monitoring & Observability Design | Inputs to Statement of Work and delivery artifacts
Development | Phase 1 Foundation | Provision Cognito User Pool; API Gateway HTTP v2; DynamoDB tables; S3 buckets; baseline IAM roles (Weeks 1-4) | Cloud Engineer | 40 | 1.3 | 52 | 200 |  | Design Documentation | Hard gate: Phase 1 complete before Phase 2 kickoff (Week 5)
Development | Cognito Post-Confirmation Lambda | Implement post-confirmation trigger Lambda: eager DynamoDB user-profile write; error handling; unit tests | Solutions Engineer | 16 | 1.3 | 21 | 200 |  | Phase 1 Foundation | 30-day refresh token config validated
Development | CLI Development Authentication | pip-installable CLI: login / logout / token-refresh subcommands; JWT storage; credential helper; 14 total subcommands | Solutions Engineer | 40 | 1.3 | 52 | 200 |  | Cognito Post-Confirmation Lambda | CLI must support all 14 documented subcommands
Development | Agent Framework Implementation | Strands Agents multi-agent graph: register all 5 agents in AgentCore Runtime; inter-agent messaging; solution state machine (Weeks 5-9) | Solutions Engineer | 64 | 1.3 | 83 | 200 |  | CLI Development Authentication | Core of the agentic orchestration platform
Development | Bedrock Model Integration | Claude Sonnet 4.6 (primary generation); Claude Haiku 4.5 (validation); prompt templates; retry logic (up to 3 retries per artifact) | ML/AI Engineer | 48 | 1.3 | 62 | 225 |  | Agent Framework Implementation | Per-artifact: format-check pass + LLM quality-check with retry
Development | eof-tools Container Integration | Bake eof-tools library into AgentCore container image; validate all 12 artifact-type converters (DOCX; PPTX; XLSX; Terraform) | DevOps Engineer | 40 | 1.3 | 52 | 200 |  | Bedrock Model Integration | Terraform validate as syntax gate for IaC bundle
Development | Lambda API Routes Implementation | Implement all 11 Lambda routes: solution CRUD; artifact download; user quota check; admin usage; status endpoints | Solutions Engineer | 48 | 1.3 | 62 | 200 |  | eof-tools Container Integration | JWT-protected; per-route throttle policies applied
Development | Quota Enforcement Implementation | Atomic DynamoDB conditional writes: per-user 10 sol/mo; global 1000 sol/mo pool; quota-exceeded error responses | Solutions Engineer | 24 | 1.3 | 31 | 200 |  | Lambda API Routes Implementation | Atomic enforcement prevents race conditions at scale
Development | GitHub Integration | Commit output artifacts to public GitHub repository via stored PAT; branch strategy; commit message format; error handling | Solutions Engineer | 16 | 1.3 | 21 | 200 |  | Quota Enforcement Implementation | PAT stored in Secrets Manager; rotation procedure documented
Development | CI/CD Pipeline | CodePipeline + CodeBuild: Docker image build; ECR push; AgentCore Runtime re-registration; automated smoke test on deploy | DevOps Engineer | 40 | 1.3 | 52 | 200 |  | GitHub Integration | Enables consistent deployments across dev / staging / prod
Development | Terraform IaC Full Platform | Terraform modules: Cognito; API GW; Lambda; DynamoDB; S3; ECR; AgentCore; IAM; CloudWatch; terraform validate gate | DevOps Engineer | 48 | 1.3 | 62 | 200 |  | CI/CD Pipeline | Automation bundle artifact; terraform validate must pass in CI
Development | Token Usage Instrumentation | Instrument all 5 agents: emit per-phase token counts to CloudWatch; surface in CLI status command and GET /admin/usage | ML/AI Engineer | 16 | 1.3 | 21 | 225 |  | Terraform IaC Full Platform | Required for budget tracking against $5/solution Bedrock target
Development | Security Hardening | Secrets Manager rotation; VPC endpoint for Bedrock/DynamoDB/S3; CloudTrail data events; GuardDuty enablement | Security Engineer | 24 | 1.3 | 31 | 200 |  | Token Usage Instrumentation | Reduces attack surface; aligns with CTO security expectations
Development | Configuration and Code Documentation | Inline code documentation; README files; deployment guide; environment variable reference; eof-tools integration notes | Technical Writer | 32 | 1.3 | 42 | 125 |  | Security Hardening | Feeds delivery-phase runbooks
Testing | Test Plan Development | Comprehensive test plan: unit; integration; E2E; load; security; 12 artifact-type validation coverage matrix | QA Engineer | 16 | 1.1 | 18 | 150 |  | Configuration and Code Documentation | Phase 3 Weeks 10-12 gate
Testing | Unit Testing Agents and Lambda | Unit tests for all 5 agents; 11 Lambda routes; Cognito trigger; quota logic; GitHub integration module | Solutions Engineer | 32 | 1.1 | 35 | 200 |  | Test Plan Development | Target >80% code coverage
Testing | Integration Testing Full Pipeline | End-to-end solution generation: Input Validator through EO Validator; all 12 artifact types validated | Solutions Engineer | 32 | 1.1 | 35 | 200 |  | Unit Testing Agents and Lambda | Validate all 5 presales + 6 delivery + 1 Terraform bundle artifacts
Testing | Validation Loop Testing | Test format-check + LLM quality-check retry mechanism (up to 3 retries); confirm deterministic pass/fail on all artifact types | QA Engineer | 24 | 1.1 | 26 | 150 |  | Integration Testing Full Pipeline | EO Validator agent must surface actionable error messages
Testing | Performance and Load Testing | Load test: 200 solutions/month throughput; concurrent solution generation; DynamoDB quota atomic writes under load | Solutions Engineer | 24 | 1.1 | 26 | 200 |  | Validation Loop Testing | Verify <1hr end-to-end SLA at target throughput
Testing | Security Testing | IAM policy review; Cognito token validation; JWT authoriser bypass testing; Secrets Manager access; VPC endpoint validation | Security Engineer | 16 | 1.1 | 18 | 200 |  | Performance and Load Testing | Include OWASP API Top 10 checks on 11 Lambda routes
Testing | Terraform Validate Gate Testing | Verify terraform validate passes in CI for all IaC modules; test plan/apply in staging environment | DevOps Engineer | 16 | 1.1 | 18 | 200 |  | Security Testing | IaC automation bundle must pass gate before delivery
Testing | UAT Coordination | Coordinate UAT with Marcus Patel (pre-sales scenarios); Daniel Park (delivery scenarios); CTO (Cognito / production gate) | Project Manager | 16 | 1.1 | 18 | 175 |  | Terraform Validate Gate Testing | UAT sign-off required before go-live
Testing | CloudWatch Green Baseline | Validate green CloudWatch metrics baseline: error rates; latency P99; retry rates; token spend per solution | DevOps Engineer | 16 | 1.1 | 18 | 200 |  | UAT Coordination | Required deliverable: Phase 3 completion criterion
Testing | Defect Resolution | Address and resolve all P1/P2 defects identified during integration; UAT; performance; and security testing | Solutions Engineer | 40 | 1.1 | 44 | 200 |  | CloudWatch Green Baseline | 10-20% contingency buffer applied to defect-resolution hours
Testing | Test Results Report | Document test results; coverage metrics; UAT sign-off; security attestation; CloudWatch baseline screenshot | QA Engineer | 8 | 1.1 | 9 | 150 |  | Defect Resolution | Distribute to Sarah Lin; Marcus Patel; Daniel Park; CTO
Deployment | Go-Live Planning | Cutover plan: production deployment checklist; rollback procedures; Cognito CTO sign-off gate; procurement notification | Project Manager | 8 | 1 | 8 | 175 |  | Test Results Report | Hard gate: CTO sign-off before production Cognito User Pool activation
Deployment | Production Deployment | Deploy full platform to production us-west-2: AgentCore Runtime; Lambda; DynamoDB; Cognito; S3; API GW; monitoring | Cloud Engineer | 24 | 1 | 24 | 200 |  | Go-Live Planning | Follows 12-week schedule; demo-ready by end of April 2026
Deployment | GitHub Repository Setup | Configure public GitHub repository; branch protection; initial artifact commits; PAT integration validation in production | Solutions Engineer | 8 | 1 | 8 | 200 |  | Production Deployment | PAT stored in Secrets Manager; rotation schedule established
Deployment | Runbook Development | Operational runbooks: agent failure recovery; quota reset; PAT rotation; DynamoDB backup; CloudWatch alarm response | Technical Writer | 24 | 1 | 24 | 125 |  | Production Deployment | Handed to Daniel Park (Head of Delivery Operations)
Deployment | Knowledge Transfer Engineering | Technical deep-dive sessions for Amatra engineering team: agent architecture; Lambda routes; CI/CD; Terraform modules | Solution Architect | 16 | 1 | 16 | 225 |  | Runbook Development | Recorded sessions for future onboarding
Deployment | Knowledge Transfer Pre-Sales | Pre-sales workflow training for Marcus Patel's team: CLI usage; solution generation; artifact review; quota management | Trainer | 16 | 1 | 16 | 150 |  | Knowledge Transfer Engineering | Target audience: 120 distributed consultants (train-the-trainer approach)
Deployment | Documentation Delivery | Deliver complete as-built documentation: architecture docs; API reference; runbooks; ADRs; deployment guide; eof-tools guide | Technical Writer | 16 | 1 | 16 | 125 |  | Knowledge Transfer Pre-Sales | Stored in S3 and GitHub repository
Deployment | Hypercare Support | 8-week post-go-live hypercare: Bedrock quota monitoring; agent failure triage; validation retry tuning; quota adjustment | Support Engineer | 80 | 1 | 80 | 150 |  | Documentation Delivery | Large-complexity engagement; 8 weeks covers ~200 solutions/mo ramp
Deployment | Optimisation Recommendations | Document Phase 2 opportunities: multi-region expansion; advanced analytics; Haiku 4.5 cost optimisation; auto-scaling | Solution Architect | 16 | 1 | 16 | 225 |  | Hypercare Support | Feeds Phase 2 engagement scoping and budget planning
Deployment | Project Closeout | Project retrospective; lessons learned; KPI measurement (90% effort reduction; <1hr generation time); executive summary | Project Manager | 8 | 1 | 8 | 175 |  | Optimisation Recommendations | Executive summary distributed to Sarah Lin (CRO)
Management | Technical Leadership | EO Quarterback: technical oversight across all phases; architecture governance; agent-graph quality reviews; escalation handling | Solution Architect |  | 1 |  | 225 |  |  | 10% of engineering hours
Management | Project Management | Project coordination: weekly status reports; RAID log; milestone tracking; stakeholder comms to Sarah Lin and Marcus Patel | Project Manager |  | 1 |  | 175 |  |  | 10% of engineering hours
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Network (APN) Services Credit | -15000 | APN Advanced Tier Partner credit applied to professional services engagement; eligible for AWS AI/ML solution builds using Bedrock and AgentCore Runtime
AWS Bedrock Launch Partner Incentive | -5000 | Early adopter incentive for AgentCore Runtime (Bedrock AgentCore); applicable to new platform builds leveraging Bedrock generative AI services in Year 1
Implementation Volume Discount | -10000 | Volume discount on professional services for engagement exceeding $200k; applied as 4% reduction on total services cost for strategic PREDICTif / Amatra deal
TOTAL |  | Total professional services cost minus APN credit ($15k) + Bedrock incentive ($5k) + volume discount ($10k) = $30,000 total credits applied in Year 1