## Cover
Level of Effort
Generated: | June 09, 2026
Solution: | Tmppnqxy2Bn
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Accounts | Single business unit (~100 users) | ~4500 employees across platform team and workload owners | Up to 100 | 100–500 | 500+ | Scope includes platform team plus onboarded workload account owners
Regions / Geographies | Single AWS region | Two regions: ap-southeast-2 (primary) + ap-southeast-4 (DR) | 1 region | 2 regions | 3+ regions | All data must remain in-country (Australia); DR replica required
Cloud Environments | Dev + Prod (2 environments) | Three production environments + dev/test/staging per workload | 2–3 | 4–6 | 7+ | Existing three prod environments plus new structured account hierarchy
Identity Integration | New identity deployment | Federation with existing on-premises enterprise directory | New IdP | Federate 1 IdP | Federate 2+ IdPs | On-prem IdP federated via AWS IAM Identity Center; no replacement
Compliance Frameworks | Single framework | ISO 27001 + internal security baseline + financial services regulations | 1 framework | 2 frameworks | 3+ frameworks | Regulatory review hard deadline Q2 2026 (end of April)
ITSM / Integration Points | No ITSM integration | Existing SIEM + ticketing platform integrations required | 0–1 | 2–3 | 4+ | Change approval workflow must route through existing ITSM; SIEM alert forwarding
Infrastructure-as-Code Coverage | Greenfield IaC | All new accounts and guardrails via IaC; legacy workloads excluded | Partial IaC | Full IaC new | Full IaC + legacy remediation | Two legacy on-prem workloads explicitly out of scope
Policy-as-Code Guardrails | Basic SCPs | Comprehensive preventive + detective guardrails (no manual console access in prod) | Basic SCPs only | SCPs + Config rules | SCPs + Config + custom Lambda guardrails | Production console access must be fully blocked with break-glass procedure
SLA / Availability Target | Standard business hours support | 99.9% platform availability; DR RTO < 4h / RPO < 1h | Best effort | 99.5% SLA | 99.9%+ with DR | DR replica must be tested and validated before regulatory review

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1.2 | Elevated for regulated environment; includes compliance assessment and CISO alignment sessions
Planning | planning_factor | 1.3 | Increased for multi-region architecture and policy-as-code design complexity
Development | development_factor | 1.5 | Large complexity multiplier; covers IaC automation + two-region deployment + ITSM and SIEM integrations
Testing | testing_factor | 1.2 | Compliance validation and DR failover testing add overhead beyond standard functional testing
Deployment | deployment_factor | 1.2 | Staged rollout across three prod environments with change-approval gate at each phase
Management | management_factor | 1 | Standard overhead applied to PM and technical leadership rows (10% of engineering hours)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Project kickoff meeting with CTO (James Wu) and Head of Platform Engineering (Priya Nair); align on objectives and timeline | Project Manager | 8 | 1.2 | 9.6 | 175 |  |  | Round to 10h in practice
Discovery | Stakeholder Interviews | Conduct structured interviews with platform team and CISO; document requirements and security baseline expectations | Solution Architect | 24 | 1.2 | 28.8 | 225 |  |  | CISO sign-off required before prod changes
Discovery | Current State Assessment | Assess existing AWS footprint; document account structure; inventory manual provisioning procedures and shared credentials | Solutions Engineer | 32 | 1.2 | 38.4 | 200 |  |  | Access to existing AWS console and IAM reports needed
Discovery | Cloud Readiness Assessment | Evaluate AWS Control Tower / Organizations readiness; assess existing SCPs and IAM policies; identify gaps | Solution Architect | 24 | 1.2 | 28.8 | 225 |  |  | Output feeds architecture design phase
Discovery | Compliance & Regulatory Assessment | Map ISO 27001 controls and internal security baseline to AWS service capabilities; document evidence requirements for Q2 2026 review | Security Engineer | 32 | 1.2 | 38.4 | 200 |  |  | Engage compliance team; document control mapping matrix
Discovery | Identity & Directory Assessment | Document on-premises IdP configuration; design federation architecture using AWS IAM Identity Center; define attribute mapping | Security Engineer | 16 | 1.2 | 19.2 | 200 |  |  | On-prem IdP documentation required from Contoso
Discovery | ITSM & SIEM Integration Assessment | Review existing ticketing platform and SIEM; define integration patterns for change approval workflow and security alert forwarding | Solutions Engineer | 16 | 1.2 | 19.2 | 200 |  |  | Integration scope confirmed with IT Delivery Manager
Discovery | Gap Analysis & Risk Assessment | Identify gaps between current and target state; document risks and mitigations; present findings to James Wu and Priya Nair | Solution Architect | 16 | 1.2 | 19.2 | 225 |  |  | Feeds planning and architecture phases
Discovery | Discovery Report | Document all findings; produce current-state assessment report with prioritised recommendations | Technical Writer | 16 | 1.2 | 19.2 | 125 |  |  | Deliverable: Discovery & Assessment Report
Planning | Detailed Architecture Design | Design AWS Control Tower landing zone with OU structure, account vending, and guardrail framework for ap-southeast-2 and ap-southeast-4 | Solution Architect | 40 | 1.3 | 52 | 225 |  |  | Based on discovery findings
Planning | IaC Framework Design | Design Terraform / CloudFormation module structure for account provisioning; define pipeline and state management approach | Solutions Engineer | 32 | 1.3 | 41.6 | 200 |  |  | IaC toolchain selection confirmed with platform team
Planning | Policy-as-Code Design | Design preventive SCPs and detective AWS Config rules; define break-glass procedure for emergency console access; document no-console-access enforcement | Security Engineer | 32 | 1.3 | 41.6 | 200 |  |  | Feeds Development phase for guardrail implementation
Planning | DR Architecture Design | Design multi-region DR replication and failover architecture for ap-southeast-2 to ap-southeast-4; define RTO/RPO targets | Solution Architect | 24 | 1.3 | 31.2 | 225 |  |  | Coordinate with Contoso infrastructure team
Planning | Network & Connectivity Design | Design Transit Gateway, VPC topology, and connectivity between regions and on-premises data centres | Cloud Engineer | 24 | 1.3 | 31.2 | 200 |  |  | Two data centres and two AWS regions in scope
Planning | Security Architecture Design | Design centralised security monitoring: Security Hub, GuardDuty, Config aggregation, and CloudTrail for audit evidence | Security Engineer | 24 | 1.3 | 31.2 | 200 |  |  | Must produce audit-ready evidence before April 2026
Planning | Identity Federation Design | Detail IAM Identity Center permission set design, attribute-based access control, and SSO application assignments | Security Engineer | 16 | 1.3 | 20.8 | 200 |  |  | On-prem IdP federation architecture confirmed in Discovery
Planning | Architecture Documentation | Produce as-designed architecture diagrams; document design decisions and rationale for CISO review | Technical Writer | 24 | 1.3 | 31.2 | 125 |  |  | Deliverable: Architecture Design Document
Development | AWS Control Tower Deployment | Deploy AWS Control Tower in ap-southeast-2; configure management account, log archive, and audit accounts; establish OU hierarchy | Cloud Engineer | 40 | 1.5 | 60 | 225 |  |  | AWS-certified architect rate applies; foundation for all workloads
Development | Account Vending Machine | Develop and deploy IaC-based account vending pipeline; integrate with ITSM for change-approval-gated provisioning | Solutions Engineer | 48 | 1.5 | 72 | 200 |  |  | ITSM integration required before go-live
Development | IaC Module Library | Build reusable Terraform modules for VPC networking; IAM roles; logging; tagging; and environment baseline configuration | Solutions Engineer | 64 | 1.5 | 96 | 200 |  |  | Modules must meet internal security baseline standards
Development | Preventive Guardrails (SCPs) | Implement Service Control Policies blocking console access in production; restrict disallowed services; enforce encryption at rest and in transit | Security Engineer | 40 | 1.5 | 60 | 225 |  |  | Security Engineer rate + $25 for CISSP specialisation; CISO review required
Development | Detective Guardrails (Config Rules) | Deploy AWS Config conformance packs for ISO 27001; create custom Config rules for internal security baseline; configure auto-remediation | Security Engineer | 40 | 1.5 | 60 | 200 |  |  | Auto-remediation rules must be tested before enabling in prod
Development | Centralised Security Monitoring | Configure AWS Security Hub with aggregated findings; enable GuardDuty across all accounts; configure CloudTrail with log integrity validation | Security Engineer | 32 | 1.5 | 48 | 200 |  |  | Produces audit evidence for Q2 2026 regulatory review
Development | SIEM Integration | Develop and deploy integration to forward Security Hub findings and CloudTrail events to existing SIEM platform | Solutions Engineer | 32 | 1.5 | 48 | 200 |  |  | SIEM API credentials and endpoint documentation required
Development | Identity Federation Implementation | Configure AWS IAM Identity Center; federate with on-premises IdP; deploy permission sets; configure SSO for workload accounts | Security Engineer | 32 | 1.5 | 48 | 200 |  |  | On-prem IdP team availability required for federation configuration
Development | ITSM Workflow Integration | Develop change-approval workflow integration between account vending pipeline and existing ITSM; configure approval routing and notifications | Solutions Engineer | 32 | 1.5 | 48 | 200 |  |  | ITSM API access and workflow documentation required
Development | DR Region Baseline | Deploy mirrored baseline in ap-southeast-4; configure cross-region replication for Config, CloudTrail, and Security Hub | Cloud Engineer | 32 | 1.5 | 48 | 200 |  |  | Follows primary region deployment; data sovereignty validated
Development | Network Infrastructure Deployment | Deploy Transit Gateway; configure VPC peering / attachments; establish Direct Connect or VPN connectivity to on-premises data centres | Cloud Engineer | 40 | 1.5 | 60 | 200 |  |  | Network design approved in Planning phase required
Development | Workload Onboarding (3 Prod Environments) | Onboard existing three production environments into new account structure; apply guardrails without service interruption | Solutions Engineer | 48 | 1.5 | 72 | 200 |  |  | Change window approvals required; CISO sign-off before prod changes
Development | CI/CD Pipeline for IaC | Implement GitOps pipeline for IaC deployment; integrate with change approval gate; configure automated policy compliance checks | DevOps Engineer | 40 | 1.5 | 60 | 200 |  |  | Pipeline must enforce no-manual-deployment policy
Development | Configuration Documentation | Document all configurations; produce runbook for account vending and guardrail management | Technical Writer | 32 | 1.5 | 48 | 125 |  |  | Deliverable: Configuration and Operations Guide
Testing | Test Plan Development | Create test plan covering account provisioning, guardrail enforcement, identity federation, SIEM integration, and DR failover | QA Engineer | 16 | 1.2 | 19.2 | 150 |  |  | Test plan requires sign-off from Priya Nair before execution
Testing | Functional Testing — Account Vending | Test automated account provisioning end-to-end; validate ITSM change approval workflow; confirm tagging and baseline configuration | QA Engineer | 24 | 1.2 | 28.8 | 150 |  |  | Account vending machine deployment complete
Testing | Functional Testing — Guardrails | Validate preventive SCPs block prohibited actions; confirm detective Config rules fire alerts and trigger auto-remediation correctly | Security Engineer | 24 | 1.2 | 28.8 | 200 |  |  | Test in non-production environment first; then validate in prod replica
Testing | Identity Federation Testing | Validate SSO login flows; test permission set assignments; confirm break-glass access procedure works and is audited | Security Engineer | 16 | 1.2 | 19.2 | 200 |  |  | On-prem IdP team participation required for end-to-end test
Testing | SIEM Integration Testing | Validate Security Hub findings and CloudTrail events are correctly ingested and correlated in existing SIEM | Solutions Engineer | 16 | 1.2 | 19.2 | 200 |  |  | SIEM team co-ordination required
Testing | Compliance Validation | Execute ISO 27001 control checklist; produce compliance evidence package for regulatory review; remediate any findings | Security Engineer | 32 | 1.2 | 38.4 | 225 |  |  | Rate includes CISSP specialist premium; must complete before April 2026
Testing | DR Failover Testing | Conduct DR failover drill for ap-southeast-4; validate RTO < 4h and RPO < 1h; document test results | Cloud Engineer | 24 | 1.2 | 28.8 | 200 |  |  | DR failover testing deliverable required for regulatory evidence pack
Testing | Performance & Resilience Testing | Load-test account vending pipeline; validate guardrail enforcement under concurrent provisioning; confirm no throttling | Solutions Engineer | 16 | 1.2 | 19.2 | 200
Testing | UAT Co-ordination | Co-ordinate UAT with platform team and CISO; facilitate sign-off on all controls before production cutover | Project Manager | 16 | 1.2 | 19.2 | 175 |  |  | CISO sign-off is gate for production deployment
Testing | Defect Resolution | Triage and resolve defects identified during functional and compliance testing; re-test resolved items | Solutions Engineer | 24 | 1.2 | 28.8 | 200 |  |  | Buffer allocated for expected defects
Testing | Test Results Report | Document all test results and sign-off evidence; package compliance artefacts for regulatory submission | Technical Writer | 16 | 1.2 | 19.2 | 125 |  |  | Deliverable: Test Results and Compliance Evidence Package
Deployment | Go-Live Planning | Document production cutover plan and rollback procedures for each of three production environments | Project Manager | 8 | 1.2 | 9.6 | 175 |  |  | Cutover plan reviewed and approved by Rachel Moore
Deployment | Production Cutover — Environment 1 | Deploy guardrails and account structure to first production environment; validate no service interruption | Solutions Engineer | 16 | 1.2 | 19.2 | 200 |  |  | Change window approved via ITSM
Deployment | Production Cutover — Environment 2 | Deploy guardrails and account structure to second production environment; validate no service interruption | Solutions Engineer | 16 | 1.2 | 19.2 | 200 |  |  | Change window approved via ITSM
Deployment | Production Cutover — Environment 3 | Deploy guardrails and account structure to third production environment; validate no service interruption | Solutions Engineer | 16 | 1.2 | 19.2 | 200 |  |  | Change window approved via ITSM
Deployment | Runbook Delivery | Finalise and deliver operational runbooks for account vending; guardrail management; break-glass procedure; and DR failover | Technical Writer | 24 | 1.2 | 28.8 | 125 |  |  | Deliverable: Operational Runbook Suite
Deployment | Knowledge Transfer Sessions | Conduct knowledge transfer sessions with platform team covering IaC pipeline, guardrail management, IAM Identity Center, and Security Hub operations | Trainer | 24 | 1.2 | 28.8 | 150 |  |  | Target audience: Priya Nair's platform team
Deployment | Administrator Training | Train platform engineers on day-to-day operations; account onboarding; escalation procedures; and evidence collection for audits | Trainer | 16 | 1.2 | 19.2 | 150
Deployment | Hypercare Support (8 weeks) | Post-go-live hypercare support for 8 weeks; on-call assistance for platform team; incident triage; guardrail tuning | Support Engineer | 80 | 1.2 | 96 | 150 |  |  | Large complexity = 8-week hypercare; covers regulatory review period
Deployment | Optimisation Recommendations | Document platform optimisation recommendations; cost optimisation opportunities; and roadmap for ongoing compliance automation | Solution Architect | 16 | 1.2 | 19.2 | 225 |  |  | Deliverable: Platform Optimisation Roadmap
Deployment | Project Closeout | Project retrospective; lessons learned; final status report to James Wu and Priya Nair | Project Manager | 8 | 1.2 | 9.6 | 175 |  |  | Deliverable: Project Closeout Report
Management | Technical Leadership | Quarterback technical oversight across all phases; escalation point for architecture and security decisions | Solution Architect |  | 1 |  | 225 |  |  | 10% of engineering hours; no circular reference
Management | Project Management | Project co-ordination; stakeholder reporting; risk and issue management; schedule tracking across 4-month engagement | Project Manager |  | 1 |  | 175 |  |  | 10% of engineering hours; Rachel Moore counterpart
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -10000 | AWS Partner Network (APN) Advanced Tier credit applied to solution architecture and implementation services for Contoso Financial engagement
AWS MAP (Migration Acceleration Program) | -15000 | AWS MAP professional services funding available for enterprise landing zone and workload onboarding engagements; eligibility confirmed with AWS account team
Volume Implementation Discount | -5000 | Volume discount on professional services for strategic financial services engagement; 2% discount on total PS fees applied in Year 1
TOTAL |  | Total professional services cost minus AWS Partner credits, MAP funding, and volume discount. Infrastructure costs are captured separately in infrastructure-costs.csv