## Cover
Test Plan
Generated: | June 10, 2026
Solution: | Tmpqz8Q6Wcz
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
FT-001 | Unit | Cognito JWT Authentication | Validate that API Gateway accepts a valid Cognito-issued JWT and returns an authenticated response | Cognito User Pool deployed; test user exists in PreSales group; API Gateway Cognito authoriser configured | 1. Obtain JWT access token from Cognito for test PreSales user 2. Send GET /api/v1/health with Authorization: Bearer <token> 3. Verify HTTP 200 response 4. Verify token claims match expected user attributes | HTTP 200 with authenticated response; token sub and cognito:groups claims correct | Critical | Integration | Security Engineer | Not Started | Not Executed | DDD §Security – Identity & Access Management; IG §Security – Deployment Steps | Test all three Cognito groups: AmAdmin/PreSales/Delivery
FT-002 | Unit | Cognito JWT Rejection | Validate that API Gateway rejects missing or invalid Cognito JWT tokens | API Gateway Cognito authoriser configured; WAF WebACL active | 1. Send POST /api/v1/solutions with no Authorization header 2. Send request with an expired token 3. Send request with a tampered token signature 4. Verify response codes for each scenario | HTTP 401 for all three unauthorised attempts; no Lambda function invoked | Critical | Integration | Security Engineer | Not Started | Not Executed | DDD §Security – Identity & Access Management; DDD §Integration Design – Authentication & SSO Flows | Verify CloudTrail logs each rejected attempt
FT-003 | Unit | Input Validation – Brief Payload | Validate that the isb-api-submit Lambda enforces request payload schema | API Gateway and isb-api-submit Lambda deployed; valid Cognito JWT available | 1. Send POST /api/v1/solutions with missing required fields 2. Send request with invalid data types in brief payload 3. Send request with brief payload exceeding 512 KB 4. Send request with all required fields valid | HTTP 400 with descriptive error body for cases 1-3; HTTP 202 with solution_id for case 4 | High | Integration | QA Engineer | Not Started | Not Executed | DDD §Integration Design – API Design; IG §Application Configuration – Environment Variable Reference | Max brief size is 512 KB per application config
FT-004 | Integration | Brief Submission to SQS Enqueue | Validate that a valid brief submission is written to SolutionState and enqueued on the SQS job queue | isb-api-submit Lambda deployed; DynamoDB AmatraISB-SolutionState table active; SQS amatra-isb-job-queue provisioned | 1. Submit valid brief via POST /api/v1/solutions with valid JWT 2. Verify HTTP 202 and solution_id in response 3. Query DynamoDB SolutionState for the returned solution_id 4. Verify SQS queue depth incremented by 1 after submission | HTTP 202 returned within 500 ms p99; DynamoDB record created with status PENDING; SQS message visible in queue | Critical | Integration | QA Engineer | Not Started | Not Executed | DDD §Data Architecture – Data Flow Design Step 1; DDD §Component Design | Monitor provisioned concurrency on isb-api-submit
FT-005 | Integration | Step Functions Execution Start | Validate that the isb-orchestrator-start Lambda consumes the SQS message and starts a Step Functions execution | SQS job queue populated with a test job message; Step Functions state machine active; isb-orchestrator-start Lambda deployed | 1. Place a synthetic job message on amatra-isb-job-queue-staging 2. Wait for Lambda SQS trigger (≤5 s) 3. Query Step Functions for active executions 4. Verify DynamoDB SolutionState record updated to IN_PROGRESS | Step Functions execution starts within 5 s of SQS message delivery; DynamoDB status updated to IN_PROGRESS | Critical | Integration | QA Engineer | Not Started | Not Executed | DDD §Data Architecture – Data Flow Design Step 2; DDD §Infrastructure – Compute Sizing | Verify execution input contains solution_id and artifact_type_list
FT-006 | Integration | DynamoDB Usage Limit Enforcement | Validate that isb-api-submit blocks submissions when the per-user monthly generation limit is reached | DynamoDB AmatraISB-UsageTracking table populated with a user at their monthly limit; valid JWT for that user | 1. Set user generation_count equal to per_user_monthly_default (10) 2. Submit a new brief via POST /api/v1/solutions 3. Verify HTTP 429 response 4. Verify DynamoDB UsageTracking record was NOT modified | HTTP 429 returned; DynamoDB record unchanged; no SQS message enqueued | High | Integration | QA Engineer | Not Started | Not Executed | DDD §Data Architecture – Logical Model UsageCounter; DDD §Integration Design – API Design GET /api/v1/usage/me | Test admin override path separately in FT-013
FT-007 | Integration | Bedrock Invocation – Claude Sonnet | Validate that isb-bedrock-sonnet Lambda successfully invokes Amazon Bedrock Claude 3 Sonnet and returns generated content | Bedrock Claude 3 Sonnet model enabled in us-west-2; isb-bedrock-sonnet Lambda deployed with correct IAM execution role; test prompt available in S3 templates bucket | 1. Invoke isb-bedrock-sonnet directly with a test prompt payload 2. Verify Lambda returns within 900 s timeout 3. Verify response body contains generated text content 4. Verify Bedrock token usage is captured in the response metadata | Generated artifact content returned; no ThrottlingException; token count recorded in Lambda response | Critical | Integration | ML/AI Engineer | Not Started | Not Executed | DDD §Component Design – AI Generation Engine; DDD §Technology Stack – AI/ML Generation | Use a representative SOW-type prompt; verify Sonnet model ID matches config
FT-008 | Integration | Bedrock Invocation – Claude Haiku | Validate that isb-bedrock-haiku Lambda successfully invokes Amazon Bedrock Claude 3 Haiku for lightweight artifact types | Bedrock Claude 3 Haiku model enabled in us-west-2; isb-bedrock-haiku Lambda deployed; test discovery-questionnaire prompt in S3 | 1. Invoke isb-bedrock-haiku with a discovery-questionnaire prompt payload 2. Verify Lambda returns within 600 s timeout 3. Verify generated content matches expected questionnaire structure 4. Compare cost (token count) to Sonnet equivalent | Generated questionnaire content returned; token count lower than Sonnet baseline for same prompt; no errors | High | Integration | ML/AI Engineer | Not Started | Not Executed | DDD §Component Design – AI Generation Engine; DDD §Technology Stack | Haiku used for discovery-questionnaire and infrastructure-costs types
FT-009 | Integration | Artifact Processor S3 Write | Validate that isb-artifact-processor writes the generated artifact to S3 under the correct key taxonomy and updates DynamoDB SolutionState | isb-artifact-processor Lambda deployed; S3 artifacts bucket provisioned with SSE-KMS; DynamoDB SolutionState table active | 1. Invoke isb-artifact-processor with synthetic Bedrock output and solution_id 2. Verify S3 object created at key {solution_id}/raw/pre-sales/{artifact_type}/{filename} 3. Verify DynamoDB SolutionState record updated with artifact S3 key 4. Verify S3 object metadata includes SSE-KMS encryption | S3 object present at correct key; DynamoDB s3_key attribute populated; S3 object server-side encrypted with CMK alias/amatra-isb-s3-artifacts-prod | Critical | Integration | QA Engineer | Not Started | Not Executed | DDD §Data Architecture – Data Flow Design Steps 5-6; DDD §Data Architecture – Data Governance | Test with all 7 artifact types to confirm correct key paths
FT-010 | Integration | Presigned URL Artifact Retrieval | Validate that GET /api/v1/solutions/{solution_id}/artifacts/{type} returns a valid 24-hour presigned S3 URL | DynamoDB SolutionState record exists with status COMPLETE and artifact s3_key populated; isb-api-retrieve Lambda deployed with valid IAM role | 1. Authenticate and call GET /api/v1/solutions/{solution_id}/artifacts/solution-briefing 2. Verify HTTP 200 with presigned_url in response body 3. Download the artifact via the presigned URL 4. Verify the presigned URL expires after 24 hours | HTTP 200 returned; presigned URL valid and downloadable; URL expires at expected TTL of 86400 s per application config | High | Integration | QA Engineer | Not Started | Not Executed | DDD §Integration Design – API Design GET artifacts/{type}; IG §Application Configuration – presigned_url_ttl_seconds | Verify unauthenticated access to URL succeeds; authenticated access to expired URL returns 403
FT-011 | System | End-to-End Pre-Sales Pipeline – All 4 Phase 1 Artifact Types | Validate the complete brief-to-artifact generation pipeline for all four Phase 1 artifact types in one submission | Full Phase 1 platform deployed in Staging; Cognito user with PreSales group available; representative synthetic client brief prepared | 1. Submit client brief via POST /api/v1/solutions specifying all 4 Phase 1 artifact types 2. Poll GET /api/v1/solutions/{solution_id}/status until COMPLETE or timeout at 60 min 3. Retrieve presigned URLs for each artifact type 4. Download and inspect each artifact for required sections 5. Verify QA scores in DynamoDB SolutionState | All 4 artifacts (discovery-questionnaire; solution-briefing; statement-of-work; infrastructure-costs) generated within 60 min; all required sections present; no placeholder text remaining | Critical | Staging | QA Lead | Not Started | Not Executed | DDD §Implementation Approach – Phase 1c Exit Criteria; SOW §Testing & Validation – Functional Validation | Primary Phase 1 UAT gateway test
FT-012 | System | End-to-End Delivery Pipeline – All 3 Phase 2 Artifact Types | Validate the complete brief-to-artifact generation pipeline for all three Phase 2 delivery artifact types | Full Phase 2 platform deployed in Staging; Cognito user with Delivery group; representative synthetic client brief prepared | 1. Submit client brief specifying detailed-design; implementation-guide; terraform artifact types 2. Poll status until COMPLETE or 60-min timeout 3. Retrieve and download all 3 artifacts 4. Verify Terraform HCL output is syntactically valid using terraform validate 5. Verify QA validation layer score ≥ 90% in DynamoDB | All 3 delivery artifacts generated within 60 min; terraform validate returns success; QA score ≥ 90%; all required document sections present | Critical | Staging | QA Lead | Not Started | Not Executed | DDD §Implementation Approach – Phase 2 Exit Criteria; DDD §Data Architecture – Data Governance | Run terraform validate in an isolated workspace
FT-013 | System | Admin Usage Limit Override | Validate that an AmAdmin user can override a per-user monthly generation limit and the affected user can then submit a new job | DynamoDB UsageTracking record for target user at monthly limit; Cognito user in AmAdmin group available | 1. Authenticate as AmAdmin and call PUT /api/v1/usage/users/{user_id}/limit with new limit value 2. Verify HTTP 200 and updated limit value in response 3. Authenticate as the target user and submit a new brief 4. Verify job enqueued and generation proceeds normally 5. Verify admin action recorded in CloudTrail | HTTP 200 on override; DynamoDB UsageTracking record reflects new limit; subsequent job submission succeeds; CloudTrail event for PUT /api/v1/usage logged | High | Staging | QA Engineer | Not Started | Not Executed | DDD §Integration Design – API Design PUT /api/v1/usage/users/{user_id}/limit; DDD §Security – Identity & Access Management – Role Definitions | Verify AmAdmin CloudTrail event includes caller identity
FT-014 | System | Multi-User Concurrent Submission | Validate platform handles 24 concurrent brief submissions without errors or data conflicts | Full platform deployed in Staging with Locust or pytest fixtures; 24 distinct synthetic brief payloads prepared; DynamoDB on-demand capacity active | 1. Submit 24 brief generation jobs simultaneously from 24 different test user sessions 2. Poll status for all 24 solution_ids 3. Monitor SQS queue depth; DLQ depth; Step Functions active executions 4. Wait for all 24 jobs to reach COMPLETE or FAILED within 60 min | All 24 jobs reach COMPLETE within 60 min; DLQ depth remains 0; no DynamoDB throttle events; no Lambda throttle events | Critical | Staging | QA Lead | Not Started | Not Executed | DDD §Business Context – Workload Criticality (24 concurrent jobs); SOW §Testing & Validation – Performance & Load Testing | Corresponds to the quarterly throughput target of 24 engagements
FT-015 | Regression | Rollback Alias Revert – Lambda Blue-Green | Validate that reverting Lambda PROD aliases to a prior verified version restores platform functionality within 30 minutes | Two verified Lambda deployment versions exist in Production (or Staging); GitHub Actions rollback.yml workflow available | 1. Record current PROD alias version for all API Handler functions 2. Deploy a synthetic defective Lambda version and update PROD aliases 3. Execute rollback.yml workflow targeting the prior version 4. Verify PROD aliases revert to prior version 5. Confirm POST /api/v1/solutions returns HTTP 202 after rollback | All PROD aliases reverted to prior version within 30 min; health endpoint returns HTTP 200; end-to-end brief submission succeeds post-rollback | Critical | Staging | Cloud/DevOps Engineer | Not Started | Not Executed | DDD §Implementation Approach – Rollback Strategy; IG §Migration & Cutover – Rollback Procedure | Rollback must complete in ≤30 min per SOW RTO commitment
FT-016 | Regression | Legacy Template Pipeline Ingestion | Validate that the Template Ingestion Lambda parses a Word/Excel/PowerPoint template and produces a valid Bedrock prompt template in S3 | isb-template-ingest Lambda deployed; sample DOCX/XLSX/PPTX templates uploaded to S3 under templates/legacy/ | 1. Upload a representative DOCX template to s3://amatra-isb-templates-staging/legacy/solution-briefing/ 2. Trigger isb-template-ingest Lambda manually with S3 event payload 3. Verify extracted prompt template written to S3 under templates/prompts/solution-briefing/ 4. Submit a brief using the new prompt and verify artifact is generated | Prompt template created in S3 without error; downstream generation job completes with ≥90% QA score | High | Staging | ML/AI Engineer | Not Started | Not Executed | DDD §Data Architecture – Data Migration Strategy – Legacy Template Pipeline; IG §Prerequisites – Technical Prerequisites | Test DOCX; XLSX; and PPTX formats separately

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
NFT-001 | Performance | API Gateway Response Time Under Load | Validate that the job submission endpoint meets the ≤500 ms p99 response time target under 24 concurrent users | Staging platform deployed; Locust load test configured; provisioned concurrency active on isb-api-submit (5 units) | 1. Configure Locust with 24 concurrent users and 2 user/s spawn rate 2. Execute 30-min sustained load test against POST /api/v1/solutions 3. Collect API Gateway latency metrics from CloudWatch 4. Calculate p99 response time from latency distribution | p99 response time ≤500 ms for POST /api/v1/solutions throughout the 30-min run; zero Lambda cold-start errors on provisioned concurrency functions | Critical | Staging | Performance Engineer | Not Started | Not Executed | DDD §Business Context – Workload Criticality – API Response Time ≤500 ms p99; SOW §Testing & Validation – Performance & Load Testing | Baseline before Phase 1 go-live; repeat after Phase 2 go-live
NFT-002 | Performance | Async Job Completion Under Peak Load | Validate that all 24 concurrent generation jobs complete within the 60-minute SLA under sustained peak load | Full platform deployed in Staging; Locust load test configured for 24 concurrent job submissions; Step Functions state machine active | 1. Submit 24 concurrent generation jobs via Locust at spawn rate of 2 users/s 2. Poll Step Functions execution statuses every 60 s 3. Record completion time for each execution 4. Monitor DLQ depth and Lambda error rates throughout | All 24 jobs reach COMPLETE status within 60 min; DLQ depth remains 0; Lambda error rate < 1%; no Step Functions execution failures | Critical | Staging | Performance Engineer | Not Started | Not Executed | DDD §Business Context – Workload Criticality – Async Job Completion ≤60 min p95; SOW §Testing & Validation – Performance & Load Testing | 2× expected peak per SOW performance test requirement
NFT-003 | Performance | Lambda Cold Start Latency | Validate that Lambda cold-start latency is ≤3 seconds for all four API Handler functions under production-like conditions | API Handler Lambda functions deployed in Staging without provisioned concurrency enabled (to simulate cold starts); CloudWatch cold-start metric configured | 1. Disable provisioned concurrency on all API Handler functions temporarily 2. Wait 15 min for all warm instances to expire 3. Submit 5 rapid sequential requests to each handler 4. Collect cold-start duration from CloudWatch Lambda metric 5. Re-enable provisioned concurrency | Cold-start duration ≤3 s for all API Handler functions; provisioned concurrency re-enabling eliminates cold starts in subsequent requests | High | Staging | Performance Engineer | Not Started | Not Executed | DDD §Business Context – Workload Criticality – Lambda Cold Start ≤3 s; IG §Infrastructure Deployment – Compute | Provisioned concurrency values: isb-api-submit 5; isb-api-status 5; isb-api-retrieve 3; isb-api-admin 2
NFT-004 | Performance | DynamoDB Read/Write Latency at Target Load | Validate DynamoDB SolutionState and UsageTracking tables meet the ≤10 ms p99 latency target under production workload | DynamoDB tables AmatraISB-SolutionState-Staging and AmatraISB-UsageTracking-Staging active with PAY_PER_REQUEST billing; CloudWatch DynamoDB metrics configured | 1. Execute 2 000 read operations and 500 write operations against both tables via a load script 2. Collect SuccessfulRequestLatency metric from CloudWatch for a 10-min window 3. Calculate p99 latency for reads and writes separately | p99 read latency ≤10 ms; p99 write latency ≤10 ms; zero DynamoDB throttle events throughout the run | Medium | Staging | Performance Engineer | Not Started | Not Executed | DDD §Business Context – Workload Criticality – DynamoDB Read/Write ≤10 ms p99; DDD §Infrastructure – Compute Sizing | Matches ~2M reads + 500K writes/month projection from SOW scope parameters
NFT-005 | Performance | Bedrock Token Budget Monitoring | Validate that monthly Bedrock token consumption is tracked and the P3 alarm fires at 80% of the monthly budget | CloudWatch alarm amatra-isb-bedrock-budget-warning-prod configured; SNS subscription for Head of Solutions email active; Bedrock token usage metrics available | 1. Simulate token consumption equal to 80% of the 10M input / 5M output monthly budget in Staging 2. Verify CloudWatch alarm transitions to ALARM state 3. Verify SNS email notification sent to Head of Solutions 4. Reset alarm state and verify it returns to OK | CloudWatch P3 alarm fires at 80% threshold; email notification delivered within 5 min; alarm resets to OK after state reset | Medium | Staging | Performance Engineer | Not Started | Not Executed | DDD §Infrastructure – Monitoring – Alert Definitions P3; DDD §Component Design – AI Generation Engine | Haiku substitution for discovery-questionnaire reduces Sonnet token cost by ~20%
NFT-006 | Security | Authentication Bypass Attempt | Validate that the API Gateway Cognito authoriser blocks all unauthenticated and tampered token attempts | API Gateway deployed with Cognito authoriser; WAF WebACL with CRS rule group active | 1. Send requests with no Authorization header 2. Send requests with an expired token (>15 min old) 3. Send requests with a token signed by a different Cognito User Pool 4. Send requests with base64-decoded payload tampered then re-encoded 5. Verify all attempts are rejected before Lambda invocation | HTTP 401 for all four unauthorised patterns; no Lambda invocation recorded in CloudWatch; CloudTrail event logged for each rejection | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Identity & Access Management – Authentication; DDD §Integration Design – Authentication & SSO Flows | OWASP A01; verify GuardDuty does not generate false positives
NFT-007 | Security | WAF SQL Injection and Rate Limit Validation | Validate that WAF blocks SQL injection payloads and enforces the 2 000 requests per 5-min per-IP rate limit | AWS WAF WebACL with CRS + KBI managed rules attached to API Gateway stage; rate-based rule configured at 2 000 req/5 min/IP | 1. Send POST /api/v1/solutions with SQL injection payload in brief field 2. Verify WAF CRS rule blocks the request 3. Send 2 001 requests from the same IP within a 5-min window using a load script 4. Verify the 2 001st request returns HTTP 429 5. Verify WAF logs record both the SQLi block and the rate-limit block | SQLi payload blocked with HTTP 403 by WAF; rate limit triggers HTTP 429 at request 2 001; all blocks recorded in WAF CloudWatch logs | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Network Security – WAF Rules; IG §Infrastructure Deployment – Networking Validation | OWASP A03; confirm CRS rule group version in use
NFT-008 | Security | KMS Encryption at Rest Verification | Validate that all S3 buckets and DynamoDB tables reject unencrypted writes and use the correct CMKs | Four KMS CMKs deployed; S3 bucket policies with deny on unencrypted PutObject; DynamoDB tables encrypted with amatra-isb-dynamodb CMK | 1. Attempt PutObject to artifacts bucket without SSE-KMS header 2. Verify HTTP 403 returned by S3 3. Query each S3 bucket and DynamoDB table for their encryption configuration 4. Verify CMK aliases match alias/amatra-isb-s3-artifacts and alias/amatra-isb-dynamodb respectively | S3 unencrypted PutObject rejected with HTTP 403; all buckets report SSE-KMS with correct CMK alias; both DynamoDB tables report ENABLED encryption with correct CMK | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Data Protection – Encryption at Rest; IG §Infrastructure Deployment – Security Validation Procedures | SOC 2 CC6 evidence item; results documented in evidence package
NFT-009 | Security | TLS Version Enforcement | Validate that API Gateway rejects TLS 1.0 and TLS 1.1 connections and accepts only TLS 1.2 and above | API Gateway custom domain configured with TLS 1.2+ security policy; ACM certificate issued | 1. Attempt HTTPS connection to api.amatra-isb.internal using TLS 1.0 2. Attempt connection using TLS 1.1 3. Attempt connection using TLS 1.2 4. Attempt connection using TLS 1.3 5. Verify response codes and handshake outcomes | TLS 1.0 and TLS 1.1 connections refused with handshake failure; TLS 1.2 connection accepted; TLS 1.3 connection accepted; health endpoint returns HTTP 200 on TLS 1.2+ | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Network Security – TLS Enforcement; IG §Infrastructure Deployment – Networking Validation | Run via curl with --tlsv1.0 / --tlsv1.1 / --tlsv1.2 flags
NFT-010 | Security | GuardDuty Threat Detection Validation | Validate that GuardDuty detects a simulated credential-stuffing event and triggers the automated Lambda remediation response | GuardDuty detector ENABLED; automated remediation Lambda (isb-guardduty-remediation-prod) deployed; SNS topic configured for Security & Compliance Lead notification | 1. Simulate a high-rate Cognito authentication failure pattern exceeding the 10% threshold 2. Verify GuardDuty generates a HIGH severity finding within 5 min 3. Verify automated remediation Lambda suspends the affected Cognito user account 4. Verify SNS notification sent to Security & Compliance Lead 5. Verify event recorded in CloudTrail | GuardDuty HIGH finding raised within 5 min; Cognito user account suspended by remediation Lambda; SNS notification delivered; CloudTrail event logs the suspension | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Monitoring & Threat Detection; DDD §Security – Audit Logging – GuardDuty high-severity remediation | SOC 2 CC7 evidence item
NFT-011 | Security | IAM Least-Privilege Verification | Validate that all Lambda execution roles contain no wildcard resource policies and pass IAM Access Analyzer with zero active findings | IAM Access Analyzer configured for the production account; all Lambda execution roles deployed via iam-lambda-roles.yaml | 1. Run IAM Access Analyzer and retrieve findings for all Lambda execution roles 2. Run automated policy scanner checking for Resource: * statements 3. Verify isb-api-submit-prod role can only access AmatraISB-UsageTracking-Prod and AmatraISB-SolutionState-Prod tables 4. Verify Bedrock invoker role is scoped to named model ARNs only | Zero active IAM Access Analyzer findings; no wildcard resource policies found; isb-api-submit-prod role access limited to specified tables; Bedrock invoker scoped to named ARNs | Critical | Staging | Security Engineer | Not Started | Not Executed | DDD §Security – Identity & Access Management – Service Accounts; IG §Application Configuration – IAM Role Configuration | Run after every Lambda deployment via CI/CD pipeline gate
NFT-012 | Reliability | Platform Availability – 99.9% SLA Measurement | Validate that the platform meets the 99.9% monthly availability target measured by the CloudWatch Synthetics canary | CloudWatch Synthetics canary amatra-isb-health-canary deployed with 60-s interval; SNS P1 alarm configured on health-check failure rate | 1. Deploy CloudWatch Synthetics canary pinging GET /api/v1/health every 60 s 2. Monitor canary over a 7-day measurement window in Staging 3. Collect successful request count and failed request count 4. Calculate availability percentage 5. Trigger a simulated Lambda error and verify alarm fires | Availability ≥99.9% over the 7-day window; P1 alarm fires when health-check success rate drops below threshold within 5 min; alarm resolves automatically when service recovers | Critical | Staging | Operations Engineer | Not Started | Not Executed | DDD §Business Context – Workload Criticality – Platform Availability 99.9%; SOW §Success Metrics – Platform Availability | 7-day Staging measurement prior to each production go-live
NFT-013 | Reliability | DynamoDB PITR Restore – RPO ≤15 Minutes | Validate that DynamoDB Point-in-Time Recovery can restore the SolutionState table to within 15 minutes of a specified timestamp | DynamoDB PITR enabled on AmatraISB-SolutionState-Staging; test data written to the table; IAM permissions for PITR restore granted | 1. Write 10 known solution records to AmatraISB-SolutionState-Staging at T0 2. Record exact timestamp T0 3. Write 5 additional records at T0+5 min 4. Initiate PITR restore to timestamp T0+2 min to a new table AmatraISB-SolutionState-Restored 5. Verify restored table contains exactly 10 original records and not the 5 new ones | Restore completes within 30 min; restored table contains exactly the records written before T0+2 min; no data loss beyond the targeted RPO window of 15 min | Critical | Staging | Operations Engineer | Not Started | Not Executed | DDD §Infrastructure – Disaster Recovery – RPO ≤15 min; DDD §Infrastructure – Disaster Recovery – DR Test; IG §Infrastructure Deployment – Compute – Rollback | Results documented for SOC 2 availability evidence package
NFT-014 | Reliability | Step Functions Retry on Bedrock Throttling | Validate that the Step Functions state machine retries the Bedrock invocation task up to 3 times with exponential backoff on ThrottlingException | Step Functions state machine deployed with retry config: maxAttempts=3; interval=30s; backOffRate=2; Bedrock invocation task configured; a mock Lambda that returns ThrottlingException is available | 1. Substitute a mock Bedrock invoker Lambda that returns ThrottlingException for the first 2 invocations then succeeds on the 3rd 2. Start a Step Functions execution 3. Monitor execution timeline for retry intervals 4. Verify execution completes successfully on the 3rd attempt | Execution retries 2 times before succeeding; retry intervals approximately 30 s and 60 s (exponential backoff); final execution status SUCCEEDED; no DLQ message generated | High | Staging | QA Engineer | Not Started | Not Executed | DDD §Integration Design – Messaging & Event Patterns – Retry Policy; DDD §Integration Design – External System Integrations | Validates async job durability for the 30–60 min job window
NFT-015 | Reliability | DLQ Alert and Job Replay | Validate that a failed job message triggers the P1 DLQ alarm and can be successfully replayed to the primary queue | SQS DLQ amatra-isb-job-dlq-staging active with maxReceiveCount=3; CloudWatch P1 alarm on DLQ depth > 0; SNS PagerDuty integration configured in Staging using a test endpoint | 1. Place a synthetic message that will fail processing onto amatra-isb-job-queue-staging 2. Allow the message to exhaust 3 receive attempts and move to DLQ 3. Verify CloudWatch P1 alarm transitions to ALARM 4. Run replay_dlq_message.py script to move message back to primary queue 5. Verify message is processed successfully on replay | P1 alarm fires within 5 min of message arriving in DLQ; SNS notification delivered; replayed message processed successfully with job reaching COMPLETE; DLQ depth returns to 0 | Critical | Staging | QA Engineer | Not Started | Not Executed | DDD §Integration Design – Messaging & Event Patterns – Dead Letter Queue; IG §Appendix D – Troubleshooting – DLQ Message Received | Runbook RUN-001 validation
NFT-016 | Compliance | CloudTrail Audit Log Integrity | Validate that CloudTrail captures all required API calls and that log file integrity validation detects no tampering | CloudTrail trail amatra-isb-cloudtrail-prod active for management events and S3 data events; S3 Object Lock enabled on log bucket with 7-year Compliance mode retention | 1. Perform 10 auditable platform actions (brief submission; usage override; Cognito user change; S3 PutObject) 2. Wait 15 min for CloudTrail log delivery 3. Run aws cloudtrail validate-logs for the log period 4. Verify each of the 10 actions appears in CloudTrail events 5. Attempt to delete a log file and verify Object Lock prevents deletion | All 10 auditable actions present in CloudTrail; validate-logs returns zero failures; delete attempt rejected by Object Lock with HTTP 403 | High | Staging | Compliance Officer | Not Started | Not Executed | DDD §Security – Audit Logging & SIEM Integration; DDD §Security – Compliance Mappings SOC 2 CC7 | SOC 2 evidence item; run monthly per ongoing monitoring schedule
NFT-017 | Compliance | GDPR Right-to-Erasure End-to-End | Validate that the admin right-to-erasure Lambda deletes all user-linked S3 objects; DynamoDB SolutionState records; DynamoDB UsageTracking records; and the Cognito UserRecord for a given user_id | Test user with 3 solutions in SolutionState; 2 months of UsageTracking records; Cognito account; and S3 artifacts written; admin erasure Lambda deployed | 1. Record all S3 keys; DynamoDB records; and Cognito sub for the test user 2. Invoke the admin erasure Lambda with the test user_id 3. Verify all S3 objects under the user's solution keys are deleted (versioned) 4. Verify DynamoDB SolutionState and UsageTracking records removed 5. Verify Cognito UserRecord deleted | All S3 objects deleted (S3 version markers created for audit); DynamoDB records removed; Cognito account deleted; CloudTrail logs the erasure events; no personal data remains in any store | High | Staging | Compliance Officer | Not Started | Not Executed | DDD §Data Architecture – Data Governance – Right to Erasure GDPR; DDD §Security – Compliance Mappings GDPR Article 25 | GDPR Article 17 compliance test; execute annually in Staging

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
UAT-001 | Business Process | Phase 1 Pre-Sales Brief-to-Package – End-to-End Workflow | Validate that a pre-sales consultant can submit a real (PII-scrubbed) client brief and receive a complete pre-sales engagement package meeting Amatra's quality standards | UAT environment with platform deployed; Cognito UAT user in PreSales group; 3-5 representative PII-scrubbed client briefs provided by Head of Solutions; quality rubric defined | 1. Pre-sales consultant logs in via Cognito 2. Submits one of the provided client briefs via the platform 3. Polls job status until COMPLETE 4. Downloads all 4 Phase 1 artifact types 5. Scores each artifact against the quality rubric 6. Records pass/fail and any defects on the structured scoring form | All 4 Phase 1 artifacts generated within 60 min; each artifact scores ≥90% on the quality rubric; no placeholder text remaining; cross-references consistent (e.g. cost figures reconcile across SoW and infrastructure-costs artifact) | Critical | Staging | Head of Solutions | Not Started | Not Executed | SOW §Testing & Validation – User Acceptance Testing – Phase 1 UAT; SOW §Success Metrics – QA first-pass ≥90% | Phase 1 production go-live gate; written sign-off from Head of Solutions required
UAT-002 | Business Process | Phase 2 Delivery Artifact Pipeline – End-to-End Workflow | Validate that a delivery consultant can generate all three Phase 2 delivery artifacts and that outputs meet Amatra's delivery quality standards | Phase 2 platform deployed in UAT environment; Cognito UAT user in Delivery group; representative client brief for a delivery engagement provided by VP Engineering team | 1. Delivery consultant logs in and submits a brief requesting all 3 delivery artifact types 2. Polls status until COMPLETE 3. Downloads detailed-design; implementation-guide; and terraform artifacts 4. Reviews detailed-design against its required section structure from guidance 5. Runs terraform validate on the Terraform output 6. Scores each artifact against the quality rubric | All 3 delivery artifacts generated within 60 min; terraform validate returns success; detailed-design contains all required sections; implementation-guide commands are syntactically correct; rubric score ≥90% for each artifact | Critical | Staging | VP Engineering | Not Started | Not Executed | SOW §Testing & Validation – User Acceptance Testing – Phase 2 UAT; SOW §Deliverables – Delivery Artifact Pipeline | Phase 2 production go-live gate; written sign-off from VP Engineering required
UAT-003 | Business Process | Artifact Turnaround Time – ≤2 Business Days | Validate that the end-to-end platform artifact turnaround time from brief submission to full package availability meets the ≤2 business days SOW success metric | Full Phase 2 platform deployed in production; representative mix of all 7 artifact types requested; normal business-hours workload | 1. Record timestamp T_start at brief submission 2. Monitor job status for all 7 artifact types 3. Record timestamp T_complete when all artifacts reach COMPLETE 4. Calculate elapsed time and compare to the 2-business-day SLA 5. Verify result is consistent across 5 sequential test submissions over 5 business days | All 5 test submissions complete within 2 business days (480 business minutes); median turnaround time logged in the SLA & Availability CloudWatch dashboard; no submission exceeds the 2-day threshold | Critical | Production | Head of Solutions | Not Started | Not Executed | SOW §Success Metrics – Artifact Turnaround ≤2 business days; DDD §Business Context – Business Drivers – Artifact Turnaround Acceleration | Reported at Phase 3 GA review; 90-day post-GA measurement for throughput metric
UAT-004 | Business Process | Proposal Throughput – ≥24 Engagements per Quarter | Validate that the platform supports ≥24 active engagement generation runs per calendar quarter without degradation | GA platform deployed; all 120 users onboarded; CloudWatch Quality & Usage dashboard active; Bedrock token budget tracking live | 1. Monitor generation run count on the Quality & Usage dashboard over a 30-business-day period post-GA 2. Verify total active engagements per quarter trend toward ≥24 3. Check that no per-user or global usage limit is blocking legitimate submissions 4. Verify QA pass rate stays ≥90% throughout the period | Total quarterly engagement count ≥24 within 90 days of GA; no legitimate submission blocked by usage limits; QA pass rate ≥90%; monthly Bedrock token spend within budget (no P3 alarm sustained over 30 days) | Critical | Production | Head of Solutions | Not Started | Not Executed | SOW §Success Metrics – Quarterly Proposal Throughput ≥24; SOW §Background & Objectives – Triple Proposal Throughput | Key SOW business objective metric; reviewed at project close (Deliverable #24)
UAT-005 | Business Process | Okta-to-Cognito Identity Migration – All Users Authenticated | Validate that 100% of the migrated Okta user records can authenticate via Amazon Cognito with zero authentication outages | Okta-to-Cognito migration complete; all ~50 active user records imported to Cognito prod user pool; temporary passwords issued; AmAdmin users have TOTP MFA enrolled | 1. Notify all 50 migrated users to log in and set a new permanent password 2. Track successful logins over the 2-week parallel-run period 3. Verify no user is unable to authenticate at the end of the parallel-run window 4. Verify AmAdmin users are prompted for TOTP MFA on every login 5. Decommission Okta only after 100% authentication confirmed | 100% of migrated users authenticate successfully within the parallel-run window; zero authentication outages during migration; all AmAdmin users pass TOTP MFA challenge; Okta tenant decommissioned with no user locked out | Critical | Production | Security & Compliance Lead | Not Started | Not Executed | SOW §Success Metrics – Identity Migration 100% of Okta records; DDD §Data Architecture – Data Migration Strategy – Okta-to-Cognito; IG §Phase 2 Core Platform – Detailed Procedures 2.1 | Zero-downtime migration requirement from SOW; Security & Compliance Lead sign-off required
UAT-006 | User Interface | CloudWatch SLA Dashboard Usability | Validate that the SLA & Availability CloudWatch dashboard provides the VP Engineering team with the real-time visibility needed to monitor platform SLA targets | CloudWatch SLA dashboard amatra-isb-sla-prod deployed; live production traffic flowing; all alarms configured | 1. VP Engineering navigates to the SLA & Availability dashboard 2. Reviews the monthly availability percentage vs. 99.9% target 3. Reviews the async job completion rate vs. >99% target 4. Reviews average and p95 job completion time vs. ≤60 min target 5. Validates that CloudWatch alarm states match expected operational status | Dashboard displays all three SLA KPIs with correct values; each metric widget is labelled clearly; alarm state widgets accurately reflect current system health; no stale or missing data in any widget | High | Production | VP Engineering | Not Started | Not Executed | DDD §Infrastructure – Monitoring – Logging & Observability – SLA Dashboard; SOW §Deliverables #20 – CloudWatch Monitoring & SLA Dashboards | Deliverable #20 acceptance criterion
UAT-007 | User Interface | Quality & Usage Dashboard – QA Pass Rate Visibility | Validate that the Quality & Usage CloudWatch dashboard accurately displays the QA first-pass acceptance rate against the ≥90% target | CloudWatch Quality dashboard amatra-isb-quality-prod deployed; QA validation layer active in production; at least 20 artifacts processed | 1. Head of Solutions navigates to the Quality & Usage dashboard 2. Reviews QA first-pass acceptance rate metric vs. ≥90% target 3. Reviews Bedrock token consumption vs. monthly budget 4. Reviews per-user and global generation counts vs. monthly limits 5. Verifies artifact type distribution is visible | QA first-pass rate widget shows current rate and trend line; token consumption widget matches CloudWatch Bedrock metrics; generation counts match DynamoDB UsageTracking records; all metrics refreshed within 5 min of new data | High | Production | Head of Solutions | Not Started | Not Executed | DDD §Infrastructure – Monitoring – Business KPI Monitoring; SOW §Success Metrics – QA first-pass ≥90%; SOW §Deliverables #15 – QA Validation Layer & Pass-Rate Dashboard | Deliverable #15 acceptance criterion
UAT-008 | Business Rules | QA Validation Layer – ≥90% First-Pass Acceptance Rate | Validate that the Artifact Processor QA scoring produces a first-pass acceptance rate of ≥90% across a representative set of 20 generated artifacts | QA validation layer (isb-artifact-processor) deployed in Phase 2; 20 representative client briefs submitted and artifacts generated; quality rubric scoring criteria formalised by Head of Solutions | 1. Generate artifacts from all 20 representative briefs across all 7 artifact types 2. Allow isb-artifact-processor to score each artifact automatically 3. Head of Solutions manually reviews all artifacts scoring below the 90% threshold 4. Calculate overall first-pass acceptance rate (automated + manual agreement) 5. Document any P1 blocking defects for prompt refinement | ≥18 of 20 artifacts (90%) pass the quality rubric on first review with no P1 blocking defects; defects < 90% threshold are flagged with qa_status: REVIEW_REQUIRED in DynamoDB; prompt refinement backlog created for any failing types | Critical | Staging | Head of Solutions | Not Started | Not Executed | SOW §Success Metrics – QA first-pass ≥90%; SOW §Testing & Validation – Functional Validation – Target acceptance criterion; DDD §Data Governance – Quality | Core UAT quality gate for Phase 1 and Phase 2 go-live decisions
UAT-009 | Acceptance | Consulting Hours Reduction – ≥40% vs Baseline | Validate that the platform reduces consulting hours per engagement by ≥40% compared to the manual baseline of approximately 3 weeks | Platform GA with all 7 artifact types; historical manual engagement time baseline documented by Head of Solutions during Discovery (approximately 15 business days per engagement) | 1. Time 5 end-to-end engagement package generation runs on the platform (brief submission to all artifacts ready) 2. Record platform elapsed time plus any consultant review/adjustment time per engagement 3. Compare total time to the 15-business-day manual baseline 4. Calculate percentage reduction | Average total consultant time per engagement ≤60% of the 15-business-day baseline (i.e. ≤9 business days including review); generation time alone ≤2 business days; ≥40% reduction confirmed; result reported to CTO at project close | High | Production | Head of Solutions | Not Started | Not Executed | SOW §Success Metrics – Consulting hours ≤60% of current baseline; SOW §Background & Objectives – Reduce consulting hours by 40% | Measured and reported in Optimisation Recommendations Report (Deliverable #21)
UAT-010 | Business Process | SOC 2 Type II Controls Evidence – Go-Live Readiness | Validate that all SOC 2 Type II evidence collection activities are confirmed active prior to the Phase 2 production deployment gate | CloudTrail active from Phase 1 go-live; AWS Config SOC 2 rules deployed; Security Hub aggregating; KMS encryption active; PITR enabled; quarterly Cognito access review scheduled | 1. Security & Compliance Lead reviews the SOC 2 evidence log for all five Trust Service Criteria 2. Confirms CloudTrail has been logging continuously since Phase 1 go-live 3. Confirms AWS Config has zero CRITICAL non-compliance findings 4. Confirms Security Hub CRITICAL findings are at zero 5. Signs off on the SOC 2 evidence package (Deliverable #16) | SOC 2 evidence package complete and signed off by Security & Compliance Lead; CloudTrail continuous since Phase 1 go-live with no integrity failures; Config zero CRITICAL non-compliance; Security Hub zero CRITICAL findings; evidence package delivered by Month 8 Week 2 | Critical | Production | Security & Compliance Lead | Not Started | Not Executed | SOW §Success Metrics – SOC 2 Type II audit-ready controls prior to GA; DDD §Security – Compliance Mappings SOC 2 CC6/CC7/A1/PI1/C1/P1-P8; SOW §Deliverables #16 | Phase 2 go-live gate; CTO phase-gate approval depends on this sign-off
UAT-011 | Acceptance | GA Rollout – All 120 Users Onboarded Before 31 January 2027 | Validate that all ~120 internal Amatra users are onboarded and authenticated on the platform before the GA hard deadline of 31 January 2027 | GA rollout plan activated; all user cohorts scheduled for onboarding and training; Cognito user pool at full capacity; CloudWatch active user metric tracking | 1. Execute GA rollout plan in cohorts: pre-sales consultants (Phase 1 trained); delivery consultants; sales; admin 2. Track Cognito monthly active users metric against the 120-user target 3. Verify all users have logged in at least once before 31 January 2027 4. Deliver Train-the-Trainer session to Head of Solutions (Deliverable #22) 5. CTO signs off on project close | All 120 users authenticated at least once before 31 January 2027; CloudWatch monthly active users metric reaches 120; zero users unable to authenticate; Train-the-Trainer session completed and recorded; CTO project close sign-off received | Critical | Production | Head of Solutions | Not Started | Not Executed | SOW §Success Metrics – Platform live and all 120 users onboarded before 31 January 2027; SOW §Deliverables #22 – Train-the-Trainer Session; SOW §Milestones – M8 GA Rollout Complete | Hard deadline from SOW; directly tied to flagship client renewal by 31 January 2027
UAT-012 | Business Process | Hypercare P1 Incident Response – ≤2 Hour Vendor Response | Validate that the vendor team responds to a P1 platform-down incident within the 2-hour hypercare SLA during the Phase 1 hypercare period | Phase 1 hypercare active (October/November 2026); Slack #amatra-isb-ops channel live; PagerDuty integration configured; vendor on-call rotation set | 1. Amatra VP Engineering simulates a P1 incident by disabling the CloudWatch Synthetics canary and confirming the platform availability alarm fires 2. Records the time of PagerDuty alert creation (T_alert) 3. Records the time of first vendor response in Slack (T_response) 4. Calculates response time T_response minus T_alert 5. Vendor provides incident triage notes within 2 hours | Vendor first response in Slack within 2 hours of PagerDuty alert; triage notes provided identifying root cause or escalation path; incident resolved or escalated to L3 within the hypercare SLA window; CloudTrail event confirms vendor access was time-limited and logged | High | Production | VP Engineering | Not Started | Not Executed | SOW §Handover & Support – Hypercare Support P1 ≤2-hour response; IG §Operational Handover – Support Model L2 Vendor Hypercare | Runbook RUN-005 validation; test during first week of Phase 1 hypercare