## Cover
Test Plan
Generated: | June 05, 2026
Solution: | Tmphvehf53R
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
FT-001 | Unit | Cognito User Registration | Validate new consultant can register in the Cognito User Pool and receive a verified JWT | Cognito User Pool amatra-user-pool-dev is ACTIVE; post-confirmation Lambda deployed | 1. Register new user via amatra login CLI 2. Complete email verification 3. Verify post-confirmation Lambda fires 4. Check DynamoDB user_profiles for new record 5. Verify JWT returned on login | HTTP 200 with valid Cognito JWT; DynamoDB user_profiles record created with monthly_quota_used=0 | Critical | Unit | Solutions Engineer | Not Started | Not Executed | DDD-Identity §Security — Identity & Access Management; SOW §Testing — Functional Validation | Validate token TTL is 1-hour access / 30-day refresh
FT-002 | Unit | JWT Authentication Rejection | Validate expired and tampered tokens are rejected by the API Gateway JWT authoriser | API Gateway deployed with Cognito JWT authoriser; test tokens prepared | 1. Send request with expired JWT to POST /solutions 2. Send request with tampered JWT signature 3. Send request with no Authorization header 4. Send valid JWT to GET /health | HTTP 401 for all unauthorized attempts; HTTP 200 for valid token on public health endpoint | Critical | Unit | Security Engineer | Not Started | Not Executed | DDD-Security §Cognito and JWT Validation; IG §Security Validation — Cognito and JWT Validation | Test all 11 protected routes with invalid tokens
FT-003 | Unit | Input Validation — CLI Brief | Validate the Input Validator agent rejects malformed brief.txt before any generation occurs | AgentCore Input Validator agent ACTIVE; test brief files prepared | 1. Submit brief with missing required fields via amatra generate 2. Submit brief with invalid EO Framework schema 3. Submit brief with oversized payload 4. Submit valid brief | HTTP 400 / structured rejection for invalid briefs; SolutionState.status=FAILED with rejection reason; valid brief proceeds to RUNNING | Critical | Unit | QA Engineer | Not Started | Not Executed | DDD §Component Design — Input Validator Agent; IG §Phase 2 Agents and Integration | Adversarial brief inputs test prompt injection resistance
FT-004 | Unit | Per-User Quota Enforcement | Validate DynamoDB atomic conditional write blocks generation at 10 solutions per user per month | DynamoDB user_profiles and quota_global tables provisioned; test user with 9 used solutions | 1. Submit 10th solution generation request for the test user 2. Submit 11th solution generation request for the same user 3. Check DynamoDB monthly_quota_used counter 4. Verify HTTP response codes | 10th request accepted (HTTP 202); 11th request rejected (HTTP 429 QuotaExceededException); counter increments atomically | Critical | Unit | Solutions Engineer | Not Started | Not Executed | DDD §Data Architecture — QuotaGlobal; SOW §Success Metrics — Zero quota overruns | Test 20 concurrent writes — exactly 10 must succeed
FT-005 | Unit | Global Pool Quota Enforcement | Validate DynamoDB conditional write blocks generation when global 1000/month cap is reached | DynamoDB quota_global table with solutions_used_this_month=999; test user with available quota | 1. Submit one solution generation request (should succeed and reach 1000) 2. Submit another solution generation request from a different user 3. Verify quota_global counter | First request accepted; second request rejected HTTP 429; quota_global counter does not exceed 1000 | Critical | Unit | Solutions Engineer | Not Started | Not Executed | DDD §Data Architecture — QuotaGlobal; SOW §Scope Parameters — Global Monthly Quota | Race condition test with concurrent writes at limit boundary
FT-006 | Integration | Post-Confirmation Lambda Trigger | Validate Cognito post-confirmation Lambda eagerly writes user profile and quota counters to DynamoDB on sign-up | Cognito User Pool live; post-confirmation Lambda deployed; DynamoDB user_profiles table ready | 1. Register new user in Cognito 2. Complete email confirmation 3. Query DynamoDB user_profiles for new user_id 4. Verify all required attributes are present 5. Verify monthly_quota_used initialised to 0 | DynamoDB record created within 5 seconds of confirmation; monthly_quota_used=0; quota_reset_month set to current YYYY-MM | Critical | Integration | Solutions Engineer | Not Started | Not Executed | DDD §Component Design — Post-Confirmation Lambda; IG §Phase 1 — Section 1.2 | Every authenticated call must have a valid quota record
FT-007 | Integration | Step Functions Orchestration — Five-Agent Pipeline | Validate Step Functions state machine correctly sequences all five agents for a complete solution generation run | All five AgentCore agents ACTIVE; Step Functions state machine deployed; valid brief in S3 | 1. Start Step Functions execution with a valid solution_id 2. Verify Input Validator stage completes and transitions to generation 3. Verify Pre-Sales Generator produces 5 presales artifacts in S3 4. Verify Delivery Generator produces 6 delivery artifacts in S3 5. Verify Code Generator produces Terraform IaC bundle 6. Verify EO Validator runs format-check on each artifact | All 5 agents invoked in correct sequence; 12 artifacts written to S3 under {solution_id}/raw/; SolutionState.status transitions QUEUED→RUNNING→VALIDATING→COMPLETE | Critical | Integration | QA Engineer | Not Started | Not Executed | DDD §Architecture Patterns — Primary Pattern; IG §Phase 2 — Agent Integration Milestone Report | Monitor Step Functions execution history for state transition audit
FT-008 | Integration | eof-tools Converter Pipeline | Validate all 12 artifact-type converters in the ECR container image produce well-formed DOCX/PPTX/XLSX output | ECR image with eof-tools baked in deployed; all 12 raw markdown/CSV artifacts available in S3 | 1. Invoke eof-tools converter for each of 12 artifact types 2. Verify DOCX produced for: solution-briefing, SOW, detailed-design, implementation-guide 3. Verify PPTX produced for: solution-briefing 4. Verify XLSX produced for: LOE, infrastructure-costs, discovery-questionnaire 5. Open each converted file and validate structure | All 12 converters produce non-empty well-formed files; no eof_tools exceptions; converted files written to S3 under {solution_id}/converted/ | Critical | Integration | Solutions Engineer | Not Started | Not Executed | DDD §Technology Stack — eof-tools; IG §2.1 Docker Image Build — validate_converters | Run docker run --rm amatra-agents:1.0.0 python -m eof_tools.validate_converters
FT-009 | Integration | GitHub Artifact Commit Integration | Validate Code Generator agent commits all 12 artifacts to the public GitHub repository via Secrets Manager PAT after successful generation | GitHub PAT stored in Secrets Manager amatra/github-pat; public GitHub repository with write access; all 12 artifacts validated in S3 | 1. Complete a full solution generation run 2. Check GitHub repository for new branch {solution_id} 3. Verify all 12 artifacts are present under {solution_id}/ in the branch 4. Verify commit message format 5. Verify SolutionState.status=COMPLETE in DynamoDB | GitHub branch created with all 12 artifacts; commit message contains solution_id correlation key; S3 and GitHub artifact counts match (12); DynamoDB status=COMPLETE | High | Integration | Solutions Engineer | Not Started | Not Executed | DDD §Integration Design — GitHub API; IG §GitHub Commit Validation | Verify PAT is retrieved from Secrets Manager not Lambda env vars
FT-010 | Integration | API Route — POST /solutions | Validate the solution generation initiation route decrements quotas and starts Step Functions execution | API Gateway deployed with JWT authoriser; valid Cognito JWT; DynamoDB quota tables initialised | 1. Send POST /api/v1/solutions with valid JWT and brief payload 2. Verify quota counters decremented atomically 3. Verify Step Functions execution started 4. Verify solution_id returned in HTTP 202 response | HTTP 202 with valid solution_id UUID; DynamoDB monthly_quota_used incremented; Step Functions execution RUNNING; SolutionState.status=QUEUED | Critical | Integration | Solutions Engineer | Not Started | Not Executed | DDD §API Design — POST /api/v1/solutions; IG §Application Configuration — API Gateway Route Configuration | Verify HTTP 429 on quota exhaustion and HTTP 401 on missing JWT
FT-011 | Integration | API Route — GET /solutions/{id} Status Polling | Validate the solution status route returns accurate phase progress and per-phase token usage from DynamoDB | Solution generation in progress or complete; JWT token for owning user | 1. Submit POST /solutions to initiate generation 2. Poll GET /solutions/{solution_id} every 30 seconds 3. Verify status transitions are reflected in real time 4. On COMPLETE verify artifact_status map shows all 12 artifacts as PASSED 5. Verify token_usage_by_phase populated | HTTP 200 with status QUEUED/RUNNING/VALIDATING/COMPLETE progression; artifact_status map shows 12 keys; token_usage_by_phase populated after generation | High | Integration | QA Engineer | Not Started | Not Executed | DDD §API Design — GET /api/v1/solutions/{solution_id}; IG §CLI End-to-End Test — amatra status | Cross-user access to another user's solution_id must return HTTP 403
FT-012 | System | End-to-End CLI Workflow — All 14 Subcommands | Validate a consultant can complete a full solution generation workflow using all 14 CLI subcommands from a clean pip install | Clean Python virtual environment; amatra-cli published to PyPI or test index; valid Cognito credentials | 1. pip install amatra-cli in clean venv 2. amatra login 3. amatra quota status 4. amatra generate --brief sample-brief.txt 5. amatra solutions list 6. amatra status --solution-id {id} 7. amatra artifacts list --solution-id {id} 8. amatra artifacts download all artifact types 9. amatra admin usage 10. amatra logout | All 14 subcommands execute without error; complete 12-artifact solution generated; all artifacts downloadable; quota counter updated; clean logout revokes local token | Critical | System | QA Engineer | Not Started | Not Executed | DDD §Technology Stack — CLI Distribution; SOW §Scope — CLI Subcommands; IG §CLI End-to-End Test | Validate on macOS and Linux (Windows out of scope)
FT-013 | System | End-to-End Generation — All 12 Artifact Types | Validate the complete platform generates all 12 EO Framework artifact types from a single representative client brief without manual intervention | Full platform deployed in staging; representative client brief available; all five agents ACTIVE | 1. Submit a realistic PREDICTif client brief via amatra generate 2. Monitor Step Functions execution through all five agent stages 3. Verify all 5 presales artifacts produced (solution-briefing, SOW, discovery-questionnaire, LOE, infrastructure-costs) 4. Verify all 6 delivery artifacts produced (detailed-design, test-plan, runbook, implementation-guide, change-management, as-built) 5. Verify Terraform IaC automation bundle produced 6. Verify all 12 pass EO Validator format-check and LLM quality-check | 12 artifacts in S3 under {solution_id}/raw/; all 12 have SolutionState ArtifactStatus=PASSED; generation completes within 60 minutes P95; GitHub branch contains all 12 artifacts | Critical | System | QA Lead | Not Started | Not Executed | DDD §Success Criteria — All 12 artifact types; SOW §Success Metrics; IG §Integration Test Success Criteria | Primary go-live gate — must pass before UAT
FT-014 | Regression | Quota Reset After Monthly Cycle | Validate the scheduled Lambda correctly resets per-user and global quota counters at the start of each calendar month | All quota tables populated with non-zero values; scheduled monthly reset Lambda deployed | 1. Set monthly_quota_used=10 for multiple test users 2. Set solutions_used_this_month=500 on quota_global 3. Invoke the monthly reset Lambda manually (simulating first-of-month trigger) 4. Verify all per-user counters reset to 0 5. Verify quota_global counter reset to 0 6. Verify quota_reset_month updated to new YYYY-MM | All user monthly_quota_used=0 after reset; quota_global solutions_used_this_month=0; quota_reset_month=current month; new generation requests accepted | High | Integration | Solutions Engineer | Not Started | Not Executed | DDD §Data Architecture — QuotaGlobal; IG §DynamoDB Quota Initialisation | Run regression after any quota enforcement code change
FT-015 | Regression | EO Validator Retry Loop — Up to 3 Retries | Validate the EO Validator agent retries format-check and LLM quality-check up to 3 times before escalating to DLQ | EO Validator agent deployed; Step Functions state machine with retry configuration; test artifact that fails initial validation | 1. Submit a brief that generates an artifact with a known format defect on first attempt 2. Observe Step Functions retry count increments 3. Verify retry attempts 1 2 and 3 are logged in CloudWatch 4. Verify successful correction on retry resolves to PASSED 5. Simulate consistent failure to verify DLQ escalation after 3 retries | Retry count 0→1→2→3 in SolutionState; successful artifact passes on ≤3 retries; persistent failure triggers DLQ after exactly 3 retries; CloudWatch metric AmatraPlatform/ValidationRetryRate emitted | Critical | Integration | QA Engineer | Not Started | Not Executed | DDD §Architecture Patterns — Validation Pattern; IG §Phase 3 — Validation loop testing | Core quality gate — retry cap enforces $5/solution cost ceiling

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
NFT-001 | Performance | P95 End-to-End Generation Latency | Validate complete 12-artifact solution generation completes within 60 minutes at the 95th percentile under steady-state load | Staging environment with all 5 AgentCore agents ACTIVE; load testing harness configured; representative client briefs available | 1. Submit 20 concurrent solution generation requests using the Lambda concurrency test harness 2. Collect CloudWatch AmatraPlatform/GenerationLatencyMs metrics for all executions 3. Calculate P50 P95 and P99 latency 4. Verify per-phase token counts are within expected range 5. Confirm no Step Functions execution timeouts | P50 latency < 30 minutes; P95 latency < 60 minutes; P99 latency < 90 minutes; zero execution timeouts; all 20 solutions complete with 12 artifacts | Critical | Performance | QA Engineer | Not Started | Not Executed | DDD §Business Context — SLA Expectations; SOW §Success Metrics — P95 < 60 minutes; IG §Phase 3 — Load testing | Baseline before and after Bedrock prompt optimisation
NFT-002 | Performance | 200 Solutions/Month Throughput Validation | Validate the platform sustains 200 solutions/month throughput with no quota throttle events or Bedrock spend overruns | Staging environment with production-equivalent DynamoDB on-demand capacity; k6 load script simulating 200 solutions/month at 10 concurrent peak | 1. Configure k6 load test to simulate 200 solutions/month (approx 10 concurrent during peak) 2. Execute 4-hour sustained load test 3. Monitor DynamoDB conditional write failures (target: 0) 4. Monitor per-solution Bedrock token spend via AmatraPlatform/TokenCostUSD metric 5. Monitor Lambda error rate and Step Functions failure rate | Zero DynamoDB quota throttle events; per-solution Bedrock spend ≤ $5 confirmed across all runs; Lambda error rate < 1%; Step Functions failure rate < 2%; P95 latency < 60 minutes maintained throughout | Critical | Performance | Solutions Engineer | Not Started | Not Executed | DDD §Business Drivers — Parallel Pipeline Throughput; SOW §Performance — Monthly Throughput Target; IG §Load Testing | Confirms linear scalability claim in architecture
NFT-003 | Performance | Per-Solution Bedrock Token Spend | Validate per-solution Claude Sonnet 4.6 + Haiku 4.5 combined token spend remains at or below $5.00 target | Production-equivalent environment; token usage instrumentation emitting AmatraPlatform/TokenCostUSD metric; five representative briefs of varying complexity | 1. Generate solutions for 5 representative briefs (SMB mid-market enterprise simple complex) 2. Record per-phase token counts for Sonnet 4.6 and Haiku 4.5 from DynamoDB solution_state.token_usage_by_phase 3. Calculate cost using documented pricing ($0.003/$0.015 per 1K Sonnet; $0.0008/$0.004 per 1K Haiku) 4. Compare against $5.00 budget 5. Verify CLI amatra status surfaces token spend | Per-solution cost ≤ $5.00 for all 5 test briefs; AmatraPlatform/TokenCostUSD custom metric within budget; Haiku 4.5 used for all EO Validator invocations (confirmed by phase breakdown) | Critical | Performance | ML/AI Engineer | Not Started | Not Executed | DDD §SLA Expectations — Per-Solution Bedrock Token Spend; SOW §Success Metrics — $5 token spend target; IG §Application Configuration — Bedrock Model Configuration | Alert at 90% of budget threshold per YAML config
NFT-004 | Performance | Lambda Cold Start and Concurrency | Validate Lambda cold start latency does not materially impact P95 solution latency and reserved concurrency prevents starvation | All 11 Lambda routes deployed with ARM64 Graviton2; reserved concurrency configured per route; CloudWatch X-Ray enabled | 1. Force cold starts by invoking all 11 Lambda functions after 15-minute idle period 2. Record cold start duration from X-Ray traces 3. Submit 50 rapid-fire solution initiation requests to test burst concurrency 4. Verify no reserved concurrency throttle events in CloudWatch 5. Verify X-Ray service map shows complete call graph | Lambda cold start < 2 seconds for all functions; no ConcurrencyLimitExceeded errors under 50 concurrent requests; X-Ray traces complete with non-null correlation IDs | Medium | Performance | DevOps Engineer | Not Started | Not Executed | DDD §Infrastructure — Compute Sizing; IG §Infrastructure Deployment — Compute | ARM64 Graviton2 provides ~20% cost advantage vs x86
NFT-005 | Security | JWT Authoriser Bypass Testing | Validate all 11 JWT-protected Lambda routes reject expired tampered and unsigned tokens with no data exposure | API Gateway with Cognito JWT authoriser deployed; OWASP ZAP or curl-based test scripts prepared | 1. Test each of the 9 JWT-protected routes with an expired token (expect HTTP 401) 2. Test with a tampered JWT signature (expect HTTP 401) 3. Test with no Authorization header (expect HTTP 401) 4. Test with a valid JWT from a different Cognito User Pool (expect HTTP 401) 5. Verify GET /health and POST /auth/refresh are accessible without JWT | HTTP 401 for all unauthorized attempts on all 9 protected routes; HTTP 200 for valid JWT; HTTP 200 for public endpoints /health and /auth/refresh; no data leakage in error response body | Critical | Security | Security Engineer | Not Started | Not Executed | DDD §Security — Cognito and JWT Validation; IG §Security Validation — Cognito and JWT Validation | OWASP API2: Broken Authentication — maps to go-live gate
NFT-006 | Security | IAM Least-Privilege Policy Validation | Validate all five AgentCore execution roles and 11 Lambda execution roles have no wildcard resource policies | All IAM roles deployed; AWS IAM Access Analyzer configured in us-west-2 | 1. Run AWS IAM Access Analyzer scan against all Amatra IAM roles 2. Manually review each of the 5 AgentCore execution roles for Resource:* policies 3. Verify Input Validator role scoped to Haiku 4.5 Bedrock ARN and brief S3 prefix only 4. Verify Code Generator role scoped to Sonnet 4.6 Bedrock ARN and amatra/github-pat secret ARN only 5. Confirm no wildcard actions or resources | IAM Access Analyzer returns zero active findings for all Amatra roles; no Resource:* in any execution role; Code Generator cannot read secrets other than amatra/github-pat | Critical | Security | Security Engineer | Not Started | Not Executed | DDD §Security — Role Definitions; IG §Security Validation — IAM Least-Privilege Validation; SOW §Security — IAM | Maps to SOC 2 CC6.3 Access Restriction control
NFT-007 | Security | OWASP API Top 10 — All 11 Lambda Routes | Validate all 11 Lambda API routes comply with OWASP API Security Top 10 controls | All 11 Lambda routes deployed; OWASP ZAP configured; admin and non-admin Cognito test accounts prepared | 1. Test API1 (Broken Object Level Authorisation): access another user's solution_id with valid JWT (expect 403) 2. Test API4 (Unrestricted Resource Consumption): exceed per-route throttle limit (expect 429) 3. Test API5 (Broken Function Level Authorisation): call GET /admin/usage without admin Cognito group (expect 403) 4. Test API8 (Security Misconfiguration): confirm HTTPS-only; no plaintext endpoints 5. Test remaining OWASP API Top 10 controls per IG checklist | HTTP 403 on cross-user access; HTTP 429 on throttle breach; HTTP 403 on admin route without admin scope; HTTPS enforced on all routes; all 10 OWASP controls pass | Critical | Security | Security Engineer | Not Started | Not Executed | DDD §Security — Audit Logging; IG §Security Validation — OWASP API Top 10 Validation; SOW §Testing — Security Testing | Security Test Report Deliverable #22 prerequisite for UAT
NFT-008 | Security | Data Encryption Validation | Validate S3 SSE-KMS encryption and DynamoDB KMS encryption are enforced and no plaintext credentials exist in Lambda environment variables | Platform deployed; SSE-KMS configured on S3 bucket; KMS CMK deployed | 1. Verify S3 artifact bucket encryption algorithm is aws:kms via get-bucket-encryption 2. Verify all Block Public Access settings are true on S3 artifact bucket 3. Verify DynamoDB tables use KMS encryption 4. Check all 11 Lambda environment variables for plaintext secrets (must be empty) 5. Verify S3 bucket policy includes aws:SecureTransport condition | S3 SSE algorithm = aws:kms; all 4 Block Public Access settings = true; DynamoDB encryption status = ENABLED; zero plaintext credentials in Lambda env vars; SecureTransport condition present in bucket policy | Critical | Security | Security Engineer | Not Started | Not Executed | DDD §Security — Data Protection; IG §Application Security Validation Checklist | Maps to SOC 2 CC6.7 and C1.1 controls
NFT-009 | Security | Secrets Manager PAT Rotation | Validate GitHub PAT stored in Secrets Manager rotates automatically and commits resume within 15 minutes of rotation | Secrets Manager secret amatra/github-pat deployed with rotation Lambda; GitHub PAT with repo scope injected | 1. Record current PAT version and last-rotated date 2. Manually trigger rotation Lambda for amatra/github-pat 3. Verify new PAT version created in Secrets Manager 4. Trigger a GitHub artifact commit within 5 minutes of rotation 5. Verify commit succeeds with rotated PAT and no 401 errors | Rotation Lambda completes without error; new secret version AWSCURRENT; GitHub commit succeeds within 15 minutes; no Lambda errors due to stale PAT; rotation audit event in CloudTrail | High | Security | Security Engineer | Not Started | Not Executed | DDD §Secrets Management; IG §Appendix D Troubleshooting — GitHub PAT Expiry; SOW §Security — Governance | Test quarterly per SOW runbook
NFT-010 | Reliability | Platform Availability — 99.5% Target | Validate the platform meets the 99.5% availability SLA measured over a 72-hour test window | Full platform deployed in staging; CloudWatch canary synthetic monitor configured at 5-minute intervals; all components ACTIVE | 1. Enable CloudWatch synthetic canary against GET /api/v1/health endpoint 2. Monitor over 72-hour window with canary checks every 5 minutes 3. Record any canary failures 4. Calculate availability percentage 5. Verify Lambda multi-AZ execution on simulated AZ failure (by temporarily adjusting security group) | Availability ≥ 99.5% (≤ 2 failed canary checks per 72-hour window after initial stabilisation); canary failures trigger CloudWatch alarm within 10 minutes; platform self-heals without manual intervention | High | Reliability | DevOps Engineer | Not Started | Not Executed | DDD §SLA Expectations — Platform Availability; DDD §High Availability Design; IG §Monitoring — Validation | CloudWatch canary alarm is go-live gate per green baseline requirement
NFT-011 | Reliability | Disaster Recovery — DynamoDB PITR Restoration | Validate DynamoDB PITR restoration recovers all three tables to a consistent 24-hour-old snapshot within RTO target | PITR enabled on all three DynamoDB tables (amatra-user_profiles amatra-solution_state amatra-quota_global); DR test environment available | 1. Confirm PITR ENABLED on all three tables via describe-continuous-backups 2. Write test records to all three tables and record their values 3. Wait 30 minutes then initiate PITR restore to T-30min for all three tables 4. Verify restored records match expected pre-test values 5. Measure restoration time | PITR restore completes within RTO target of 4 hours; restored data matches pre-test values; no data corruption; restoration time recorded and within SLA | Critical | Reliability | DevOps Engineer | Not Started | Not Executed | DDD §Disaster Recovery — RPO/RTO Targets; IG §Phase 1 — DynamoDB PITR Validation; SOW §Architecture — Operational Design | Run in staging — never run against production tables
NFT-012 | Reliability | AgentCore Agent Timeout Recovery | Validate Step Functions correctly handles an AgentCore agent timeout by escalating to DLQ and updating SolutionState to FAILED | Step Functions state machine deployed with catch clauses; SQS DLQ configured; CloudWatch alarm on DLQ depth | 1. Simulate agent timeout by configuring a test Step Functions execution with a forced task timeout 2. Observe Step Functions catch clause fires 3. Verify SolutionState.status updated to FAILED with error details 4. Verify DLQ receives the failed execution message 5. Verify CloudWatch alarm amatra-dlq-depth fires within 5 minutes | Step Functions catch clause fires within task HeartbeatSeconds (15 min per agent); DLQ depth increases to 1; CloudWatch CRITICAL alarm fires; SolutionState.status=FAILED with structured error; user receives HTTP error on next status poll | High | Reliability | Solutions Engineer | Not Started | Not Executed | DDD §Integration Design — Dead Letter Queue; IG §Appendix D — Troubleshooting Issue 1; SOW §Architecture — Operational Design | Validates all five runbook scenarios — agent timeout runbook
NFT-013 | Reliability | VPC Endpoint Traffic Isolation | Validate that no Bedrock DynamoDB or S3 traffic traverses the NAT Gateway and all internal service traffic remains on the AWS private network | All VPC endpoints deployed in available state; VPC Flow Logs enabled on NAT Gateway ENI | 1. Submit a complete solution generation run 2. Monitor NAT Gateway bytes-processed metric in CloudWatch during generation 3. Capture VPC Flow Logs for Lambda ENIs during generation 4. Verify Bedrock DynamoDB and S3 API calls do not appear in NAT Gateway flow logs 5. Verify only github.com and pypi.org traffic traverses NAT Gateway | NAT Gateway bytes-processed during generation is negligible (GitHub commit only); VPC Flow Logs confirm Bedrock/DynamoDB/S3 traffic uses VPC endpoint ENIs; no AWS API traffic via NAT | Medium | Reliability | DevOps Engineer | Not Started | Not Executed | DDD §Network Security — VPC Endpoints; IG §Networking Deployment — Validation; IG §Security Controls — VPC endpoint validation | VPC endpoints reduce NAT Gateway cost by ~60%
NFT-014 | Compliance | CloudTrail Audit Trail — S3 and DynamoDB Data Events | Validate CloudTrail captures all S3 object-level and DynamoDB table-level events with tamper-proof WORM retention | CloudTrail data events enabled; audit S3 bucket with Object Lock configured; test solution generation completed | 1. Submit a solution generation and completion run 2. Query CloudTrail for S3 PutObject events on the artifact bucket within past hour 3. Query CloudTrail for DynamoDB UpdateItem events on quota_global table 4. Verify each event includes user identity and solution_id correlation key 5. Attempt to delete a CloudTrail log object from the audit bucket (expect AccessDenied) | CloudTrail records S3 PutObject events for all 12 artifacts; DynamoDB quota modification events logged with actor sub; delete attempt returns AccessDenied (Object Lock WORM); log retention ≥ 365 days confirmed | High | Compliance | Security Engineer | Not Started | Not Executed | DDD §Compliance — SOC 2 CC7.2; DDD §Audit Logging; SOW §Security — Compliance and Auditing | Maps to SOC 2 CC7.2 System Monitoring control evidence
NFT-015 | Compliance | GuardDuty Threat Detection Active | Validate AWS GuardDuty is enabled and HIGH-severity findings route to the security SNS topic via EventBridge | GuardDuty detector ENABLED in us-west-2; EventBridge rule configured; SNS security topic with confirmed subscription | 1. Confirm GuardDuty detector status = ENABLED 2. Generate a test GuardDuty finding using the sample findings API (if available in region) 3. Verify EventBridge rule triggers on HIGH-severity finding 4. Verify SNS security topic delivers email notification within 5 minutes 5. Verify finding appears in CloudWatch alarm state | GuardDuty ENABLED; test finding triggers EventBridge rule; SNS email delivered within 5 minutes; CloudWatch alarm changes to ALARM state; zero HIGH or CRITICAL real findings in 72 hours post-deployment | High | Compliance | Security Engineer | Not Started | Not Executed | DDD §Compliance — SOC 2 CC7.2; DDD §Monitoring — SIEM Integration; IG §Monitoring Validation | Maps to SOC 2 CC7.2 and OWASP API10 Insufficient Logging

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
UAT-001 | Business Process | Marcus Patel — Pre-Sales Bundle Generation | Validate a Director-level pre-sales consultant can generate a complete 5-artifact presales bundle from a representative PREDICTif client brief using the CLI | UAT environment with Cognito credentials for Marcus Patel persona; amatra-cli installed; representative client brief prepared | 1. pip install amatra-cli in clean environment 2. amatra login with Marcus Patel UAT credentials 3. amatra generate --brief representative-brief.txt 4. Monitor progress with amatra status until COMPLETE 5. amatra artifacts download all 5 presales artifacts 6. Review solution-briefing PPTX SOW DOCX discovery-questionnaire LOE and infrastructure-costs against EO Framework quality standards 7. Verify CLI surfaces per-phase token spend | 5 presales artifacts downloaded and reviewable in Office applications; artifacts meet EO Framework quality standards per Marcus Patel's review; generation completes in < 60 minutes; CLI usable by a non-engineer consultant | Critical | UAT | Marcus Patel | Not Started | Not Executed | SOW §UAT — Marcus Patel pre-sales workflow scenarios; DDD §Success Criteria; IG §TRN-006 Solution Generation | Formal UAT sign-off required — SOW Deliverable #23
UAT-002 | Business Process | Daniel Park — Delivery Artifacts Review | Validate delivery artifact quality for a Head of Delivery Operations reviewing 6 delivery artifacts against EO Framework standards | UAT environment; complete solution generation run available; Daniel Park UAT credentials | 1. Access completed solution via amatra solutions list and amatra status 2. Download all 6 delivery artifacts: detailed-design implementation-guide test-plan runbook change-management as-built 3. Review each artifact for EO Framework schema compliance and content quality 4. Verify Terraform IaC bundle passes terraform validate 5. Confirm GitHub branch contains all 12 artifacts 6. Confirm as-built documentation matches deployed architecture | 6 delivery artifacts meet Daniel Park's quality bar for delivery engagements; terraform validate passes in CI; GitHub branch complete with all 12 artifacts; as-built documentation accurate and complete | Critical | UAT | Daniel Park | Not Started | Not Executed | SOW §UAT — Daniel Park delivery workflow scenarios; DDD §Success Criteria; IG §Phase 3 — UAT Coordination | Formal UAT sign-off required — SOW Deliverable #23
UAT-003 | Business Process | CTO Production Gate — Cognito Activation and Security Review | Validate CTO can activate production Cognito User Pool confirm MFA enforcement verify quota reset behaviour and review security event visibility in CloudWatch | Production Cognito User Pool staged for activation pending CTO sign-off; CTO AWS console read access; CloudWatch security dashboard available | 1. CTO reviews Cognito User Pool design against approved architecture spec 2. CTO activates production Cognito User Pool (providing formal sign-off in RAID log) 3. Verify MFA eligibility is configured on the User Pool 4. Execute a quota reset test in staging and walk CTO through the procedure 5. CTO reviews CloudWatch security dashboard: GuardDuty findings CloudTrail API events Cognito auth failure alarms 6. CTO confirms security event visibility meets governance requirements | CTO provides formal written sign-off in RAID log; Cognito production User Pool ACTIVE; MFA policy confirmed; CloudWatch security visibility accepted; CTO satisfied with audit trail completeness | Critical | UAT | CTO | Not Started | Not Executed | SOW §UAT — CTO production gate scenario; DDD §Security — Identity & Access Management; SOW §Deliverables — #4 CTO Sign-Off | Formal UAT sign-off required — SOW Deliverable #23
UAT-004 | Business Process | 90% Effort Reduction Demonstration | Validate the platform reduces per-engagement consultant effort from the 6–10 hour baseline to under 1 hour as claimed in the SOW success metrics | UAT environment with UAT-001 scenario results; Marcus Patel available to review; time tracking in place | 1. Time the complete workflow from amatra generate submission to artifact download and review 2. Have Marcus Patel review all 12 artifacts for quality acceptability 3. Record total human effort time (excluding generation compute time) 4. Compare against 6–10 hour manual baseline 5. Document any artifact requiring human rework and estimated rework time | Total human effort (generate + review + any rework) < 1 hour; at least 90% effort reduction vs 6–10 hour baseline confirmed by Marcus Patel; all 12 artifacts reviewed and accepted without major rework | Critical | UAT | Marcus Patel | Not Started | Not Executed | SOW §Success Metrics — 90% effort reduction; Solution Briefing §Business Opportunity — Success Criteria | Executive sponsor demonstration (Deliverable #31) anchor metric
UAT-005 | User Interface | CLI Usability — Consultant Persona | Validate the 14-subcommand CLI is intuitive and usable for a non-engineer pre-sales consultant without referring to documentation | amatra-cli installed; Cognito credentials for a non-engineer consultant UAT persona; representative brief available | 1. Ask a non-engineer consultant persona to install CLI and log in without assistance 2. Have them generate a solution using amatra generate 3. Have them check status with amatra status 4. Have them download artifacts with amatra artifacts download 5. Have them check quota with amatra quota status 6. Collect usability feedback including time-to-first-generation | Consultant generates first solution within 30 minutes of CLI install without escalating to IT support; all key subcommands usable without reading full documentation; error messages are descriptive and actionable | High | UAT | Business User | Not Started | Not Executed | DDD §Technology Stack — CLI Distribution; IG §TRN-005 CLI Installation; SOW §Deliverables — #11 Complete CLI Package | Target: time-to-first-generation < 30 min per training success metric
UAT-006 | Business Process | Quota Visibility and Governance | Validate that a pre-sales manager can monitor per-user and global quota utilisation and understand the monthly reset cycle | UAT environment; admin Cognito credentials; multiple test users with varying quota usage | 1. Run amatra quota status to view personal quota usage 2. Call GET /api/v1/admin/usage to view global pool and per-user top-10 utilisation 3. Verify monthly reset date is visible in output 4. Simulate a quota exhaustion scenario (user at 10/10) 5. Confirm clear HTTP 429 message is returned and quota counter not exceeded | Quota usage visible via CLI and API with correct values; monthly reset date shown; HTTP 429 message clearly explains quota exhaustion; global pool counter accurate; admin route returns per-user top-10 list | High | UAT | Marcus Patel | Not Started | Not Executed | DDD §API Design — GET /api/v1/quota and GET /api/v1/admin/usage; SOW §Success Metrics — Zero quota overruns | Governance requirement from SOW — no quota overruns at go-live
UAT-007 | Business Rules | Artifact Quality — EO Framework Compliance | Validate that all 12 generated artifacts comply with EO Framework schema standards and meet PREDICTif's quality bar for client-ready output | Complete 12-artifact solution bundle from UAT-001 available; EO Framework artifact quality checklist | 1. Apply EO Framework format-check validation to all 12 raw markdown/CSV artifacts 2. Open all converted Office documents (DOCX PPTX XLSX) in Microsoft Office 3. Review content quality for coherence client specificity and accuracy vs the source brief 4. Check that no placeholder text or template variables remain 5. Verify SOW and solution-briefing reference correct client name (PREDICTif) and project details | All 12 artifacts pass EO Framework format-check; all converted Office files open without errors or corruption; no placeholder text in any artifact; content is client-specific and accurate; Marcus Patel and Daniel Park accept quality | Critical | UAT | Marcus Patel | Not Started | Not Executed | DDD §Data Architecture — Data Quality; SOW §Testing — Functional Validation; IG §Integration Test Success Criteria | EO Validator passed artifacts in FT-013 are the baseline — UAT reviews human quality judgment
UAT-008 | Business Process | Token Spend Transparency — CLI Status and Admin API | Validate that per-phase token usage is surfaced in the CLI status command and the admin API endpoint so managers can track Bedrock cost against the $5/solution target | Complete solution generation; AmatraPlatform/TokenUsage metrics emitting to CloudWatch; admin Cognito credentials | 1. Run amatra status --solution-id {id} after generation completes 2. Verify per-phase token counts displayed (phase breakdown by agent and model) 3. Call GET /admin/usage to see aggregate monthly token spend and estimated cost 4. Verify estimated per-solution cost shown is ≤ $5 5. Compare CLI-displayed spend vs CloudWatch AmatraPlatform/TokenCostUSD metric | CLI status shows per-phase token counts by model (Sonnet 4.6 vs Haiku 4.5); admin API returns monthly aggregate spend and per-user top-10; estimated per-solution cost ≤ $5; CLI values match CloudWatch custom metrics | High | UAT | Marcus Patel | Not Started | Not Executed | DDD §SLA Expectations — Per-Solution Bedrock Token Spend; SOW §Success Metrics — $5 per-solution target; IG §Token Usage Instrumentation | Financial governance visibility required by SOW
UAT-009 | Business Process | Green CloudWatch Metrics Baseline Certification | Validate the CloudWatch Operations and Cost dashboards display a certified green metrics baseline that confirms platform readiness for go-live | Full load test completed; monitoring layer deployed; CloudWatch dashboards populated with real data | 1. Open CloudWatch Operations dashboard amatra-operations-prod 2. Verify P99 Lambda latency widget shows green (within SLA) 3. Verify Lambda error rate widget shows < 1% 4. Verify EO Validator retry rate widget shows ≥ 95% resolved within 3 retries 5. Verify per-solution Bedrock cost widget shows ≤ $5 6. DevOps Engineer certifies dashboard green and records sign-off | All CloudWatch dashboard widgets green; P99 Lambda latency within SLA; error rate < 1%; retry success rate ≥ 95%; Bedrock spend ≤ $5/solution; DevOps Engineer formally signs off green baseline — go-live gate confirmed | Critical | UAT | DevOps Engineer | Not Started | Not Executed | DDD §SLA Expectations; SOW §Success Metrics — Green CloudWatch metrics baseline; IG §Phase 3 Success Criteria — Green CloudWatch baseline | SOW Milestone M6 gate — must be green before go-live declared
UAT-010 | Acceptance | Executive Sponsor Demonstration Readiness | Validate the platform is ready for Sarah Lin (CRO) executive sponsor demonstration confirming 90% effort reduction and end-to-end generation under 60 minutes | Production platform deployed and go-live declared; demonstration environment prepared; all UAT-001 through UAT-009 passed | 1. Prepare demonstration environment with fresh user credentials 2. Rehearse full demonstration flow: login → generate → status → download → review artifacts 3. Confirm generation of a representative solution completes in < 60 minutes 4. Verify all 12 artifacts are client-presentable quality 5. Confirm CLI pip install works in a clean environment on the demo machine 6. Verify GitHub repository shows committed artifacts for demo solution | Demonstration rehearsal completes successfully; full generation under 60 minutes confirmed; all 12 artifacts client-presentable; GitHub repository shows committed artifacts; Sarah Lin demonstration package (Deliverable #31) ready | Critical | UAT | Engagement Lead | Not Started | Not Executed | SOW §Success Metrics — Executive sponsor demonstration; SOW §Deliverables — #31 Executive Sponsor Demonstration Package; Solution Briefing §Slide 2 — Success Criteria | Hard deadline end of April 2026 — non-negotiable per SOW