## Slide 1
Project Closeout
ANP Streaming AI Mood & Recommendation API
Jonas Bull | 2025-07-18

## Slide 2
Slide 2: Executive Summary
Project Duration: 6 weeks, delivered on schedule
Budget: $15,000 professional services, fully offset by AWS credits
Go-Live Date: End of Week 5 as planned in SOW
Quality: Zero critical defects at Production go-live
Classification Accuracy: 92% exceeding ≥90% SOW target
API Latency: 1.4s p95 — below the ≤2s SLA target
AWS Funding: $16,500 in credits applied; net Year 1 cost $1,751
Deliverables: All 20 SOW deliverables accepted by ANP Streaming
Integration: FlutterFlow calling Production API with zero frontend changes
Hypercare: 2-week post-go-live support period commenced on schedule
ANP Streaming AI Mood & Recommendation API
Notes: *Talking Points:*
- Open with confidence — the engagement was delivered on time, on budget, and on scope.
- ANP Streaming's net Year 1 investment is just $1,751 — infrastructure only — against a $17,400+ list value. That is a 90% cost reduction through AWS credits.
- The 92% classification accuracy surpasses the contractual 90% threshold, validated across 200+ faith-based lyric and transcript samples.
- API Gateway p95 latency of 1.4 seconds for both endpoints beats the ≤2s SLA target by a comfortable margin.
- All 20 formal deliverables enumerated in the SOW have been submitted, reviewed, and accepted within the 3-business-day window.
*Budget Detail:*
- Professional Services list: $15,000 — fully offset by $15,000 AWS Partner Services Credit ($10K APN + $5K APF).
- Cloud infrastructure Year 1: $2,903 list; $1,403 net after $1,500 MAP credit.
- Support & Maintenance: $348/year for AWS Developer Support.
- Total Year 1 net: $1,751. 3-year total: $8,254.
*Presales Alignment:*
- Budget figures match SOW Investment Summary exactly.
- Timeline matches SOW 6-week delivery commitment.
- All success metrics from SOW Section "Success Metrics" have been met or exceeded.

## Slide 3
Slide 3: Solution Architecture
ANP Streaming AI Mood & Recommendation API
AI & Inference Layer
  Amazon Bedrock for LLM mood classification
  Auto-tagger Lambda on S3 upload events
  92% accuracy on faith-based content
Serverless API Platform
  API Gateway with key auth and throttling
  Lambda: Classifier, Recommender, Auto-Tagger
  DynamoDB catalog moods and user history
Security & Observability
  IAM least-privilege per Lambda function
  Secrets Manager for all credentials
  CloudWatch dashboards, alarms, and logs
Notes: *Talking Points:*
- Walk through the architecture from the FlutterFlow client at the top, down to the AWS backend.
- The solution is 100% serverless — no EC2, no containers, no servers for ANP to manage.
- Three Lambda functions handle all compute: Classifier, Recommender, and Auto-Tagger.
- Bedrock on-demand inference means ANP pays only for tokens consumed — no idle GPU costs.
*Technical Details:*
- API Gateway exposes two routes: POST /classify and GET /recommend.
- POST /classify → Classifier Lambda → Amazon Bedrock (foundation model) → mood label + confidence score.
- GET /recommend → Recommender Lambda → DynamoDB query (user history + catalog mood tags) → ordered playlist.
- S3 ObjectCreated event → Auto-Tagger Lambda → Bedrock classification → DynamoDB catalog-moods write.
- DynamoDB: anp-catalog-moods (PK: content_id) and anp-user-history (PK: user_id, SK: played_at).
- CloudWatch alarms: Lambda error rate >1%, API Gateway p95 >2s, both with SNS email notifications.
*Presales Alignment:*
- Architecture matches Solution Briefing Slide 4 and SOW Architecture & Design section exactly.
- Services in scope: API Gateway, Lambda (×3), Bedrock, DynamoDB, S3, Cognito, Secrets Manager, CloudWatch, CDK/CloudFormation.
- No services added beyond presales scope. Amazon Personalize and Comprehend were evaluated in Phase 1 and Bedrock was selected as the sole inference engine per the ADR.
- Architecture diagram is inherited from pre-sales assets; no diagram recreation needed.

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Architecture Design & Decision Record | AWS design decisions and API schemas | `/delivery/detailed-design.md`
Infrastructure as Code (CDK/CloudFormation) | Repeatable environment provisioning | `/delivery/scripts/cdk/`
POST /classify & GET /recommend Lambdas | Bedrock-integrated mood and playlist API | `/delivery/scripts/lambda/`
Auto-Tagging Batch Lambda Pipeline | Mood-tags new catalog uploads automatically | `/delivery/scripts/lambda/auto-tagger/`
Test Plan & Results Report | Test cases, execution, UAT sign-off | `/delivery/test-plan.csv`
Developer-Facing API Reference | Endpoint specs, auth, request/response | `/delivery/implementation-guide.md`
Operational Runbook | Monitoring, alarm response, maintenance | `/delivery/runbook.md`
Knowledge Transfer Session (recorded) | Architecture walkthrough, operations demo | `/delivery/training/kt-recording.mp4`
ANP Streaming AI Mood & Recommendation API
Notes: *Talking Points:*
- All 20 SOW deliverables have been submitted and accepted. This slide highlights the 8 most operationally significant artifacts.
- The full deliverable register (SOW Table, items 1–20) is available in the Project Closeout Report.
- Every artifact has been reviewed and accepted by either Lilly Goyah or the ANP Technical Contact within the 3-business-day review window.
*Deliverable Details:*
- Detailed Design document covers: API Gateway configuration, Lambda function design, Bedrock prompt engineering, DynamoDB schema, security controls, and CloudWatch observability setup.
- IaC CDK templates cover both Dev and Production environments — fully parameterized for environment-specific config.
- API Reference documentation is developer-facing: covers both endpoints, API key auth, Cognito JWT flow, request/response schemas, HTTP error codes, and FlutterFlow-compatible example calls.
- Runbook covers: CloudWatch alarm investigation, Lambda cold-start tuning, DynamoDB capacity mode adjustment, Secrets Manager rotation, and full environment re-deployment from IaC.
- The knowledge transfer session (approx. 2 hours) was recorded and the MP4 is included in the handover package.
*SOW Items Not Listed Above (also delivered):*
- Project Kickoff Deck & Meeting Notes (Week 1)
- Firebase Catalog Assessment Report (Week 1)
- Discovery Summary Report (Week 2)
- Provisioned Dev and Production AWS Environments (Weeks 2 and 5)
- Security Baseline Configuration (Week 2)
- Detailed Architecture Specification & API Schemas (Week 3)
- CloudWatch Dashboards & Alerting (Week 4)
- Project Closeout Report (Week 6)

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Test cases executed: 100% of plan
  Functional test pass rate: 97% (target: ≥95%)
  Critical defects at go-live: 0
  Security test pass rate: 100%
  UAT sign-off: completed by ANP contact
Performance Metrics
  Classification accuracy: 92% (target: ≥90%)
  API p95 latency: 1.4s (target: ≤2s)
  Peak concurrent users tested: 50
  CloudWatch alarms validated in Dev: 100%
  DynamoDB PITR restore test: passed
ANP Streaming AI Mood & Recommendation API
Notes: *Talking Points:*
- Quality was embedded at every phase — not just tested at the end.
- Functional testing ran in Week 5 against labeled faith-based lyric and transcript samples, meeting the ≥95% pass rate acceptance criterion.
- Zero critical defects at go-live is the most important quality indicator for executive stakeholders.
- All five security test cases from the test plan passed at 100% — API key enforcement, JWT validation, HTTPS-only access, IAM policy scope, and Secrets Manager hygiene.
*Detailed Metrics:*
- Functional test plan: 40+ test cases across POST /classify (valid, empty, oversized, non-English, ambiguous) and GET /recommend (with history, cold start, unknown user, unsupported mood, missing param).
- Performance testing used Artillery to simulate 10 and 50 concurrent users over 5-minute runs. p95 latency of 1.4s at 50 concurrent users beats the ≤2s SLA.
- Lambda provisioned concurrency was not required — warm Lambda cold-start times were acceptable at launch-stage traffic.
- Auto-Tagger pipeline validated: new S3 upload tagged in DynamoDB within 60 seconds in all test cases.
- DynamoDB PITR restore test: anp-catalog-moods table restored to point-in-time in Dev; data integrity confirmed.
- Lambda re-deployment test: all three functions deleted and redeployed from CDK in Dev; functionality restored in under 10 minutes.
*Presales Alignment:*
- 92% classification accuracy exceeds the ≥90% SOW success metric.
- 1.4s p95 latency exceeds the ≤2s SOW success metric.
- Both endpoints callable from FlutterFlow with zero frontend changes — SOW integration compatibility criterion met.

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Mood Classification Accuracy | ≥90% | 92% | Reliable auto-tagging from day one
API Response Latency (p95) | ≤2s | 1.4s | Snappy in-app experience
Manual Curation Effort | Eliminated | Eliminated | Zero tagging per new upload
Catalog Items Auto-Tagged | 100% of uploads | 100% pipeline live | Full catalog enriched at launch
AWS Partner Credits Applied | $15,000 | $16,500 | Net Year 1 cost only $1,751
Professional Services Net Cost | $0 (credits) | $0 | 100% offset via AWS funding
Personalized Playlist API | Live in 6 weeks | Live in Week 5 | 1 week ahead of final deadline
FlutterFlow Integration | Zero frontend changes | Zero changes made | Seamless drop-in integration
ANP Streaming AI Mood & Recommendation API
Notes: *Talking Points:*
- Lead with the accuracy and latency wins — these are the technical proof points that the solution does what it was designed to do.
- The elimination of manual curation is a strategic benefit: as the catalog grows, the auto-tagging pipeline scales at near-zero cost without additional ANP team effort.
- $16,500 in AWS credits applied (vs. $15,000 planned) — the MAP infrastructure credit of $1,500 was approved in addition to the $15,000 PS credit.
- The recommendation API being live at end of Week 5 (vs. Week 6 final deadline) demonstrates delivery discipline and gives ANP a week of early hypercare runway.
*ROI Calculation:*
- Estimated manual tagging effort saved: ~3 hours per new upload × estimated 20 uploads/month = 60 hours/month.
- At a conservative $25/hour content-ops rate: $1,500/month = $18,000/year in avoided manual labor.
- Year 1 net infrastructure investment: $1,751. Payback period: approximately 5 weeks.
- 3-year ROI: $54,000 in avoided curation cost against $8,254 total investment = ~6.5x return (infrastructure-only comparison; PS fully credited).
*Future Benefit Projections:*
- Session length uplift expected as personalized playlists drive deeper listening (comparable faith-based platforms have seen 20–35% session length increases post-personalization).
- App store rating improvement is a lagging benefit — expected to materialize within 60–90 days of user adoption at scale.

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Serverless-first approach removed infra bottleneck
  Bedrock LLM fallback ensured accuracy from day one
  IaC CDK templates enabled Dev→Prod in under 2 hours
  Firebase catalog export completed ahead of Week 2
  Early API contract sign-off prevented scope creep
Challenges Overcome
  Bedrock model selection required Phase 1 benchmarking
  Cold-start latency tuned via Lambda memory sizing
Recommendations
  Phase 2: add Amazon Personalize for collaborative filtering
  Upgrade to AWS Business Support as user base grows
  Enable DynamoDB Global Tables for multi-region resilience
  Schedule quarterly Bedrock prompt accuracy reviews
  Expand auto-tagger to audio transcription via Transcribe
ANP Streaming AI Mood & Recommendation API
Notes: *Lessons Learned Detail:*
- Serverless-first: eliminating EC2/container provisioning saved approximately 1.5 days of environment setup effort vs. a traditional containerized approach, directly enabling the 6-week delivery.
- Bedrock model selection: benchmarking Anthropic Claude 3 Haiku vs. Titan Text Lite against 100 labeled faith-based samples in Week 1 was critical — Claude 3 Haiku achieved 92% accuracy vs. 84% for Titan. This Phase 1 investment paid dividends in Phase 2 build confidence.
- Cold-start: Classifier Lambda memory tuned from 512 MB to 1024 MB; p95 cold-start dropped from 2.8s to 0.9s. Provisioned concurrency was not needed at current volumes but is documented in the runbook for future traffic growth.
- Firebase export: ANP's technical contact delivered the S3 catalog export 2 days ahead of the Week 2 deadline, enabling early Bedrock benchmarking. This is a best practice to replicate on future data-dependent engagements.
*Recommendations Roadmap:*
- Phase 2 (Personalize): Amazon Personalize would add true collaborative filtering ("users who listened to X also liked Y"), complementing the current mood-based approach. Estimated 6-week add-on engagement. Expected benefit: 15–25% additional session length uplift.
- Business Support: at $100/month, AWS Business Support provides 1-hour P1 response and Trusted Advisor checks. Recommended once ANP reaches 1,000+ MAU.
- Global Tables: if ANP expands internationally, DynamoDB Global Tables provides multi-region active-active replication with no application code changes.
- Bedrock prompt reviews: the mood classification prompt should be reviewed quarterly against new catalog additions to ensure accuracy is maintained as ANP's content variety grows.
- Transcribe expansion: Amazon Transcribe could auto-generate transcripts for new podcast uploads, feeding the existing auto-tagger pipeline without manual transcript creation.

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 6–8, Post Go-Live)
  Dedicated nClouds team on business-hours standby
  P1 Production outage: 4-hour response SLA
  P2 Degraded functionality: 8-hour response SLA
  P3 Queries and guidance: 1 business day response
  Daily async check-in via Slack/email
Transition to Self-Sufficiency (Week 8+)
  Full runbook and API reference handed over
  Knowledge transfer session recording delivered
  IaC CDK codebase in ANP's GitHub repository
  AWS Developer Support plan active for L1/L2
  Monthly performance review (first 90 days)
Escalation Contacts
  L1: jonas.bull@nclouds.com (Engagement Lead)
  L2: AWS Developer Support (Console case)
ANP Streaming AI Mood & Recommendation API
Notes: *Hypercare Coverage Details:*
- Hypercare runs from Production go-live through the end of Week 8 (2 calendar weeks).
- Coverage hours: Monday–Friday, 9am–5pm ANP's local time zone.
- Scope: bug fixes in delivered code, integration questions from the ANP FlutterFlow team, CloudWatch alarm investigation, Bedrock accuracy tuning. Does NOT cover new features or Firebase/FlutterFlow frontend changes.
- All issues are tracked in a shared issue log; weekly summary provided to Lilly Goyah.
*Transition Milestones:*
- Week 7: Confirm ANP technical contact can independently navigate CloudWatch dashboards and runbook.
- Week 7: Confirm ANP technical contact can rotate API keys and Secrets Manager secrets independently.
- Week 8: Final hypercare sign-off call with Jonas Bull and ANP technical contact.
- Week 8+: nClouds IAM access revoked; ANP operates the Production environment independently.
*Steady-State Operations:*
- ANP's primary operational touchpoints post-hypercare: CloudWatch dashboards (daily), CloudWatch Alarms (event-driven SNS email), monthly Cost Explorer review.
- Runbook covers all expected operational scenarios: alarm investigation, Lambda cold-start tuning, DynamoDB capacity mode adjustment, Secrets Manager rotation, and full IaC re-deployment.
- AWS Developer Support provides technical case management during steady-state; upgrade to Business Support recommended at scale.
*Response Time by Severity:*
- P1 (Production outage — all users impacted): 4-hour response, target resolution within 8 hours.
- P2 (Degraded functionality — partial impact): 8-hour response, target resolution within 24 hours.
- P3 (Queries, guidance, non-urgent): 1 business day response.

## Slide 9
Slide 9: Acknowledgments & Next Steps
Lilly Goyah for executive sponsorship and rapid decision-making
ANP Technical Contact for catalog access, testing, and UAT sign-off
nClouds delivery team for 6-week precision execution
AWS Partner team for funding approval enabling zero PS cost
This Week: Final documentation handover and hypercare kickoff
Next 30 Days: Hypercare support with daily async check-ins
Next Quarter: Phase 2 scoping — Amazon Personalize integration
ANP Streaming AI Mood & Recommendation API
Notes: *Acknowledgments — Specific Contributions:*
- Lilly Goyah: provided go/no-go decisions at every milestone within the 3-business-day review window, enabling the engagement to stay on schedule without a single day of stakeholder-caused delay.
- ANP Technical Contact: delivered the Firebase catalog S3 export 2 days ahead of schedule, participated actively in UAT with 20 real catalog items across 5 test users, and signed off on both the API reference documentation and the runbook.
- nClouds delivery team (Jonas Bull + ML/AI, Cloud, Security, QA, PM): executed a 6-phase delivery across 6 weeks with zero critical defects at go-live — a testament to the team's experience with serverless AI workloads.
- AWS Partner team: facilitated approval of both the $15,000 PS credit and the $1,500 MAP infrastructure credit — reducing ANP's net Year 1 investment from $17,400 to $1,751.
*Next Steps Timeline:*
- This week: Project Closeout Report and all remaining handover artifacts delivered; hypercare support period begins; nClouds development IAM access scoped down to read-only monitoring.
- Next 30 days: Hypercare period runs through Week 8. Jonas Bull remains the escalation contact. Daily async check-in via Slack/email.
- Next quarter: nClouds will prepare a Phase 2 proposal for Amazon Personalize collaborative-filtering integration and Amazon Transcribe podcast auto-transcription. Expected 6-week engagement of similar size and funding eligibility.
- Month 4 onward: Quarterly Bedrock prompt accuracy reviews recommended to maintain ≥90% classification accuracy as the ANP catalog grows.

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion. Have the detailed design document, test results report, and investment summary ready for reference.
- Backup detail available: architecture deep-dive, Bedrock model benchmark results, full test execution report, and the Phase 2 recommendation scope summary.
- Offer to schedule a follow-up 30-minute call to walk Lilly Goyah through the Phase 2 opportunity and associated AWS funding eligibility.
- Close on a positive note: ANP Streaming now has a production-grade, fully serverless AI capability delivering personalized mood-matched playlists and automated catalog enrichment — built in 6 weeks for a net Year 1 cost of under $2,000.
- Celebrate the partnership: this engagement is a model for how faith-based digital platforms can leverage AWS AI services and partner funding to compete with the personalization capabilities of much larger streaming platforms.
- Remind the team that the hypercare period is active — Jonas Bull is reachable at the contact above for any post-go-live questions through the end of Week 8.