## Cover
Project Plan
Generated: | June 09, 2026
Solution: | Tmp5Alxzcob
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 – Discovery & Design | Project Kickoff | 1 day | 2025-09-01 | 2025-09-01 | None | Amatra PM | Not Started
Phase 1 – Discovery & Design | AWS Account Read-Only Access Provisioning | 2 days | 2025-09-02 | 2025-09-03 | Project Kickoff | Cloud Engineer | Not Started
Phase 1 – Discovery & Design | Stakeholder Interviews (Platform Team & CISO) | 3 days | 2025-09-02 | 2025-09-04 | Project Kickoff | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | Current State Assessment – AWS Footprint & IAM | 5 days | 2025-09-03 | 2025-09-09 | AWS Account Read-Only Access Provisioning | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | Cloud Readiness & Gap Analysis | 5 days | 2025-09-08 | 2025-09-12 | Current State Assessment – AWS Footprint & IAM | Senior Security Engineer | Not Started
Phase 1 – Discovery & Design | ISO 27001 Control Mapping Matrix | 5 days | 2025-09-08 | 2025-09-12 | Stakeholder Interviews (Platform Team & CISO) | Senior Security Engineer | Not Started
Phase 1 – Discovery & Design | On-Premises IdP Federation Design Workshop | 1 day | 2025-09-15 | 2025-09-15 | Cloud Readiness & Gap Analysis | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | ITSM & SIEM Integration Assessment | 3 days | 2025-09-15 | 2025-09-17 | Cloud Readiness & Gap Analysis | Senior Solutions Engineer | Not Started
Phase 1 – Discovery & Design | Current State Assessment Report | 1 day | 2025-09-15 | 2025-09-15 | Cloud Readiness & Gap Analysis | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | Architecture Design Document | 10 days | 2025-09-16 | 2025-09-26 | ISO 27001 Control Mapping Matrix; ITSM & SIEM Integration Assessment | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | DR Topology & Network Design | 5 days | 2025-09-22 | 2025-09-26 | Architecture Design Document | Lead Solution Architect | Not Started
Phase 1 – Discovery & Design | Architecture Review Workshop (CISO Sign-Off Gate) | 1 day | 2025-09-29 | 2025-09-29 | Architecture Design Document | Amatra PM | Not Started
Phase 1 – Discovery & Design | Phase 1 Gate Review & Approval | 1 day | 2025-10-03 | 2025-10-03 | Architecture Review Workshop (CISO Sign-Off Gate) | Amatra PM | Not Started
Phase 2 – Build & Integrate | Control Tower Deployment (ap-southeast-2) | 5 days | 2025-10-06 | 2025-10-10 | Phase 1 Gate Review & Approval | Cloud Engineer | Not Started
Phase 2 – Build & Integrate | OU Hierarchy & Foundational Accounts Setup | 3 days | 2025-10-09 | 2025-10-13 | Control Tower Deployment (ap-southeast-2) | Cloud Engineer | Not Started
Phase 2 – Build & Integrate | IaC Module Library Development (Terraform) | 10 days | 2025-10-13 | 2025-10-24 | OU Hierarchy & Foundational Accounts Setup | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | Account Vending Machine (AFT) Deployment | 5 days | 2025-10-20 | 2025-10-24 | IaC Module Library Development (Terraform) | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | ITSM Change-Approval Workflow Integration | 5 days | 2025-10-20 | 2025-10-24 | Account Vending Machine (AFT) Deployment | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | SCP Guardrail Implementation | 5 days | 2025-10-27 | 2025-10-31 | OU Hierarchy & Foundational Accounts Setup | Senior Security Engineer | Not Started
Phase 2 – Build & Integrate | AWS Config Conformance Packs & Auto-Remediation | 5 days | 2025-10-27 | 2025-10-31 | SCP Guardrail Implementation | Senior Security Engineer | Not Started
Phase 2 – Build & Integrate | IAM Identity Center Federation (On-Prem IdP) | 5 days | 2025-11-03 | 2025-11-07 | Account Vending Machine (AFT) Deployment | Senior Security Engineer | Not Started
Phase 2 – Build & Integrate | Centralised Security Hub & GuardDuty Configuration | 5 days | 2025-11-03 | 2025-11-07 | AWS Config Conformance Packs & Auto-Remediation | Senior Security Engineer | Not Started
Phase 2 – Build & Integrate | SIEM Integration (EventBridge + Lambda Pipeline) | 3 days | 2025-11-03 | 2025-11-05 | Centralised Security Hub & GuardDuty Configuration | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | DR Baseline Deployment (ap-southeast-4) | 5 days | 2025-11-10 | 2025-11-14 | Control Tower Deployment (ap-southeast-2) | Cloud Engineer | Not Started
Phase 2 – Build & Integrate | Network Infrastructure (Transit Gateway & Direct Connect) | 5 days | 2025-11-03 | 2025-11-07 | OU Hierarchy & Foundational Accounts Setup | Cloud Engineer | Not Started
Phase 2 – Build & Integrate | Production Environment Onboarding (3 Environments) | 5 days | 2025-11-10 | 2025-11-14 | IAM Identity Center Federation (On-Prem IdP); SCP Guardrail Implementation | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | CI/CD GitOps Pipeline for IaC | 3 days | 2025-11-10 | 2025-11-12 | IaC Module Library Development (Terraform) | Senior Solutions Engineer | Not Started
Phase 2 – Build & Integrate | Configuration and Operations Guide | 3 days | 2025-11-13 | 2025-11-17 | Production Environment Onboarding (3 Environments) | Technical Writer | Not Started
Phase 3 – Testing & Validation | Test Plan Development | 3 days | 2025-11-18 | 2025-11-20 | Configuration and Operations Guide | QA Engineer | Not Started
Phase 3 – Testing & Validation | Functional & Guardrail Testing | 5 days | 2025-11-21 | 2025-11-27 | Test Plan Development | QA Engineer | Not Started
Phase 3 – Testing & Validation | SCP & Config Rule Validation | 3 days | 2025-11-24 | 2025-11-26 | Functional & Guardrail Testing | Senior Security Engineer | Not Started
Phase 3 – Testing & Validation | SIEM & Federation Integration Testing | 3 days | 2025-11-24 | 2025-11-26 | Functional & Guardrail Testing | Senior Solutions Engineer | Not Started
Phase 3 – Testing & Validation | ISO 27001 Compliance Validation | 5 days | 2025-11-27 | 2025-12-03 | SCP & Config Rule Validation | Senior Security Engineer | Not Started
Phase 3 – Testing & Validation | DR Failover Test (RTO/RPO Validation) | 2 days | 2025-11-27 | 2025-12-01 | DR Baseline Deployment (ap-southeast-4) | Cloud Engineer | Not Started
Phase 3 – Testing & Validation | User Acceptance Testing (UAT) | 5 days | 2025-12-01 | 2025-12-05 | ISO 27001 Compliance Validation | QA Engineer | Not Started
Phase 3 – Testing & Validation | Operational Runbook Suite | 5 days | 2025-12-01 | 2025-12-05 | Configuration and Operations Guide | Technical Writer | Not Started
Phase 3 – Testing & Validation | Knowledge Transfer Sessions (4 Sessions) | 5 days | 2025-12-08 | 2025-12-12 | Operational Runbook Suite | Lead Solution Architect | Not Started
Phase 3 – Testing & Validation | Administrator Training Sessions | 2 days | 2025-12-11 | 2025-12-12 | Knowledge Transfer Sessions (4 Sessions) | Lead Solution Architect | Not Started
Phase 3 – Testing & Validation | Platform Optimisation Roadmap | 2 days | 2025-12-11 | 2025-12-12 | User Acceptance Testing (UAT) | Lead Solution Architect | Not Started
Phase 3 – Testing & Validation | ISO 27001 Compliance Evidence Package | 2 days | 2025-12-08 | 2025-12-09 | ISO 27001 Compliance Validation | Technical Writer | Not Started
Phase 3 – Testing & Validation | UAT Sign-Off & Go-Live Approval (CISO Gate) | 1 day | 2025-12-10 | 2025-12-10 | User Acceptance Testing (UAT) | Amatra PM | Not Started
Phase 3 – Testing & Validation | Production Go-Live Execution | 1 day | 2025-12-11 | 2025-12-11 | UAT Sign-Off & Go-Live Approval (CISO Gate) | Cloud Engineer | Not Started
Phase 3 – Testing & Validation | Project Closeout Report | 1 day | 2025-12-15 | 2025-12-15 | Production Go-Live Execution | Amatra PM | Not Started
Hypercare (Weeks 17-24) | Hypercare Support – Week 17-18 | 2 weeks | 2025-12-22 | 2026-01-02 | Production Go-Live Execution | Cloud Engineer | Not Started
Hypercare (Weeks 17-24) | Hypercare Support – Week 19-20 | 2 weeks | 2026-01-05 | 2026-01-16 | Hypercare Support – Week 17-18 | Senior Security Engineer | Not Started
Hypercare (Weeks 17-24) | Hypercare Support – Week 21-22 | 2 weeks | 2026-01-19 | 2026-01-30 | Hypercare Support – Week 19-20 | Senior Solutions Engineer | Not Started
Hypercare (Weeks 17-24) | Hypercare Support – Week 23-24 | 2 weeks | 2026-02-02 | 2026-02-13 | Hypercare Support – Week 21-22 | Amatra PM | Not Started
Hypercare (Weeks 17-24) | Final Hypercare Handover & BAU Transition | 1 day | 2026-02-13 | 2026-02-13 | Hypercare Support – Week 23-24 | Amatra PM | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Project Kickoff Complete | 2025-09-01 | Phase 1 – Discovery & Design | All stakeholders aligned; RAID log established; AWS account access confirmed; project charter signed | Amatra PM | Not Started
MS-002 | Discovery & Assessment Sign-Off | 2025-09-15 | Phase 1 – Discovery & Design | Current state assessment complete; gap analysis accepted by Priya Nair and CISO; remediation scope confirmed | Lead Solution Architect | Not Started
MS-003 | Architecture Design Approved (CISO Gate) | 2025-10-03 | Phase 1 – Discovery & Design | Architecture Design Document signed off by CISO; ISO 27001 control mapping accepted; Phase 2 cleared to begin | Lead Solution Architect | Not Started
MS-004 | Landing Zone Live | 2025-10-24 | Phase 2 – Build & Integrate | Control Tower ACTIVE in ap-southeast-2; OU hierarchy established; log archive and audit accounts provisioned; AFT pipeline operational | Cloud Engineer | Not Started
MS-005 | Guardrails Enforced | 2025-10-31 | Phase 2 – Build & Integrate | SCPs active on all production OUs; no console access enforced; Config conformance packs deployed; ITSM workflow integrated | Senior Security Engineer | Not Started
MS-006 | Identity Federation Live | 2025-11-07 | Phase 2 – Build & Integrate | IAM Identity Center federated with on-premises IdP; shared credentials retired; permission sets assigned; Security Hub forwarding to SIEM validated | Senior Security Engineer | Not Started
MS-007 | Full Platform Live | 2025-11-17 | Phase 2 – Build & Integrate | All 3 production environments onboarded; DR baseline active in ap-southeast-4; SIEM and ITSM integrations validated; CI/CD pipeline operational | Senior Solutions Engineer | Not Started
MS-008 | UAT Sign-Off | 2025-12-10 | Phase 3 – Testing & Validation | CISO and platform team accept all controls; all functional test cases passed; no outstanding CRITICAL defects; ISO 27001 evidence package accepted | QA Engineer | Not Started
MS-009 | Production Go-Live | 2025-12-11 | Phase 3 – Testing & Validation | Governance platform fully operational; compliance evidence package delivered; DR failover validated RTO < 4h and RPO < 1h | Amatra PM | Not Started
MS-010 | Hypercare End & BAU Handover | 2026-02-13 | Hypercare (Weeks 17-24) | 8-week hypercare support period complete; all P1 and P2 items resolved; platform team self-sufficient; BAU handover signed off by Priya Nair and Rachel Moore | Amatra PM | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Amatra PM | Amatra Architect | Amatra Engineer | Amatra QA | Amatra Security | Client PM | Client Tech Lead | Client CISO
Project Kickoff & Governance Setup | A | C | I | I | I | R | C | I
Current State Assessment & Account Inventory | C | A | R | I | R | I | C | C
Cloud Readiness & Gap Analysis | C | A | R | I | R | I | C | C
ISO 27001 Control Mapping Matrix | I | C | I | R | A | I | C | R
Architecture Design Document | I | A | C | I | R | I | C | C
Architecture Design Sign-Off (CISO Gate) | C | C | I | I | C | C | C | A
IaC Module Library Development (Terraform) | I | C | A | C | C | I | R | I
Control Tower Landing Zone Deployment | I | A | R | C | C | I | C | I
Account Vending Machine (AFT) Deployment | I | C | A | C | I | I | R | I
ITSM Change-Approval Workflow Integration | C | C | A | C | I | R | R | I
SCP Guardrail Implementation | I | C | R | I | A | I | C | R
AWS Config Rules & Auto-Remediation | I | C | R | I | A | I | C | C
IAM Identity Center Federation | I | C | R | I | A | I | R | C
Centralised Security Hub & GuardDuty Configuration | I | C | R | I | A | I | C | R
SIEM Integration (Security Hub to On-Prem SIEM) | I | C | A | C | R | I | R | C
DR Baseline Deployment (ap-southeast-4) | I | A | R | C | C | I | C | I
Network Infrastructure (Transit Gateway & Direct Connect) | I | A | R | I | C | I | R | I
Production Environment Onboarding (3 Environments) | C | C | A | C | C | R | R | R
CI/CD GitOps Pipeline for IaC | I | C | A | C | I | I | R | I
Test Plan Development | C | C | R | A | C | I | C | I
Functional & Guardrail Testing | C | C | R | A | R | I | C | C
ISO 27001 Compliance Validation | I | C | C | A | R | I | C | R
DR Failover Test (RTO/RPO Validation) | I | A | R | C | C | I | C | I
User Acceptance Testing (UAT) | C | C | I | R | C | R | C | A
UAT Sign-Off Gate | A | C | I | R | C | R | C | A
Knowledge Transfer & Training Sessions | C | A | R | I | C | R | C | I
Operational Runbook Suite | C | C | R | I | C | R | A | I
ISO 27001 Compliance Evidence Package | I | C | C | R | A | I | C | R
Platform Optimisation Roadmap | C | A | C | I | C | I | C | I
Project Closeout & BAU Handover | A | C | I | I | I | R | C | C
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff Workshop | Once | All stakeholders — Amatra team and Contoso Financial (James Wu; Priya Nair; Rachel Moore; CISO) | Launch project; align on scope; RACI; governance and RAID log; confirm access and Week 1 actions | Amatra PM | 2025-09-01 (Half day)
Weekly Status Call | Weekly | Cloud CoE Lead (Priya Nair); Amatra PM; Amatra team leads | Review progress against plan; discuss blockers; decisions and risks; update RAID log | Amatra PM | Mondays 10:00 AEST
Architecture Review Workshop | Once | Priya Nair; CISO; Lead Solution Architect; Senior Security Engineer | Review and approve Architecture Design Document and ISO 27001 control mapping; gate for Phase 2 commencement | Lead Solution Architect | 2025-10-02 (3 hours)
Phase Gate Review | End of each phase | Priya Nair; Rachel Moore; CISO; Amatra PM | Review phase completion criteria; accept deliverables; approve next phase commencement | Amatra PM | 2025-10-03; 2025-11-17; 2025-12-12
Fortnightly Executive Steering | Fortnightly | James Wu (CTO); Rachel Moore; Amatra PM | Report milestone progress; escalate risks or scope changes; seek executive decisions | Amatra PM | Fortnights — Fridays 09:00 AEST
UAT Facilitation Sessions | Daily during Weeks 14-15 | Priya Nair; Platform Engineers; QA Engineer; Amatra facilitation | Execute UAT scenarios; log defects; obtain CISO sign-off on acceptance criteria | QA Engineer | 2025-12-01 to 2025-12-10 (2 hours/day)
Go-Live Readiness Review | Once | Priya Nair; CISO; Rachel Moore; Amatra PM; Cloud Engineer | Present UAT results and go-live readiness checklist for CISO and PM sign-off | Amatra PM | 2025-12-10 (1 hour)
Knowledge Transfer Sessions (4 sessions) | Once per session | Priya Nair; Platform Engineers; CISO (Sessions 2-4) | Hands-on training on IaC pipeline; guardrail management; Security Hub; IAM Identity Center | Lead Solution Architect | 2025-12-08 to 2025-12-12
Hypercare Weekly Check-In | Weekly during hypercare | Priya Nair; Rachel Moore; Amatra PM; on-call Engineer | Review open P1/P2 hypercare items; guardrail tuning; regulatory review readiness | Amatra PM | Wednesdays 10:00 AEST
P1 Incident Escalation | As required | Priya Nair; CISO; Amatra PM; Cloud Engineer | Notify and resolve Priority 1 incidents (platform outage or compliance-blocking issue) during hypercare | Cloud Engineer | Within 2 business hours of detection
Project Closeout Meeting | Once | James Wu; Priya Nair; Rachel Moore; CISO; Amatra PM | Formal project closure; confirm BAU handover; present lessons learned and optimisation roadmap | Amatra PM | 2026-02-13 (1 hour)