## Cover
Test Plan
Generated: | June 05, 2026
Solution: | Tmpnaegu_A5
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
FT-001 | Unit | Cognito JWT Issuance | Validate that the Cognito User Pool issues a valid JWT access token and refresh token on successful authentication | Cognito User Pool deployed; test consultant account created | 1. Invoke auth login via CLI PKCE flow 2. Capture JWT access token 3. Decode and inspect token claims 4. Verify access token expiry is 1 hour 5. Verify refresh token expiry is 30 days | JWT access token issued with correct claims; access expiry 1 hour; refresh token expiry 30 days | Critical | Dev | Developer | Not Started | Not Executed | DD-Security-IAM; IG-Phase1-1.2 | Test consultant and admin roles separately
FT-002 | Unit | JWT Authentication Rejection | Validate API Gateway rejects requests with invalid or missing JWT tokens | API Gateway deployed with JWT Cognito authoriser | 1. Send request to /api/v1/solutions with no Authorization header 2. Send request with an expired JWT 3. Send request with a tampered JWT payload 4. Send request with an unsigned JWT | All three unauthorized attempts return HTTP 401; no Lambda invocation occurs | Critical | Dev | Developer | Not Started | Not Executed | DD-Security-IAM; IG-Security-Identity | Cover all three rejection scenarios per SOW security testing scope
FT-003 | Unit | DynamoDB Quota Counter Initialisation | Validate that the global quota counter is correctly initialised to zero for the current month | DynamoDB quotas table deployed; no prior counter entry for current month | 1. Run initialisation script for GLOBAL partition key 2. Query quotas table for GLOBAL + current month_key 3. Attempt to initialise again to verify idempotency (condition expression) | Counter exists with value 0; second put-item is rejected by condition expression; no duplicate entries | High | Dev | Developer | Not Started | Not Executed | DD-DataArch-DataModel; IG-AppConfig-DynamoDB | Use IG Section Application Configuration script verbatim
FT-004 | Unit | Input Validation — Missing Required Fields | Validate Agent 0 (Input Validator) rejects a client brief missing required fields | Agent 0 deployed in AgentCore Runtime; test brief with missing fields prepared | 1. Submit brief with missing solution_name field 2. Submit brief with missing client_name field 3. Submit brief with empty discovery questionnaire 4. Verify DynamoDB solution state set to FAILED_VALIDATION | All three briefs are rejected with actionable error messages; solution state is FAILED_VALIDATION; no generation agents invoked | Critical | Dev | QA Engineer | Not Started | Not Executed | DD-SolArch-Component; DD-DataArch-DataFlow | Validate no token spend occurs on invalid inputs
FT-005 | Integration | JWT-Authenticated API Health Check | Validate the /api/v1/health endpoint returns 200 with DynamoDB and S3 connectivity status using a valid JWT | API Gateway and all Lambda route handlers deployed; valid JWT available | 1. Send GET /api/v1/health with valid Bearer JWT 2. Inspect response body for status and service fields 3. Send GET /api/v1/health without JWT to confirm 401 not enforced on health route | Authenticated request returns HTTP 200 with body containing status:healthy and dynamodb:connected and s3:connected; unauthenticated request also returns 200 (health is unauthenticated per design) | High | Dev | QA Engineer | Not Started | Not Executed | DD-Integration-API; IG-Phase1-1.3 | Matches IG Phase 1 step 1.3 expected output
FT-006 | Integration | DynamoDB Atomic Quota Enforcement | Validate that concurrent generation requests enforce the per-user 10/month quota using atomic conditional writes | DynamoDB quotas table deployed; test consultant user created; quota counter at zero | 1. Submit 15 simultaneous generate requests for the same test user 2. Monitor HTTP response codes 3. Query quotas table for final counter value 4. Verify no race condition allowed more than 10 successes | Exactly 10 requests succeed with HTTP 202; exactly 5 requests return HTTP 429; DynamoDB counter equals 10; no race condition bypass observed | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Integration-Msg; IG-Integration-Quota | Matches IG quota enforcement test: 15 requests → 10 success + 5 x 429
FT-007 | Integration | Per-Artifact Validation Loop — Format Check | Validate the EO Validator agent applies deterministic format-check rules and triggers up to 3 retries on failure | All five agents deployed in AgentCore Runtime; known-bad artifact prepared in S3 | 1. Place a known-bad artifact (missing required H1 section) in the staging S3 bucket 2. Invoke EO Validator agent against this artifact 3. Verify retry count increments in DynamoDB artifact_statuses map 4. Confirm failure state after 3 retries 5. Place known-good artifact and verify immediate pass | Known-bad artifact triggers up to 3 retries; DynamoDB retry_count reaches 3 before final FAILED status; known-good artifact passes on first attempt with PASSED status | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-SolArch-Component; DD-SolArch-Patterns | Test both known-good and known-bad fixtures per DD format-check design
FT-008 | Integration | GitHub PAT Commit Pipeline | Validate the GitHub push Lambda retrieves the PAT from Secrets Manager and commits generated artifacts to the configured repository | GitHub repository provisioned; PAT stored in Secrets Manager; at least one artifact generated and stored in S3 | 1. Trigger GitHub push Lambda manually with a test solution_id 2. Verify PAT is retrieved from Secrets Manager (check CloudTrail for GetSecretValue) 3. Verify artifact files appear in GitHub repository with correct commit message format 4. Verify commit SHA is written to DynamoDB solutions table | Artifacts committed to GitHub; commit message contains solution_id and artifact_type; DynamoDB solutions.github_commit_sha populated; PAT not exposed in CloudWatch Logs | High | Integration | QA Engineer | Not Started | Not Executed | DD-Integration-External; IG-Phase2-GitHub | Commit message format: solution_id/<artifact_type>: generated by EO Validator
FT-009 | Integration | CLI Generate Subcommand — Presales Bundle | Validate the CLI generate subcommand produces all five presales artifacts end-to-end in the staging environment | All five agents operational; CLI pip package installed; representative brief available | 1. Run eoframework auth login 2. Run eoframework generate --brief representative-brief-001.json --env staging --wait 3. Monitor status until completion 4. Run eoframework artifact list for the solution 5. Download all five presales artifacts | CLI exits with success; all five presales artifacts (solution-briefing.md; statement-of-work.md; discovery-questionnaire.csv; infrastructure-costs.csv; level-of-effort-estimate.csv) are present; each passes EO Validator format-check | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Impl-Sequencing; IG-Phase2-2.3 | This is the Phase 2 exit gate per SOW Milestone M5
FT-010 | System | End-to-End 12-Artifact Bundle Generation | Validate the full twelve-artifact solution bundle is generated end-to-end via CLI and all artifacts pass EO Validator format-check and LLM quality-check | All five agents operational in staging; full platform deployed; representative client brief available | 1. Submit generation request via eoframework generate --wait 2. Poll status every 10 seconds until solution state is COMPLETE or PARTIAL 3. Run artifact list to enumerate all twelve artifact types 4. Verify each artifact in DynamoDB artifact_statuses shows PASSED 5. Confirm GitHub commit contains all twelve artifacts | All twelve artifact types present and show PASSED status; generation completes in under 60 minutes; GitHub commit contains all twelve files with correct commit messages; no artifact exhausts all 3 retries on a valid brief | Critical | Staging | QA Lead | Not Started | Not Executed | DD-Business-SuccessCriteria; IG-Integration-E2E | Primary Phase 3 exit gate per SOW; ties to SOW success metric ≤60 min E2E
FT-011 | System | Role-Based API Access Control | Validate that API route permissions are enforced per Consultant / Admin / Read-Only roles across all eleven routes | Cognito User Pool live with three test users (one per role); valid JWTs for each role | 1. As Consultant: call POST /api/v1/solutions (expect 202) 2. As Consultant: call GET /api/v1/admin/usage (expect 403) 3. As Admin: call GET /api/v1/admin/usage (expect 200) 4. As Admin: call POST /api/v1/admin/quota-override (expect 200) 5. As Read-Only: call POST /api/v1/solutions (expect 403) | Role enforcement matches DD Role Definitions table exactly; Consultant blocked from admin routes; Read-Only blocked from generate; Admin has full access | High | Staging | QA Engineer | Not Started | Not Executed | DD-Security-IAM-Roles; IG-Security-Identity | Test all three roles against all eleven routes systematically
FT-012 | Regression | Quota Counter Integrity After Month Rollover | Validate that the quota counter initialisation is re-executed at the start of each calendar month and does not carry over the previous month count | DynamoDB quotas table with a simulated prior-month entry; current-month entry absent | 1. Simulate month rollover by setting month_key to current month on the GLOBAL counter 2. Run the first generate request of the new month 3. Verify a new GLOBAL counter entry is created for the new month_key with counter starting from 1 4. Verify prior month entry is untouched | New month_key entry created with counter = 1; previous month entry preserved; no quota bypass from prior month bleed-over | High | Dev | QA Engineer | Not Started | Not Executed | DD-DataArch-DataModel; IG-AppConfig-DynamoDB | Critical regression risk at month boundary; run on first day of each month during hypercare

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
NFT-001 | Performance | End-to-End Generation Time at Target Throughput | Validate that the full twelve-artifact solution bundle is produced in under 60 minutes at 10 concurrent generation requests (200 solutions/month peak load) | Staging environment fully deployed; Locust load test scripts configured; representative briefs available | 1. Configure Locust for 10 concurrent users each submitting one generate request 2. Start load test and record submission timestamps 3. Poll solution status endpoints until all solutions reach terminal state 4. Calculate wall-clock elapsed time for each solution from submission to COMPLETE 5. Collect P50 and P95 elapsed time metrics | P95 end-to-end generation time ≤ 60 minutes; zero solutions fail all retries on valid representative briefs; no Lambda timeout errors observed in CloudWatch | Critical | Staging | QA Engineer | Not Started | Not Executed | DD-Business-SLA; SOW-Success-Metrics | SOW success metric: ≤60 min E2E for full 12-artifact bundle; validates cost < $5 per solution
NFT-002 | Performance | API Gateway P99 Latency — Synchronous Routes | Validate that synchronous API routes respond within the 3-second P99 latency target under load | API Gateway and Lambda deployed in staging; Locust configured for 100 concurrent API calls | 1. Configure Locust to send 100 concurrent GET /api/v1/solutions/{id} and GET /api/v1/auth/me requests 2. Run for 10-minute sustained load 3. Collect API Gateway P50; P95; P99 latency metrics from CloudWatch 4. Verify no 5xx errors during the test window | API Gateway P99 latency ≤ 3 seconds on synchronous routes; error rate < 1%; no Lambda cold-start timeouts observed | High | Staging | QA Engineer | Not Started | Not Executed | DD-Business-SLA; DD-Infra-Monitoring-Alerts | SOW SLA: API Gateway P99 ≤ 3 seconds; aligns with DD CloudWatch alarm threshold
NFT-003 | Performance | DynamoDB Quota Operation Latency | Validate that DynamoDB atomic quota conditional write operations complete within 50ms P99 under concurrent load | DynamoDB quotas table deployed On-Demand; quota counter at 0 for test user | 1. Execute 200 concurrent DynamoDB conditional write operations against the quotas table using boto3 2. Measure per-operation latency with timestamps 3. Compute P50; P95; and P99 latencies 4. Verify zero throttle events in CloudWatch | DynamoDB quota conditional write P99 latency < 50ms; zero ThrottledRequests in CloudWatch during the test | Medium | Staging | QA Engineer | Not Started | Not Executed | DD-Business-SLA; DD-Infra-Network | SOW SLA: DynamoDB quota op < 50ms P99; DynamoDB On-Demand auto-scales
NFT-004 | Performance | Per-Solution Bedrock Model Spend | Validate that the per-solution Bedrock model spend remains below $5 at 200 solutions/month steady-state throughput | Full generation pipeline deployed in staging; DynamoDB token usage tracking active; at least 10 solutions generated | 1. Generate 10 solutions using representative client briefs 2. Query DynamoDB solutions table for per-phase token_usage map for each solution 3. Calculate total estimated cost per solution from input/output token counts using Sonnet 4.6 and Haiku 4.5 pricing 4. Extrapolate to 200 solutions/month | Average per-solution Bedrock cost < $5; no single solution exceeds $10; token usage breakdowns available per agent in DynamoDB | High | Staging | QA Engineer | Not Started | Not Executed | DD-Infra-CostModel; SOW-Success-Metrics | SOW success metric: < $5 per solution at 200/month; key ROI validation
NFT-005 | Performance | Stress Test — Lambda Concurrency and Cold Starts | Identify Lambda cold-start behaviour and determine if provisioned concurrency is required for agent trigger functions | Agent trigger Lambda functions deployed with container images; CloudWatch X-Ray tracing enabled | 1. Scale Lambda concurrency to zero by waiting for idle period 2. Submit 5 simultaneous generate requests to force cold starts 3. Measure P99 duration on agent trigger Lambda functions 4. Evaluate if P99 duration exceeds 80% of 900-second timeout 5. If threshold exceeded enable provisioned concurrency and retest | Cold-start P99 duration < 720 seconds (80% of 900s timeout); if threshold is exceeded provisioned concurrency must be enabled and the test repeated to confirm resolution | Medium | Staging | QA Engineer | Not Started | Not Executed | DD-Infra-Compute; DD-Infra-HA | DD recommends evaluating provisioned concurrency if P99 > 80% of timeout; Phase 3 gate
NFT-006 | Security | JWT Penetration Testing — Token Tampering and Replay | Validate that expired; tampered; and unsigned JWT tokens are rejected by the API Gateway JWT Cognito authoriser on all eleven routes | Staging API Gateway deployed; valid and expired JWTs prepared for test; security testing tools configured | 1. Send a valid JWT to GET /api/v1/solutions — expect 200 2. Wait for access token to expire (or modify exp claim) — send same token — expect 401 3. Modify the JWT sub claim and send — expect 401 4. Strip the JWT signature and send — expect 401 5. Use a JWT issued by a different Cognito pool — expect 401 | All four unauthorized scenarios return HTTP 401; no Lambda function is invoked; CloudTrail logs show authoriser rejection for each attempt; no 200 responses for invalid tokens | Critical | Staging | Security Engineer | Not Started | Not Executed | DD-Security-IAM; IG-Security-Identity; SOW-Security-JWT | SOW security test: JWT auth penetration; aligns with IG Security Validation checklist
NFT-007 | Security | Quota Bypass Via Race Condition | Validate that the DynamoDB atomic conditional write prevents per-user quota bypass via concurrent batch requests | DynamoDB quotas table deployed; test user with counter at 8 (2 remaining); race condition test script prepared | 1. Send 20 simultaneous POST /api/v1/solutions requests using the same test user JWT 2. Verify total successful responses (HTTP 202) does not exceed 2 (the remaining quota) 3. Verify all remaining requests return HTTP 429 4. Query DynamoDB quotas table to confirm final counter value is exactly 10 | Maximum 2 solutions succeed regardless of concurrency; all remaining requests return HTTP 429; DynamoDB counter equals 10; zero quota bypass incidents | Critical | Staging | Security Engineer | Not Started | Not Executed | DD-Security-IAM; IG-Security-Quota; SOW-Security-Quota | SOW security test: quota bypass scenarios; zero bypass incidents is a go-live gate
NFT-008 | Security | GitHub PAT Exposure Validation | Validate that the GitHub Personal Access Token is not exposed in Lambda logs; CloudWatch Logs; or API response payloads | GitHub push Lambda deployed; PAT stored in Secrets Manager; at least one successful GitHub commit executed | 1. Trigger the GitHub push Lambda by completing a full generation 2. Inspect CloudWatch Logs for the eofw-{ENV}-fn-github-push log group for any PAT string 3. Inspect all API response payloads from /api/v1/solutions/{id} for any credential strings 4. Verify CloudTrail shows GetSecretValue call with correct requester identity (Lambda execution role only) | PAT string is absent from all CloudWatch Log entries; PAT absent from all API response payloads; CloudTrail GetSecretValue events show only the GitHub push Lambda execution role as requester | Critical | Staging | Security Engineer | Not Started | Not Executed | DD-Security-Secrets; IG-Security-Secrets; SOW-Security-PAT | SOW security test: Secrets Manager PAT protection; go-live gate per security test report
NFT-009 | Security | IAM Privilege Escalation and Wildcard Policy Review | Validate that no Lambda execution role contains wildcard IAM actions or resource ARNs using IAM Access Analyzer | All 17 Lambda IAM execution roles deployed; IAM Access Analyzer enabled in us-west-2 | 1. Run aws accessanalyzer list-findings for the account-level analyzer 2. Filter for ACTIVE findings 3. Manually inspect all 17 Lambda execution role IAM policies for wildcard * in Action or Resource 4. Verify S3 bucket public access block is enabled (all four settings) | IAM Access Analyzer reports zero active findings; no Lambda execution role contains wildcard Action or Resource ARN; S3 bucket public access block shows all four settings as true | Critical | Staging | Security Engineer | Not Started | Not Executed | DD-Security-IAM; IG-Security-IAM; IG-Security-Checklist | SOW least-privilege requirement; go-live gate; aligns with IG security quality gate
NFT-010 | Security | ECR Container Image Vulnerability Scan | Validate that the agent Docker image in ECR contains no CRITICAL CVE findings before production go-live | ECR repository with latest agent image deployed; Amazon Inspector ECR scanning enabled | 1. Trigger an Amazon Inspector scan on the latest agent image tag in ECR 2. Review scan findings for CRITICAL and HIGH severity CVEs 3. If CRITICAL findings exist remediate base image or dependency and rebuild 4. Confirm rescan shows zero CRITICAL findings | Zero CRITICAL CVE findings in the ECR agent image scan results; HIGH findings documented and accepted or remediated before go-live | High | Staging | Security Engineer | Not Started | Not Executed | DD-Security-Monitoring; IG-Security-Checklist; SOW-Security-Container | SOW security scope: ECR image scanning; CRITICAL findings block production go-live
NFT-011 | Reliability | API Availability — Lambda Error Rate Baseline | Validate that the platform maintains API availability ≥ 99.5% with Lambda error rate below the 1% alarm threshold during a sustained 24-hour observation window | All 17 Lambda functions deployed; CloudWatch alarms configured; staging environment receiving simulated load | 1. Submit 50 generate requests evenly spaced over a 24-hour period in staging 2. Monitor Lambda error rate CloudWatch alarm for the entire 24-hour window 3. Monitor API Gateway 5xx error rate 4. Calculate availability percentage from total invocations vs errors | Lambda error rate < 1% throughout the 24-hour window; API availability ≥ 99.5%; zero P1 CloudWatch alarms fire during the observation period | Critical | Staging | QA Engineer | Not Started | Not Executed | DD-Business-SLA; DD-Infra-Monitoring-Alerts | SOW success metric: API availability ≥ 99.5% monthly; CloudWatch alarm threshold: error rate > 1%
NFT-012 | Reliability | DynamoDB PITR Restore — RTO Validation | Validate that the DynamoDB Point-In-Time Recovery restore procedure completes within the 4-hour RTO target | DynamoDB PITR enabled on all four tables; test data present in solutions and quotas tables | 1. Record current timestamp (T0) 2. Delete a DynamoDB table row to simulate data loss 3. Initiate PITR restore to a point-in-time 1 hour prior to T0 4. Measure elapsed time from restore initiation to table availability 5. Validate data integrity of restored table against expected records | DynamoDB table restored to target point-in-time in < 4 hours; restored table data matches expected records; integrity validation script passes with zero mismatches | Critical | Staging | DevOps Engineer | Not Started | Not Executed | DD-Infra-DR; SOW-Testing-DR; IG-Phase3 | SOW RTO target: 4 hours; mandatory Phase 3 go-live gate per SOW go-live readiness checklist
NFT-013 | Reliability | CloudWatch Synthetics Canary — Continuous Availability | Validate that the CloudWatch Synthetics canary successfully polls /api/v1/health every 5 minutes and triggers a P1 alarm on consecutive failures | CloudWatch Synthetics canary deployed and running; SNS ops alerts topic with confirmed email subscription | 1. Verify canary is in RUNNING state 2. Inspect last 12 canary run results (1 hour) — expect all PASSED 3. Simulate a health check failure by temporarily disabling the health-check Lambda 4. Verify canary failure alarm fires after 2 consecutive failed runs 5. Restore health-check Lambda and verify alarm clears | Canary shows PASSED on all runs during normal operation; alarm fires within 10 minutes of 2 consecutive failures; SNS notification received by Daniel Park; alarm clears after Lambda restored | Critical | Staging | DevOps Engineer | Not Started | Not Executed | DD-Infra-HA; DD-Infra-Monitoring-Alerts; IG-Monitoring-Validation | DD CloudWatch Synthetics: every 5 minutes; P1 alarm on ≥2 consecutive failures
NFT-014 | Compliance | CloudTrail Audit Logging — API and S3 Data Events | Validate that CloudTrail captures all management events and S3 data events on the artifact bucket with the required fields | CloudTrail deployed with management events and S3 data events enabled; CloudTrail S3 bucket with Object Lock; at least one API call and one S3 PutObject executed | 1. Execute a generate request via CLI 2. Download a generated artifact (triggers S3 GetObject) 3. Query CloudTrail for events within the last 15 minutes 4. Verify management events include Lambda invocations with requester identity and source IP 5. Verify S3 data events include PutObject and GetObject on the artifact bucket | CloudTrail management events present with eventSource; eventTime; userIdentity.arn; and sourceIPAddress fields; S3 PutObject and GetObject data events present for artifact bucket; CloudTrail S3 bucket has Object Lock in COMPLIANCE mode | High | Staging | Compliance Officer | Not Started | Not Executed | DD-Security-Audit; SOW-Security-Compliance; IG-Security-Security | SOC 2 CC7.2; SOC 2 CC8.1 requirement; CloudTrail is an immutable WORM audit trail
NFT-015 | Compliance | DynamoDB Audit Events Retention and TTL | Validate that all platform API actions are logged to the audit_events DynamoDB table and that the 90-day TTL attribute is correctly set | DynamoDB audit_events table deployed with TTL enabled on the ttl attribute; several platform actions executed | 1. Execute five distinct API actions (generate; status; list; artifact download; admin usage) 2. Query audit_events table for the test user_id 3. Verify each action has a record with user_id; action; solution_id; timestamp; outcome; and source_ip fields 4. Verify each record has a ttl attribute set to current epoch + 90 days | All five actions are logged with required fields; TTL attribute is present and set to epoch timestamp approximately 90 days in the future; DynamoDB TTL setting is enabled on the table | High | Staging | Compliance Officer | Not Started | Not Executed | DD-Security-Audit; DD-DataArch-Governance; SOW-Security-Compliance | SOC 2 CC6.3; 90-day audit log retention per data governance policy

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
UAT-001 | Business Process | Full Presales Bundle Generation via CLI | Validate that a consultant can generate the complete five-artifact presales bundle from a representative client brief using the CLI generate subcommand with no human intervention in the generation loop | UAT environment fully deployed; representative client brief provided by Marcus Patel; CLI installed and authenticated on consultant laptop | 1. Login as a consultant user via eoframework auth login 2. Submit brief using eoframework generate --brief representative-brief-001.json --env production --wait 3. Monitor progress via eoframework status <solution_id> until COMPLETE 4. Run eoframework artifact list to enumerate all five presales artifacts 5. Download and review solution-briefing.md and statement-of-work.md for content accuracy 6. Confirm GitHub commit exists in the production repository | All five presales artifacts generated; solution state is COMPLETE; generation completed in under 60 minutes; artifacts are coherent and reference the client context from the brief; GitHub commit is present with correct commit message | Critical | Production | Marcus Patel | Not Started | Not Executed | SOW-Testing-UAT; DD-Business-SuccessCriteria; IG-Integration-E2E | Primary UAT scenario for Marcus Patel sign-off; go-live gate per SOW UAT sign-off requirement
UAT-002 | Business Process | Full Delivery Bundle Generation — All 12 Artifacts | Validate that the platform generates all twelve EO Framework artifacts (five presales + six delivery + one Terraform automation bundle) end-to-end and each artifact passes EO Validator quality check | UAT environment fully deployed; representative client brief available; Phase 3 validation complete | 1. Submit a full generation request via CLI with a representative brief 2. Poll status until solution reaches COMPLETE or PARTIAL state 3. Inspect DynamoDB artifact_statuses map to confirm all twelve artifact types show PASSED 4. Download at least three delivery artifacts and review content quality 5. Confirm Terraform automation bundle is present in S3 automation prefix 6. Confirm all twelve artifacts committed to GitHub repository | All twelve artifacts present with PASSED validation status; generation time ≤ 60 minutes; Terraform bundle is present in S3; GitHub contains all twelve committed files; no artifact requires manual remediation | Critical | Production | Marcus Patel | Not Started | Not Executed | SOW-Testing-UAT; SOW-Success-Metrics; DD-Business-SuccessCriteria | Validates SOW success metric: all 12 artifact types pass format-check + LLM quality-check with ≤3 retries; executive demo scenario
UAT-003 | Business Process | CLI Status — Per-Phase Token Usage Display | Validate that the CLI status subcommand displays per-phase Bedrock token usage (input tokens; output tokens; estimated cost) for a completed solution | Full generation pipeline operational; at least one completed solution with token usage data recorded in DynamoDB | 1. Run eoframework generate and wait for completion 2. Run eoframework status <solution_id> 3. Inspect the CLI output for per-agent token usage section 4. Verify input tokens; output tokens; and estimated cost (USD) are shown for Pre-Sales Generator; Delivery Generator; Code Generator; and EO Validator phases 5. Cross-check displayed cost against DynamoDB solutions table token_usage map | Status output shows per-phase token usage with input tokens; output tokens; and estimated cost for each generation agent; total estimated cost is under $5 for a full 12-artifact bundle | High | Production | Marcus Patel | Not Started | Not Executed | DD-Business-Drivers; DD-SolArch-Component; SOW-Testing-UAT | SOW UAT scenario: CLI status with per-phase token usage; demonstrates cost governance capability to PREDICTif leadership
UAT-004 | Business Process | Admin Quota Override via API | Validate that an Admin user can override a consultant's per-user monthly quota via the admin API endpoint and the consultant can immediately generate an additional solution | Admin user with valid JWT; test consultant user with quota at 10/10 (exhausted); UAT environment deployed | 1. Authenticate as Admin user via CLI 2. Confirm test consultant receives HTTP 429 on generate request 3. Call POST /api/v1/admin/quota-override with consultant user_id and new limit of 12 4. Re-attempt generate request as consultant 5. Verify generate succeeds with HTTP 202 6. Verify quota override event recorded in DynamoDB audit_events table | Quota override succeeds; consultant can generate after override; solution proceeds to completion; audit_events table contains override record with admin user_id; action; and timestamp | High | Production | Marcus Patel | Not Started | Not Executed | DD-Integration-API; DD-Security-IAM-Roles; SOW-Testing-UAT | SOW UAT scenario: admin quota override; demonstrates administrative control required for managing the 120-consultant user base
UAT-005 | Business Process | GitHub Artifact Delivery Verification | Validate that all generated and passing artifacts are automatically committed to the configured GitHub repository with the correct commit message format after each solution completes | GitHub repository provisioned; PAT stored in Secrets Manager; at least one complete solution generated in production | 1. Complete a full solution generation via CLI in production 2. Navigate to the GitHub repository in the browser 3. Locate the commit corresponding to the solution_id 4. Verify commit message follows format: solution_id/<artifact_type>: generated by EO Validator 5. Verify all passing artifact files are present under the correct solution_id directory in the repository 6. Verify commit is attributed to the platform PAT (not a personal account) | All passing artifacts are present in the GitHub repository under the solution_id directory; commit message format is correct for each file; commit author matches the Secrets Manager PAT account; Daniel Park confirms the commit is visible | High | Production | Daniel Park | Not Started | Not Executed | DD-Integration-External; DD-DataArch-DataFlow; SOW-Testing-UAT | Validates automated GitHub delivery pipeline; key operational handover requirement for Daniel Park
UAT-006 | User Interface | CloudWatch Dashboard — Operational Visibility | Validate that the CloudWatch health dashboard provides real-time operational visibility into Lambda error rates; Bedrock token usage; and solution generation throughput as required for the green metrics baseline | CloudWatch dashboard deployed; at least 5 solutions generated in production; all CloudWatch alarms in OK state | 1. Open the eofw-prd-health CloudWatch dashboard in the AWS Console 2. Review the Lambda Error Rate widget — confirm zero errors in last 1 hour 3. Review the Bedrock Token Usage — Estimated Cost widget — confirm cost data is populating 4. Review the API Gateway P99 latency widget 5. Confirm all seven CloudWatch alarms are in OK state 6. Daniel Park navigates all widgets independently and confirms understanding | Dashboard displays all key metrics without errors; Lambda error rate widget shows 0%; Bedrock cost widget shows per-agent estimated cost data; all alarms in OK state; Daniel Park confirms dashboard is operationally useful and no training gaps identified | High | Production | Daniel Park | Not Started | Not Executed | DD-Infra-Monitoring; DD-Infra-Monitoring-Alerts; SOW-GoLive-Readiness | SOW go-live gate: green CloudWatch metrics baseline confirmed; validates executive demo readiness
UAT-007 | Business Rules | Artifact Validation Pass Rate — 95% First-Attempt Target | Validate that the artifact validation first-attempt pass rate is ≥95% across all twelve artifact types using ten representative client briefs | Ten representative client briefs provided by Marcus Patel; full platform deployed in staging; DynamoDB validation metrics available | 1. Submit ten generation requests using the ten representative client briefs 2. After all solutions complete; query DynamoDB for first-attempt pass/fail status per artifact per solution 3. Calculate the first-attempt pass rate: (artifacts that passed on retry_count = 0) / (total artifacts generated) × 100 4. Confirm overall pass rate meets or exceeds 95% | First-attempt artifact validation pass rate ≥ 95% across all twelve artifact types over the ten representative briefs; any artifact falling below 95% is investigated and prompt or format-check adjustments are made before go-live | Critical | Staging | QA Lead | Not Started | Not Executed | SOW-Success-Metrics; DD-Business-SuccessCriteria; DD-SolArch-Patterns | SOW success metric: ≥95% validation pass rate on first attempt; this metric gates production go-live approval
UAT-008 | Acceptance | Executive Demonstration — End-to-End Platform Showcase | Validate the platform is demonstrable to executive sponsor Sarah Lin covering all four core capabilities: CLI auth; presales generation; delivery generation; and Terraform automation bundle | Production environment fully deployed and green; all other UAT tests passed; executive demo brief prepared; Marcus Patel UAT sign-off obtained; CTO sign-off obtained | 1. Sarah Lin and Marcus Patel observe the demonstration 2. Authenticate via eoframework auth login (demonstrates CLI + Cognito) 3. Submit generation request with a representative brief (demonstrates async generation) 4. Display real-time status updates with per-phase token usage 5. Show completed solution with all twelve artifacts including Terraform bundle in GitHub 6. Open CloudWatch dashboard to show green metrics baseline 7. Demonstrate admin quota override capability | Executive demonstration is delivered successfully; all four core capabilities shown end-to-end; Sarah Lin confirms the platform meets the executive-level acceptance criteria for Q2 2026; formal go-live approval is obtained from CTO | Critical | Production | Sarah Lin | Not Started | Not Executed | SOW-Milestones-GoLive; SOW-Testing-UAT-Signoff; DD-Business-SuccessCriteria | SOW Milestone: Go-Live — executive demo delivered to Sarah Lin; mandatory final gate before platform handover to Amatra team