## Slide 1
Project Closeout
Amatra Intelligent Solution Builder
Lead Solutions Architect | 2027-02-14

## Slide 2
Slide 2: Executive Summary
Project Duration: 9 months — on schedule
Budget: $345,000 net PS within approved budget
Phase 1 Go-Live: 30 September 2026 as committed
Phase 2 Go-Live: 15 December 2026 as committed
GA Release: Q1 2027 — all 120 users onboarded
Artifact Turnaround: 3 weeks → under 4 hours (>95% reduction)
QA First-Pass Rate: 92% (target ≥90%)
Platform Availability: 99.95% in production (target 99.9%)
Legacy Monolith: EC2 retired with zero data loss
ROI Trajectory: On track for 12-month payback
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Open with confidence — every contractual commitment was met or exceeded
- Phase 1 Pre-Sales MVP was live on 30 September 2026, satisfying the hard deadline before Amatra's flagship client renewal on 31 January 2027
- Phase 2 Delivery & Terraform automation went live on 15 December 2026, ahead of the holiday freeze
- General Availability achieved in Q1 2027 with all ~120 internal users onboarded via Cognito (migrated from Okta with zero access disruption)
- QA first-pass rate of 92% exceeded the 90% contractual target by Week 8 post-go-live
*Budget Details:*
- List price: $375,000 PS + $61,348 infrastructure + $1,632 software + $173 connectivity + $6,120 support = $444,273 Year 1 list
- Credits applied: $30,000 PS credits (APN Advanced + Bedrock Early Adopter + volume discount) + $5,000 infrastructure credit = $35,000 total
- Net Year 1 investment: $409,273 — within approved budget envelope
- Year 2 and Year 3 run-rate: ~$69,273/year (infrastructure + licenses + support only; no PS fees)
- 3-year TCO: $547,819 vs. estimated $900K+ for 3 FTEs maintaining manual workflow
*Quality Summary:*
- Zero critical (Severity 1) defects at Phase 1 go-live
- Zero critical defects at Phase 2 go-live
- 8-week hypercare completed with no platform-down incidents

## Slide 3
Slide 3: Solution Architecture
Amatra Intelligent Solution Builder
AI Generation Layer
  Amazon Bedrock (Claude 3 Sonnet) inference
  Step Functions async 30–60 min job pipeline
  SQS FIFO queues with dead-letter handling
Platform & Data
  Lambda + API Gateway serverless REST API
  DynamoDB state; S3 artifact store (KMS)
  Cognito auth with admin governance controls
Security & Compliance
  WAF, CloudTrail, and KMS encryption at rest
  PrivateLink — no public internet traversal
  SOC 2 Type II evidence package delivered
Notes: *Talking Points:*
- Architecture is fully serverless — zero managed server infrastructure to patch or scale
- Walk the audience through three logical layers: AI generation at the top, platform and data in the middle, security and compliance at the base
- All services deployed exclusively in us-west-2 (United States data residency — GDPR-aligned)
*Technical Highlights:*
- Bedrock Claude 3 Sonnet powers all 7+ artifact type generations
- Step Functions standard workflows handle 30–60 min jobs — no Lambda timeout risk
- SQS FIFO with idempotency keys ensures exactly-once job processing even on retry
- DynamoDB on-demand mode handles per-user and global usage limit enforcement
- S3 versioned buckets with lifecycle policies: Standard → Intelligent-Tiering (90 days) → Glacier (365 days)
- Cognito User Pool replaced Okta; all 120 users migrated with zero access disruption
*Presales Alignment:*
- Architecture matches the Solution Briefing specification exactly
- Services: Bedrock, Lambda, API Gateway, Step Functions, SQS, DynamoDB, S3, Cognito, WAF, CloudTrail, Secrets Manager, KMS, PrivateLink, CloudFront, SES, X-Ray, Config, CloudWatch — all in original scope
- No scope additions beyond presales commitment
*Design Decisions:*
- Step Functions over EventBridge Pipes — chosen for native execution history, retry configuration, and error-state visibility
- DynamoDB on-demand over provisioned — cost-optimal at 24 engagements/quarter; no capacity planning required
- API Gateway REST (not HTTP) — required for Cognito authoriser with custom usage-limit enforcement

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Detailed Design Document | Architecture decisions and component specs | `/delivery/detailed-design.md`
Implementation Guide | Step-by-step deployment procedures | `/delivery/implementation-guide.md`
Project Plan | Timeline, milestones, resource allocation | `/delivery/project-plan.csv`
Test Plan & Results | Test cases, coverage, and quality metrics | `/delivery/test-plan.csv`
Configuration Guide | Lambda, API, DynamoDB, Bedrock parameters | `/delivery/configuration.csv`
Terraform IaC Modules | Cloud resource provisioning across all envs | `/delivery/scripts/terraform/`
Operational Runbooks | Incident response and DR procedures | `/delivery/runbooks/`
SOC 2 Evidence Package | Audit evidence for Type II certification | `/delivery/compliance/soc2-evidence/`
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- All 30 formal deliverables listed in the SOW have been reviewed and formally accepted by the designated Amatra stakeholders
- Highlight the Terraform IaC — 100% coverage across Dev, Staging, and Production; any future infrastructure change goes through the same GitHub Actions pipeline, not manual console clicks
- SOC 2 evidence package includes: CloudTrail exports, Config compliance history, Cognito access logs, Secrets Manager rotation logs, IAM Access Analyzer findings, encryption-at-rest inventory
*Key Deliverable Highlights:*
- **Detailed Design Document** — covers all ADRs, component topology, DynamoDB schemas, S3 structure, async pipeline design, and Bedrock prompt engineering strategy
- **Implementation Guide** — step-by-step runbook for deploying the platform from scratch; validated by the VP Engineering
- **Configuration Guide** — all Lambda memory/timeout settings, API Gateway throttle limits, DynamoDB table configs, and Bedrock model parameter choices documented
- **Terraform IaC** — modular structure with separate modules for each AWS service; tfvars files per environment; S3+DynamoDB remote state backend
*Acceptance Status:*
- All deliverables formally accepted; sign-off documentation on file
- Training materials (admin deck, pre-sales user guide, delivery team guide) delivered at Week 30 and Week 32 sessions
- Hypercare Report and Optimisation Roadmap delivered at Week 36 (project close)

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Functional test pass rate: 98% (target: 90%)
  All 7 artifact types validated: 100%
  Sev 1 defects at go-live: 0
  UAT first-pass acceptance rate: 92%
  Security test findings resolved: 100%
Performance Metrics
  Platform uptime: 99.95% (target: 99.9%)
  Avg generation job duration: 42 min
  Concurrent job capacity: 25 validated
  API P99 response time: 420 ms (<2 s target)
  DLQ messages in production: 0
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Quality was embedded at every stage — not bolted on at the end
- QA Engineer developed test cases against the internal QA rubric for all 7+ artifact types across three client brief complexity levels (simple, medium, complex)
- UAT with 8 pre-sales consultants from the Head of Solutions team validated that 92% of generated artifacts passed QA on first review — exceeding the 90% contractual target
*Testing Phases Completed:*
1. Functional & Integration Testing (Weeks 21–24): API Gateway → Lambda → Bedrock → S3 end-to-end; Cognito auth flows; DynamoDB usage-limit enforcement
2. Performance & Load Testing (Week 24): 10 concurrent brief submissions — all completed within 72 minutes; 25-job stress test confirmed headroom
3. Security & Compliance Testing (Week 25): OWASP API Security Top 10; WAF rule validation; Cognito bypass tests; CloudTrail completeness audit; encryption-at-rest verification
4. DR Testing (Week 25): DynamoDB PITR restoration validated RPO <1 hour; Lambda Terraform redeployment validated RTO <4 hours
5. UAT (Week 26): 8 pre-sales consultants; 92% first-pass acceptance; all Severity 1/2 defects resolved before go-live sign-off
*Presales SLA Alignment:*
- 99.9% availability target → Achieved 99.95% in production (measured monthly via CloudWatch)
- ≥90% QA first-pass rate → Achieved 92% by Week 8 post-go-live
- 30–60 min async job duration → Average 42 minutes; max observed 58 minutes under concurrent load
- Zero data loss on legacy monolith decommission → Confirmed; data archive validated before DNS cutover

## Slide 6
Slide 6: Benefits Realized
Benefit Category | Target | Achieved | Impact
Artifact Turnaround | <2 business days | ~4 hours avg | Pre-sales capacity fully freed
Proposal Throughput | 24 engagements/qtr | 22 engagements/qtr | 2.75× increase from baseline
Consulting Hours/Engagement | 40% reduction | 43% reduction | ~12 hrs saved per engagement
QA First-Pass Rate | ≥90% | 92% | Rework cycles eliminated
Platform Availability | 99.9% monthly | 99.95% monthly | Zero unplanned outages
Annual Cost Avoidance | ~$300K (vs. 3 FTEs) | $312K projected | ROI within 12 months
Okta User Migration | 100% no disruption | 100% success | Zero access complaints
Legacy Monolith Retired | Zero data loss | Confirmed zero loss | EC2 cost eliminated
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Benefits are measurable within 8 weeks of Phase 1 go-live — faster than projected
- Artifact turnaround has gone from ~3 weeks to an average of ~4 hours — greater than 95% reduction, exceeding the sub-2-business-day target
- Throughput is ramping: 22 engagements/quarter in the first full quarter post-GA; targeting the 24/quarter run rate by Q2 2027 as all users build familiarity with the platform
*ROI Calculation:*
- 3 FTE equivalent at Amatra avg fully-loaded cost ~$104K/year = $312K/year saved
- Net Year 1 investment: $409,273 (including $35K in credits)
- Year 2 run-rate: $69,273
- Break-even: approximately Month 10–11 post-go-live (Q3 2027)
- 3-year net benefit: ($312K × 3) – $547,819 TCO = $388K net value delivered
*Detail on Throughput Ramp:*
- Baseline: ~8 active engagements/quarter (manual process, constrained by consultant hours)
- Phase 1 (Q4 2026): 14 engagements processed using Pre-Sales MVP
- Phase 2 (Q1 2027, first full GA quarter): 22 engagements
- Projecting ≥24/quarter by Q2 2027 as Bedrock prompt tuning continues and all delivery artifact types are in use
*Cost Avoidance Components:*
- Manual drafting hours eliminated: ~12 hrs/engagement × 22 engagements/qtr × $125 blended rate = $33K/quarter
- Quality rework reduction: fewer revision cycles (92% first-pass vs. estimated 50–60% manual first-pass)
- EC2 monolith retired: ~$8K/year in EC2 and Okta licensing costs eliminated

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Async Step Functions eliminated Lambda timeout risk
  Phased MVP validated AI quality before full rollout
  IaC-first deployment ensured zero environment drift
  Weekly stakeholder cadence surfaced issues early
  Structured UAT rubric drove 92% first-pass rate
  Early Okta inventory prevented migration surprises
Recommendations
  Upgrade to Bedrock Claude 3.5 Sonnet (next 30 days)
  Expand to RFP response artifact type (Q2 2027)
  Add Bedrock cost-per-solution attribution dashboard
  Initiate formal SOC 2 Type II audit (Q3 2027)
  Establish quarterly prompt-quality review cadence
  Evaluate pricing calculator artifact type (Q3 2027)
Amatra Intelligent Solution Builder
Notes: *What Worked Well — Detail:*
- **Async architecture:** The decision to use Step Functions standard workflows instead of synchronous Lambda invocations was validated repeatedly during load testing — no jobs timed out under any tested scenario
- **Phased MVP:** Delivering the Pre-Sales MVP at Month 4 gave the Head of Solutions team 5 months of real-world usage feedback before Phase 2 delivery artifacts went live — the prompt tuning done in that window was invaluable
- **IaC-first:** Using Terraform from Day 1 (even in Dev) meant that promoting to Staging and Production was a variable swap, not a rebuild — no environment drift issues observed
- **Weekly cadence:** CTO-level engagement in weekly status meetings meant that the Okta mapping challenge was escalated and resolved in Week 2, not discovered during testing
- **UAT rubric:** Providing a structured QA rubric to UAT participants (rather than open-ended feedback) produced actionable, specific prompt-tuning inputs that raised first-pass rate from 74% to 92% across three iteration cycles
*Challenges Overcome (speaker context):*
- **Bedrock prompt tuning:** Initial prompts for the SOW artifact type produced outputs that were structurally correct but too generic (first-pass rate of 74% in early testing). Three iteration cycles incorporating Head of Solutions feedback raised the rate to 92%. Key lesson: allocate explicit sprint time for prompt tuning with real client brief samples.
- **Okta group mapping:** Amatra's Okta instance had undocumented legacy groups that did not map cleanly to the three target Cognito groups. Required an extra 3-day discovery sprint (Week 3). No schedule impact because it was identified early; early Okta inventory is now listed as a "What Worked Well" item.
*Recommendations — Priority Order:*
1. **Claude 3.5 Sonnet upgrade** (next 30 days): IaC change is a single variable update in terraform.tfvars; expected to raise first-pass rate to 95%+ with no prompt changes required
2. **RFP response artifact type** (Q2 2027): Highest-demand artifact type from pre-sales consultant feedback in UAT
3. **Cost attribution dashboard** (Q2 2027): Bedrock token consumption is the primary cost driver; per-solution-ID attribution enables chargeback reporting
4. **SOC 2 Type II formal audit** (Q3 2027): Evidence package is ready; engage an accredited auditor before next flagship renewal
5. **Quarterly prompt review** (ongoing): 2-hour quarterly session between Head of Solutions and platform admin to evaluate new artifact outputs
6. **Pricing calculator artifact** (Q3 2027): Second-highest demand item from consultant feedback after RFP response

## Slide 8
Slide 8: Support Transition
Hypercare (Weeks 1–8 post-go-live)
  Dedicated vendor team on-call daily
  Sev 1: 1-hr response / 4-hr resolution SLA
  Sev 2: 4-hr response / 8-hr resolution SLA
  Bedrock prompt tuning from live usage data
  Cognito onboarding support for all 120 users
  CloudWatch alarm threshold tuning completed
Steady State (Week 9+)
  Amatra operations team owns platform fully
  Admin runbook and Confluence docs in place
  Terraform pipeline for all infra changes
  Monthly CloudWatch health review recommended
  Quarterly prompt-quality review established
  L1 escalation: solutions@partner.com (vendor)
Amatra Intelligent Solution Builder
Notes: *Hypercare Coverage Detail:*
- Hypercare ran from 30 September 2026 through approximately 25 November 2026 (8 weeks post-Phase 1 go-live)
- Coverage: business hours (8:00 am–6:00 pm CT, Mon–Fri) plus on-call for Severity 1 incidents
- During hypercare: zero Severity 1 incidents; two Severity 2 incidents resolved within 6 hours each; four Severity 3 issues resolved within next business day
- Bedrock prompt tuning performed in hypercare Weeks 3 and 6 based on live QA feedback from Head of Solutions — raised first-pass rate from initial 88% to 92%
*Transition Phase (Weeks 9–12) Detail:*
- Three formal knowledge transfer sessions delivered:
- **Session 1 (Week 30) — Admin Enablement (4 hrs):** Cognito user management, usage limit configuration, CloudWatch dashboard navigation, incident response, Terraform change procedure
- **Session 2 (Week 30) — Pre-Sales Consultant Enablement (3 hrs):** Brief submission, artifact review, QA checklist, regeneration workflow, Office document download
- **Session 3 (Week 32) — Delivery Team Enablement (2 hrs):** Phase 2 artifact types (detailed design, implementation guide, Terraform automation), review and validation workflow
- All sessions recorded and posted to Confluence; VP Engineering confirmed all designated admins have completed the admin enablement module
*Steady State Responsibilities (Amatra):*
- AWS account management and Bedrock quota monitoring (CloudWatch alarm in place at 80% of monthly quota)
- Cognito user onboarding/offboarding (quarterly access review process established)
- Usage limit configuration (admin API documented in runbook)
- Terraform-based infrastructure changes via GitHub Actions pipeline (no manual console changes)
- DLQ monitoring — CloudWatch alarm triggers SNS notification to operations team on first message
*After-Hours Support (Post-Hypercare):*
- Vendor team is not on-call after hypercare completion (Week 36)
- For critical platform issues post-hypercare, refer to the Optimisation Roadmap for a Managed Services Agreement option
- Internal escalation path: L1 platform admin → VP Engineering → CTO

## Slide 9
Slide 9: Acknowledgments & Next Steps
CTO and executive team for budget ownership and phase-gate approvals
VP Engineering for day-to-day technical ownership and milestone acceptance
Head of Solutions for QA rubric definition and UAT leadership
Security & Compliance Lead for SOC 2 design and testing sign-off
This Week: Final documentation and runbook handover complete
Next 30 Days: Activate Bedrock Claude 3.5 Sonnet model upgrade
Q2 2027: Phase 4 scoping — additional artifact types and cost dashboards
Amatra Intelligent Solution Builder
Notes: *Acknowledgment Talking Points:*
- This delivery was a genuine partnership — Amatra's team met every contractual dependency on time
- CTO's go/no-go approvals at each phase gate kept the project moving without delay
- Head of Solutions' willingness to dedicate 8 UAT participants for a full week was the primary reason QA first-pass rate exceeded the 90% target
- Security & Compliance Lead reviewed and approved all SOC 2 design decisions within the 5-business-day SLA every time — enabling the security testing phase to proceed without schedule impact
- VP Engineering's proactive identification of the Okta group mapping issue in Week 3 prevented it from becoming a testing-phase blocker
*Next Steps Detail:*
- **This week:** Hypercare Report and Optimisation Roadmap formally handed over to CTO (Week 36 deliverable); project closeout meeting scheduled
- **Next 30 days:** Bedrock model upgrade to Claude 3.5 Sonnet — IaC change is a single variable update in terraform.tfvars; estimated 2 hours of effort; expected QA first-pass improvement to 95%+
- **Q2 2027 Phase 4 planning:** Hold a half-day scoping workshop with Head of Solutions to prioritise next artifact types (RFP response and pricing calculator are current top candidates); engage security team to initiate formal SOC 2 Type II audit
- **Ongoing:** Monthly CloudWatch dashboard reviews (30-minute cadence); quarterly Bedrock prompt quality review sessions; annual Cognito access review
*Celebration Note:*
- The platform went live before Amatra's flagship client renewal on 31 January 2027 — the original hard deadline that drove the entire engagement timeline
- Amatra is now positioned to triple proposal throughput and achieve ROI within 12 months

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion
- Have the detailed-design.md and test-plan.csv ready for deep-dive questions on architecture or test coverage
- Offer to schedule a follow-up architecture walkthrough session for the VP Engineering and any new team members who join after project close
- Remind the audience of the Optimisation Roadmap document — it contains prioritised next steps with effort estimates and expected benefits for each recommendation
- End on a positive note: celebrate the delivery together — the platform is live, the ROI trajectory is confirmed, and Amatra is well-positioned to scale its proposal throughput in 2027
- If asked about post-hypercare support options: refer to the Managed Services Agreement option outlined in the Optimisation Roadmap