## Cover
Discovery Questionnaire
Generated: | June 04, 2026
Solution: | Tmpwj0_95K9
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## All Categories (Read Only)
Total Questions | Answered | Remaining | % Complete
66
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes

## Business Requirements
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
BUS-001 | Business Requirements | Business Drivers | What are the primary business pain points with the current manual EO Framework documentation process? | Describe top 3-5 inefficiencies — e.g., rework loops, LLM iteration cycles, time lost per engagement |  | Baseline for justifying automation investment and scoping the MVP
BUS-002 | Business Requirements | Business Drivers | How many presales engagements does Amatra run per month today, and what is the projected growth rate over the next 12 months? | Provide current monthly volume and expected volume at 6-month and 12-month marks |  | Drives capacity planning for agent concurrency, DynamoDB quota design, and Bedrock token budgeting
BUS-003 | Business Requirements | Success Criteria | What measurable success criteria will determine whether this platform is considered a success at go-live? | Examples: end-to-end generation in under 60 minutes, 90% reduction in senior-consultant hours, zero manual retries per artifact |  | Critical for acceptance testing and executive-sponsor sign-off
BUS-004 | Business Requirements | Success Criteria | What is the acceptable per-artifact validation failure rate in production? | Current state has 3-4 LLM iteration retries; what is the target pass-on-first-attempt rate? |  | Informs quality-gate thresholds and the LLM retry cap (currently 3)
BUS-005 | Business Requirements | Timeline | Is the Q2 2026 / end-of-April PoC deadline fixed, and what are the consequences of a slip? | Confirm executive-demonstration date; identify contractual or budget-cycle dependencies |  | Hard deadline shapes phase sequencing and MVP scope
BUS-006 | Business Requirements | Timeline | Are the three delivery phases (Weeks 1-4, 5-9, 10-12) fixed, or can they be re-baselined if scope is reduced? | Identify which phase milestones have external dependencies (e.g., Cognito approval, AWS account provisioning) |  | Impacts resource loading and sprint planning
BUS-007 | Business Requirements | Budget | What is the approved budget envelope for the 12-week build engagement versus the first-year run cost? | Confirm the $250k professional-services and $100k-$200k run-cost split; identify who controls each budget line |  | Procurement trigger and change-order thresholds
BUS-008 | Business Requirements | Budget | At what monthly AWS spend level does procurement need to be re-engaged? | Identify the existing AWS spend envelope and the threshold that triggers a new procurement cycle |  | Determines whether platform spend can be absorbed into existing agreement or requires a new commitment
BUS-009 | Business Requirements | Stakeholders | Who has authority to approve production deployment of the Cognito-based user pool? | Identify the CTO and any security/compliance reviewers who must sign off |  | Approval dependency that could block Phase 1 completion
BUS-010 | Business Requirements | Stakeholders | Who are the end users of the CLI and HTTP API — internal consultants only, or also external clients? | Define the user population: Amatra consultants, PREDICTif engineers, or customer-facing personas |  | Drives Cognito pool design, per-user quota policy, and UX requirements
BUS-011 | Business Requirements | ROI & Value | What is the current fully-loaded cost (consultant time + overhead) to produce one presales package manually? | Use the 6-10 senior-consultant-hours estimate as a baseline; confirm the blended hourly rate |  | Quantifies ROI baseline for the business case and executive presentation
BUS-012 | Business Requirements | ROI & Value | Is parallel pipeline throughput (multiple solutions generated simultaneously) a hard requirement or a stretch goal? | Confirm whether concurrent multi-solution generation is needed for the PoC demo or Phase 2 |  | Architectural decision driver for Lambda concurrency limits and AgentCore scaling

## Technical Requirements
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
TECH-001 | Technical Requirements | Current Infrastructure | Describe the existing AWS account structure — single account or multi-account org, and which account will host the new platform? | Confirm whether a net-new us-west-2 account is being created or whether an existing account is being used with a new region footprint |  | Foundation for IAM, VPC, and blast-radius decisions
TECH-002 | Technical Requirements | Current Infrastructure | What AWS services are currently active in the us-east-1 footprint, and are any shared resources (IAM roles, S3 buckets, VPCs) expected to be reused? | List managed-services workloads and identify any cross-region or cross-account dependencies |  | Isolation boundary design and blast-radius analysis
TECH-003 | Technical Requirements | Cloud Platform | Has the team used Amazon Bedrock or AgentCore Runtime in any previous engagement? | Identify existing Bedrock model access approvals, service quotas, and any prior AgentCore Runtime experience |  | Bedrock model access (Claude Sonnet 4.6 and Haiku 4.5) must be enabled before Phase 2; quota increases may have lead time
TECH-004 | Technical Requirements | Cloud Platform | What is the target AWS region for each service — is us-west-2 confirmed for all services including Bedrock, Cognito, and API Gateway? | Confirm regional availability of Bedrock model IDs (claude-sonnet-4-6, claude-haiku-4-5) in us-west-2 |  | Some Bedrock model IDs may only be available in specific regions; verify before architecture is finalised
TECH-005 | Technical Requirements | Agent Architecture | How many concurrent solution-generation workflows must the platform support at steady state (200/month) and at peak? | Estimate peak concurrency — e.g., 10 simultaneous solutions — to size Lambda reserved concurrency and AgentCore Runtime instances |  | Drives Lambda concurrency limits, DynamoDB throughput mode, and Bedrock token-per-minute quota
TECH-006 | Technical Requirements | Agent Architecture | Confirm the five-agent topology: Input Validator (Agent 0), Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator — is this fixed or subject to change? | Identify any additional agents planned (e.g., cost estimator, diagram generator) that should be architected in from the start |  | Agent count affects AgentCore Runtime registration, IAM role design, and per-solution token budget
TECH-007 | Technical Requirements | Agent Architecture | What is the expected average token count per artifact and per full solution package (12 artifacts)? | Provide estimates for input + output tokens per artifact type (e.g., solution-briefing vs. Terraform bundle) |  | Primary driver of Bedrock cost model and per-solution $5 spend target feasibility
TECH-008 | Technical Requirements | API & CLI | Describe the 14 CLI subcommands and 11 HTTP API routes — which are in-scope for the PoC and which are deferred? | List the four core capabilities required for the April demo: CLI auth, presales generation, delivery generation, automation bundle |  | Scope boundary for Phase 3 testing and acceptance
TECH-009 | Technical Requirements | API & CLI | What authentication flow does the CLI use — device-code flow, username/password, or machine-to-machine client credentials? | Confirm the Cognito auth flow (USER_PASSWORD_AUTH, DEVICE_FLOW, or MACHINE_TO_MACHINE) for the pip-installable CLI |  | Cognito app-client configuration and token-refresh design (30-day refresh tokens confirmed)
TECH-010 | Technical Requirements | Data & Storage | What is the expected S3 storage volume at steady state (200 solutions/month) — raw artifacts, converted DOCX/PPTX/XLSX, and GitHub-committed bundles? | Estimate average solution package size (raw + converted) multiplied by monthly volume and retention period |  | S3 storage cost and lifecycle-policy design
TECH-011 | Technical Requirements | Data & Storage | What is the DynamoDB access pattern for quota enforcement — single-table design with per-user and global counters, or separate tables? | Confirm atomic counter strategy: DynamoDB transactions or conditional writes for the 10/user/month and 1000/month global quota |  | DynamoDB capacity mode (on-demand vs. provisioned) and consistency requirements
TECH-012 | Technical Requirements | eof-tools Integration | Describe the eof-tools converter library interface — is it invoked as a Python subprocess, imported as a module, or called via an internal API? | Confirm how the 30-module library covering 12 artifact types is packaged into the agent container image |  | Container image size, cold-start latency, and dependency management
TECH-013 | Technical Requirements | eof-tools Integration | Are all 12 artifact types supported by the current eof-tools library, or are there gaps that require new converter modules? | Identify any artifact types (e.g., new Terraform bundle format) not yet covered by eof-tools |  | Scope risk — new converter modules may add to Phase 2 effort
TECH-014 | Technical Requirements | GitHub Integration | What GitHub repository structure is expected — one repo per solution, one repo per client, or a single monorepo with solution-scoped directories? | Confirm the fixed public repository mentioned in the brief and the branching strategy for committed artifacts |  | GitHub personal-access-token scope, repo permissions, and CI/CD trigger design
TECH-015 | Technical Requirements | GitHub Integration | How is the GitHub personal access token managed — AWS Secrets Manager, Parameter Store, or environment variable in the container? | Identify rotation policy and who owns the token |  | Security and operational risk; token expiry could silently break artifact delivery
TECH-016 | Technical Requirements | Performance | What is the maximum acceptable end-to-end latency for a full 12-artifact solution generation run? | Confirm the under-60-minute target; identify whether this is a p50, p95, or p99 target |  | Lambda timeout configuration (max 15 min per function) and Step Functions / async orchestration design
TECH-017 | Technical Requirements | Performance | What are the Terraform validation gate requirements — is `terraform validate` the only gate, or are `terraform plan` dry-runs also required? | Identify whether a live AWS account is needed for plan execution or whether validate-only is sufficient for the PoC |  | Infrastructure and IAM requirements for Terraform execution environment
TECH-018 | Technical Requirements | Monitoring & Observability | What CloudWatch metrics baseline is required for Phase 3 sign-off? | Define the specific metrics: per-agent token usage, artifact generation latency, validation pass/fail rates, quota utilisation |  | Monitoring design and CloudWatch dashboard scope
TECH-019 | Technical Requirements | Monitoring & Observability | Is distributed tracing (AWS X-Ray) required, or is CloudWatch Logs correlation sufficient for the PoC? | Confirm observability tooling preferences and any existing monitoring stack |  | Tracing instrumentation adds latency and cost; confirm if required for PoC
TECH-020 | Technical Requirements | Scalability | What is the long-term throughput target beyond the 200-solutions/month steady state — is there a 12-month or 24-month growth projection? | Provide peak throughput scenarios (e.g., 500 or 1000 solutions/month) to validate the linear-scaling architecture claim |  | Architecture validation for Lambda concurrency, DynamoDB, and Bedrock quota ceilings

## Security & Compliance
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
SEC-001 | Security & Compliance | Compliance Frameworks | What compliance frameworks apply to this platform and its generated artifacts? | SOC 2 Type II, ISO 27001, NIST CSF, or others — particularly relevant if customer data flows through the platform |  | Determines audit-logging depth, encryption requirements, and penetration-testing scope
SEC-002 | Security & Compliance | Data Classification | What is the sensitivity classification of the presales artifacts and briefing data processed by the platform? | Classify as Public, Internal, Confidential, or Restricted — presales documents may contain client pricing and architecture IP |  | Drives encryption-at-rest configuration, S3 bucket policies, and data-retention rules
SEC-003 | Security & Compliance | Authentication & Authorisation | Beyond Cognito MFA, are there additional authentication requirements such as SSO federation with an enterprise IdP (Okta, Azure AD)? | Confirm whether SAML 2.0 or OIDC federation is required for Amatra consultants or PREDICTif corporate accounts |  | Cognito identity pool vs. user pool design; federation adds configuration complexity
SEC-004 | Security & Compliance | Authentication & Authorisation | What is the role-based access control model — admin, standard user, and read-only reviewer, or a different model? | Define the permission boundaries: who can create solutions, who can view all solutions, who can manage quotas |  | IAM and Cognito group configuration; admin usage endpoint access control
SEC-005 | Security & Compliance | Data Residency | Must all data (S3 artifacts, DynamoDB records, CloudWatch logs) remain in us-west-2, or are cross-region replicas permitted? | Confirm data-residency requirements for any client-specific content processed by the platform |  | S3 replication, CloudWatch log export, and DynamoDB global table design
SEC-006 | Security & Compliance | Encryption | What encryption requirements apply to data at rest and in transit? | Confirm: S3 SSE-KMS vs. SSE-S3, DynamoDB encryption at rest, TLS 1.2+ for API Gateway, KMS key ownership (AWS-managed vs. customer-managed) |  | Customer-managed KMS keys add operational overhead; confirm if required for compliance
SEC-007 | Security & Compliance | Network Security | Is the Lambda and AgentCore Runtime environment required to run inside a VPC, or is public-endpoint execution acceptable? | Identify any network egress restrictions or VPC endpoint requirements for Bedrock, S3, and DynamoDB |  | VPC configuration significantly increases cold-start latency and adds NAT Gateway cost
SEC-008 | Security & Compliance | Audit & Logging | What audit-logging requirements exist — CloudTrail for all API calls, S3 access logs, and DynamoDB stream logging? | Confirm log retention periods and whether logs must be exported to a SIEM |  | Audit log volume and cost; SIEM integration adds to Phase 1 scope
SEC-009 | Security & Compliance | Secret Management | How are sensitive credentials managed — GitHub PAT, Bedrock API keys, Cognito client secrets? | Confirm use of AWS Secrets Manager with automatic rotation vs. Parameter Store SecureString |  | Rotation policy and access audit trail for all platform secrets
SEC-010 | Security & Compliance | Vulnerability Management | What is the container image vulnerability scanning policy for the AgentCore Runtime Docker image containing eof-tools? | Identify whether Amazon ECR image scanning (basic or enhanced via Inspector) is required at build and runtime |  | Container security posture; critical vulnerabilities in eof-tools dependencies could block deployment

## Operations & Support
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
OPS-001 | Operations & Support | RTO | What is the Recovery Time Objective (RTO) for the platform if a regional AWS service disruption occurs? | Define maximum acceptable downtime: under 1 hour, 4 hours, or next business day |  | Determines whether multi-AZ or multi-region failover is required; impacts architecture cost
OPS-002 | Operations & Support | RPO | What is the Recovery Point Objective (RPO) for DynamoDB quota counters and S3 solution artifacts? | Define maximum acceptable data loss: zero (point-in-time recovery) or last daily backup |  | DynamoDB PITR and S3 versioning configuration; PITR adds ~20% storage cost
OPS-003 | Operations & Support | Monitoring & Alerting | What CloudWatch alarms are required at launch — Lambda error rates, Bedrock throttling, API Gateway 5xx rates, DynamoDB capacity? | Define alerting thresholds and notification channels (SNS → PagerDuty, email, Slack) |  | Operational readiness gate for Phase 3 sign-off
OPS-004 | Operations & Support | Monitoring & Alerting | Is a real-time operational dashboard required for the PoC demo, or is CloudWatch Logs Insights sufficient? | Identify whether a CloudWatch Dashboard, Grafana, or third-party APM tool is expected |  | Dashboard scope affects Phase 3 timeline; confirm for demo readiness
OPS-005 | Operations & Support | Support Coverage | What support coverage is required for the platform post-launch — business hours 8x5, extended 24x5, or 24x7? | Identify the on-call rotation and escalation path for P1 incidents (e.g., platform down during peak sales cycle) |  | Managed-service scope definition and staffing cost estimate
OPS-006 | Operations & Support | Maintenance | What are acceptable maintenance windows for Lambda deployments and DynamoDB schema changes? | Identify days/times when the platform can be taken offline for updates; serverless architecture minimises downtime but blue/green deployments must be planned |  | CI/CD pipeline design and change-management process
OPS-007 | Operations & Support | Backup & Recovery | What is the artifact retention policy — how long must completed solution packages be stored in S3? | Define retention period (e.g., 90 days, 1 year, indefinite) and whether expired artifacts should be archived to S3 Glacier |  | S3 lifecycle policy design and storage cost projection
OPS-008 | Operations & Support | Capacity Planning | How will per-user (10/month) and global (1000/month) quota limits be monitored and adjusted over time? | Define the operational process for quota increases: self-service admin API, manual DynamoDB update, or automated scaling |  | Quota management runbook and admin tooling scope
OPS-009 | Operations & Support | Cost Management | What AWS Cost Explorer tags or cost-allocation tags are required to track platform spend by team, project, or client? | Identify tagging strategy for Lambda, S3, DynamoDB, Bedrock, and Cognito resources |  | Cost visibility and chargeback model; required if spend is allocated across multiple business units

## Implementation Planning
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
IMPL-001 | Implementation Planning | Migration Approach | Is this a greenfield deployment (no existing platform to migrate from) or does it need to coexist with the current manual Claude Code CLI process during a transition period? | Confirm whether a parallel-run period is required and its minimum duration |  | If parallel run is needed, both old and new processes must be supported simultaneously, increasing Phase 2 scope
IMPL-002 | Implementation Planning | Phase 1 Scope | Confirm the Phase 1 deliverables (Weeks 1-4): Cognito, API Gateway, DynamoDB, S3, and baseline IAM — are there any additions or removals? | Identify any pre-requisites not in the brief: AWS account creation, VPC setup, DNS, or certificate management |  | Phase 1 is the foundation; scope changes here cascade to Phase 2 and 3 timelines
IMPL-003 | Implementation Planning | Phase 2 Scope | Confirm Phase 2 deliverables (Weeks 5-9): Strands Agents, AgentCore Runtime registration, Docker image pipeline, eof-tools integration — are all five agents in scope? | Identify which agents (Input Validator, Pre-Sales Generator, Delivery Generator, Code Generator, EO Validator) are required for the PoC demo vs. phased delivery |  | Agent count and complexity are the primary Phase 2 risk driver
IMPL-004 | Implementation Planning | Resource Availability | What internal Amatra/PREDICTif resources are available for this engagement — dedicated engineers, part-time SMEs, and executive sponsor time? | Identify team roles: AWS architect, backend developer, DevOps/IaC engineer, QA lead, and project manager; confirm time commitment percentages |  | Resource availability is the primary schedule risk; confirm full-time vs. fractional allocation
IMPL-005 | Implementation Planning | Resource Availability | Does PREDICTif have AWS Advanced or Premier tier partnership with access to AWS ProServe or Partner Development resources? | Confirm APN tier, available AWS credits (MAP, Partner Opportunity), and access to AWS Bedrock specialists |  | AWS partner resources could accelerate Bedrock and AgentCore Runtime integration in Phase 2
IMPL-006 | Implementation Planning | Infrastructure as Code | Is Terraform the mandated IaC tool for all platform infrastructure, or is AWS CDK or CloudFormation acceptable for specific components? | Confirm IaC tooling standards; identify whether Terraform Cloud/Enterprise or open-source Terraform with S3 backend is used |  | Terraform state management design and `terraform validate` gate implementation
IMPL-007 | Implementation Planning | CI/CD Pipeline | What CI/CD platform is required — GitHub Actions, AWS CodePipeline, GitLab CI, or Jenkins? | Confirm the pipeline tooling and branching strategy for infrastructure and application code |  | CI/CD pipeline design is a Phase 2 dependency for Docker image builds and Terraform deployments
IMPL-008 | Implementation Planning | Testing & UAT | What is the User Acceptance Testing (UAT) plan for Phase 3 — which artifact types, how many test solutions, and who signs off? | Define the 12-artifact green run criteria: all 5 presales artifacts, 6 delivery artifacts, and 1 automation bundle must pass format-check and LLM quality-check |  | Phase 3 acceptance gate; confirm sign-off authority (Marcus Patel, Daniel Park, or CTO)
IMPL-009 | Implementation Planning | Training | What training is required for Amatra consultants using the CLI and for administrators managing quotas and monitoring? | Identify training format: live workshop, recorded video, runbook documentation, or hands-on lab |  | Training scope affects Phase 3 timeline and knowledge-transfer deliverables
IMPL-010 | Implementation Planning | Go-Live Readiness | What are the go-live readiness criteria for the April PoC demonstration — specific metrics, artifact types, or stakeholder sign-offs? | Define the minimum viable demo: CLI auth flow, one full presales generation, one delivery generation, and one Terraform bundle with validate gate passing |  | Executive-sponsor demo script and acceptance criteria

## Risk & Constraints
Question ID | Category | Sub-Category | Question | Guidance | Customer Response | Notes
RISK-001 | Risk & Constraints | Project Risks | What is the risk if Bedrock model access for Claude Sonnet 4.6 and Claude Haiku 4.5 is not approved in us-west-2 before Phase 2 begins? | Identify the model access request process, approval lead time, and fallback model options if specific model IDs are unavailable |  | Model access approval is a hard dependency for Phase 2; a 2-4 week lead time could compress the Phase 2 window
RISK-002 | Risk & Constraints | Project Risks | What is the contingency plan if AgentCore Runtime is not generally available or has breaking API changes before the PoC deadline? | Identify fallback orchestration options: ECS-hosted Strands agents, Step Functions, or Lambda-direct invocation |  | AgentCore Runtime is a relatively new service; GA stability and regional availability should be confirmed early
RISK-003 | Risk & Constraints | Dependencies | Are there external dependencies on AWS Professional Services, Anthropic support, or third-party Strands Agents documentation that could introduce delays? | List all vendor or partner dependencies with expected response SLAs |  | Vendor dependency lead times should be mapped to the Phase 2 critical path
RISK-004 | Risk & Constraints | Constraints | Are there any organisational constraints on open-source library usage within the platform (e.g., Strands Agents framework licensing)? | Review open-source licence compliance requirements for Strands Agents, eof-tools, and any third-party Python dependencies in the container image |  | Licence risk could block deployment to production if legal review is required
RISK-005 | Risk & Constraints | Assumptions | Confirm that the eof-tools converter library is production-ready for all 12 artifact types and does not require significant refactoring for containerised execution. | Identify any known issues with eof-tools running in a headless Lambda/container environment (e.g., font rendering, LibreOffice dependencies for DOCX conversion) |  | eof-tools readiness is a critical Phase 2 assumption; undocumented dependencies (LibreOffice, fonts) in a container can cause significant rework