## Cover
Level of Effort
Generated: | June 10, 2026
Solution: | Tmp546Ryoep
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Stakeholders | Single business unit (~50 users) | ~120 employees; pre-sales + delivery + sales teams as primary users | Up to 50 users | 51–200 users | 200+ users | All internal Amatra staff; primary day-to-day users are pre-sales consultants
Regions / Geographies | Single AWS region | us-west-2 (United States data residency required) | 1 region | 2 regions | 3+ regions | SOC 2 and GDPR require all customer data resident in United States
Artifact Types | 3–4 standard artifact templates | 7+ artifact types (briefing; SoW; infra costs; LOE; detailed design; impl guide; Terraform) | 1–3 types | 4–6 types | 7+ types | Existing Word/Excel/PowerPoint templates must be ingested and automated
Integration Points | 1 identity provider | Okta to Amazon Cognito migration; Google Workspace (existing); legacy EC2 monolith retirement | 1 integration | 2–3 integrations | 4+ integrations | Legacy monolith to be retired; Okta identities migrated to Cognito
Environments | Dev + Prod | Dev / Staging / Prod (3 environments) with CI/CD pipeline | Dev + Prod | Dev + Staging + Prod | Dev + Staging + Prod + DR | Full IaC (Terraform) required for all environments
AI/ML Models | Single LLM integration | Amazon Bedrock (Claude models) for multi-artifact generation; async jobs 30–60 min | 1 model | 2–3 models | 4+ models / complex pipelines | Async long-running generation jobs must survive without dropping; per-user usage limits enforced
Compliance Frameworks | None specified | SOC 2 Type II + GDPR-aligned data handling | None | SOC 2 Type II | SOC 2 Type II + GDPR + additional frameworks | Security & Compliance Lead sign-off required; admin governance controls mandatory
SLA / Availability Target | 99.5% availability | 99.9% platform availability; <2 business day artifact turnaround | 99.5% | 99.9% | 99.99% | Hard deadline: platform live before 2027-01-31 flagship client renewal

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1.2 | Elevated due to Okta migration complexity, legacy monolith retirement, and multi-stakeholder alignment (CTO, VP Eng, Head of Solutions, Security Lead)
Planning | planning_factor | 1.3 | Increased for serverless architecture complexity: Bedrock async orchestration, multi-env IaC, SOC 2 controls design, and Cognito identity federation
Development | development_factor | 1.4 | Large-complexity multiplier for 7+ artifact pipeline automation, Lambda + API Gateway + DynamoDB + S3 + Bedrock integration, CI/CD, and Terraform modules
Testing | testing_factor | 1.2 | Covers functional, integration, performance (async 30–60 min jobs), security validation, and SOC 2 compliance testing
Deployment | deployment_factor | 1.1 | Phased rollout across 3 environments; includes Okta-to-Cognito identity migration cutover and legacy monolith decommission coordination
Training | training_factor | 1 | Standard knowledge transfer to pre-sales consultants, delivery team, and admins; includes runbook and SOP documentation
Management | management_factor | 1 | Project management overhead (10% of engineering tasks); status reporting to CTO and VP Engineering
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Kickoff | Kickoff meeting with CTO, VP Engineering, Head of Solutions, and Security Lead; align on scope and success criteria | Project Manager | 8 | 1.2 | 10 | 175
Discovery | Current State Assessment | Document legacy EC2 monolith capabilities, existing Google Workspace workflow, and manual artifact production process | Solutions Engineer | 24 | 1.2 | 29 | 200 |  |  | Kickoff complete
Discovery | Stakeholder Interviews | Conduct structured interviews with CTO, VP Engineering, Head of Solutions, Security Lead, Delivery Consulting, and Sales teams | Solution Architect | 32 | 1.2 | 38 | 225 |  |  | Current State Assessment
Discovery | Requirements Gathering | Document functional requirements for 7+ artifact types, usage-limit enforcement, admin governance, and async job handling | Solution Architect | 40 | 1.2 | 48 | 225 |  |  | Stakeholder Interviews
Discovery | AI/ML Feasibility Assessment | Assess Bedrock Claude model selection, prompt engineering strategy, artifact quality benchmarks, and async job architecture options | ML/AI Engineer | 32 | 1.2 | 38 | 275 |  |  | Requirements Gathering
Discovery | Okta Identity Assessment | Inventory Okta users, groups, and SSO integrations; define Cognito migration strategy and admin group structure | Security Engineer | 24 | 1.2 | 29 | 225 |  |  | Current State Assessment
Discovery | Compliance & Security Assessment | Assess SOC 2 Type II and GDPR requirements; document data residency, access control, and audit logging needs | Security Engineer | 32 | 1.2 | 38 | 225 |  |  | Requirements Gathering
Discovery | Gap Analysis | Identify gaps between manual process and automated platform; prioritise Phase 1 pre-sales MVP vs Phase 2 delivery and Terraform scope | Solution Architect | 16 | 1.2 | 19 | 225 |  |  | Requirements Gathering
Discovery | Cloud Readiness Assessment | Review existing AWS footprint, IAM posture, and service-limit quotas for Bedrock, Lambda, DynamoDB, S3, API Gateway, and Cognito in us-west-2 | Cloud Engineer | 16 | 1.2 | 19 | 200
Discovery | Assessment Report | Document findings and recommendations; present to CTO and VP Engineering for Phase 1 go/no-go sign-off | Technical Writer | 16 | 1.2 | 19 | 125 |  |  | All Discovery tasks
Planning | Detailed Architecture Design | Design end-to-end serverless architecture: API Gateway to Lambda orchestration to Bedrock to S3 artifact storage; async job patterns for 30–60 min generation | Solution Architect | 48 | 1.3 | 62 | 225 |  |  | Assessment Report
Planning | AWS Infrastructure Design | Design DynamoDB table schemas (solution state and usage tracking), S3 bucket structure, Lambda function topology, and API Gateway REST API | Cloud Engineer | 40 | 1.3 | 52 | 200 |  |  | Detailed Architecture Design
Planning | Cognito Identity Architecture | Design Cognito User Pool, identity federation from Okta, admins group structure, per-user usage limit enforcement, and OIDC/OAuth 2.0 flows | Security Engineer | 32 | 1.3 | 42 | 225 |  |  | Okta Identity Assessment
Planning | AI/ML Solution Design | Design Bedrock prompt templates for each artifact type, context window management, model selection (Claude 3 Sonnet/Opus), and output validation | ML/AI Engineer | 48 | 1.3 | 62 | 275 |  |  | AI/ML Feasibility Assessment
Planning | Security & Compliance Design | Design SOC 2 controls: encryption at rest and in transit, CloudTrail audit logging, IAM least-privilege, VPC endpoints, and GDPR data-handling policies | Security Engineer | 40 | 1.3 | 52 | 225 |  |  | Compliance & Security Assessment
Planning | IaC Terraform Module Design | Design Terraform module structure for all AWS services across dev, staging, and prod environments; define state backend with S3 and DynamoDB lock | DevOps Engineer | 32 | 1.3 | 42 | 200 |  |  | AWS Infrastructure Design
Planning | CI/CD Pipeline Design | Design GitHub Actions / CodePipeline CI/CD pipeline for Lambda deployments, Terraform plan/apply gates, and artifact template versioning | DevOps Engineer | 24 | 1.3 | 31 | 200 |  |  | IaC Terraform Module Design
Planning | Artifact Template Architecture | Analyse existing Word/Excel/PowerPoint templates; design automated template ingestion pipeline and output rendering strategy | Solutions Engineer | 32 | 1.3 | 42 | 200 |  |  | Requirements Gathering
Planning | Monitoring & Observability Design | Design CloudWatch dashboards, Lambda error alarms, Bedrock token-usage metrics, and end-to-end job-tracing strategy | DevOps Engineer | 16 | 1.3 | 21 | 200 |  |  | AWS Infrastructure Design
Planning | Design Documentation | Produce architecture decision records and detailed design document for CTO and Security Lead review | Technical Writer | 24 | 1.3 | 31 | 125 |  |  | All Planning tasks
Development | Cognito Setup & Okta Migration | Provision Cognito User Pool; execute Okta user and group migration; configure admin governance group; validate SSO flows | Security Engineer | 48 | 1.4 | 67 | 225 |  |  | Cognito Identity Architecture
Development | AWS Foundation Provisioning | Deploy Terraform modules: S3 buckets, DynamoDB tables, IAM roles and policies, VPC endpoints, CloudTrail, and KMS keys across dev/staging/prod | Cloud Engineer | 56 | 1.4 | 78 | 200 |  |  | IaC Terraform Module Design
Development | API Gateway & Lambda Core | Build REST API via API Gateway; implement Lambda functions for job submission, status polling, and artifact retrieval; wire Cognito authoriser | Solutions Engineer | 64 | 1.4 | 90 | 200 |  |  | AWS Foundation Provisioning
Development | Async Job Orchestration | Implement async generation pipeline using SQS and Step Functions for 30–60 min Bedrock jobs; dead-letter queue handling; idempotency and retry logic | Solutions Engineer | 56 | 1.4 | 78 | 200 |  |  | API Gateway & Lambda Core
Development | Bedrock Integration & Prompt Engineering | Integrate Lambda with Bedrock Claude; develop and tune prompt templates for all 7+ artifact types; implement context management and output parsing | ML/AI Engineer | 80 | 1.4 | 112 | 275 |  |  | AI/ML Solution Design; Async Job Orchestration
Development | Artifact Template Automation | Build template ingestion pipeline; implement Word/Excel/PowerPoint population from Bedrock output; validate formatting and cross-references | Solutions Engineer | 72 | 1.4 | 101 | 200 |  |  | Bedrock Integration & Prompt Engineering; Artifact Template Architecture
Development | DynamoDB Data Layer | Implement solution-state and usage-tracking DynamoDB access patterns; enforce per-user and global monthly usage limits; admin override API | Solutions Engineer | 40 | 1.4 | 56 | 200 |  |  | API Gateway & Lambda Core
Development | Usage Limit & Admin Governance | Build admin console endpoints: view/set per-user limits, global limits, audit log viewer; integrate with Cognito admins group authorisation | Solutions Engineer | 32 | 1.4 | 45 | 200 |  |  | DynamoDB Data Layer; Cognito Setup
Development | CI/CD Pipeline Build | Implement GitHub Actions / CodePipeline workflows for Lambda deployments and Terraform plan/apply; branch protection and automated test gates | DevOps Engineer | 48 | 1.4 | 67 | 200 |  |  | CI/CD Pipeline Design
Development | Monitoring & Observability Build | Deploy CloudWatch dashboards, Lambda alarms, Bedrock token-usage metrics, X-Ray tracing, and automated alerting to ops team | DevOps Engineer | 32 | 1.4 | 45 | 200 |  |  | AWS Foundation Provisioning
Development | Security Hardening | Implement SOC 2 controls: secrets in Secrets Manager, WAF on API Gateway, S3 bucket policies, encryption validation, and GDPR data-retention policies | Security Engineer | 40 | 1.4 | 56 | 225 |  |  | Security & Compliance Design
Development | Legacy Monolith Decommission Planning | Document legacy EC2 decommission runbook; plan data export, DNS cutover, and stakeholder communications | Solutions Engineer | 16 | 1.4 | 22 | 200 |  |  | AWS Foundation Provisioning
Development | Configuration Documentation | Document all Lambda configurations, API schemas, DynamoDB schemas, Bedrock model parameters, and environment variable inventory | Technical Writer | 32 | 1.4 | 45 | 125 |  |  | All Development tasks
Testing | Test Plan Development | Create comprehensive test plan covering functional, integration, async job, performance, security, and compliance test cases | QA Engineer | 16 | 1.2 | 19 | 150 |  |  | All Development tasks complete
Testing | Functional Testing | Execute functional test cases for each artifact type (7+); validate Bedrock output quality and template population accuracy | QA Engineer | 40 | 1.2 | 48 | 150 |  |  | Test Plan Development
Testing | Integration Testing | Test API Gateway to Lambda to Bedrock to S3 end-to-end; validate Cognito auth flows; test DynamoDB usage-limit enforcement | Solutions Engineer | 32 | 1.2 | 38 | 200 |  |  | Functional Testing
Testing | Async Job Performance Testing | Load-test async generation pipeline; validate 30–60 min job completion; test concurrent job handling and queue depth | Solutions Engineer | 24 | 1.2 | 29 | 200 |  |  | Integration Testing
Testing | Security & Compliance Testing | Execute OWASP API security tests; validate WAF rules; verify encryption; confirm CloudTrail audit completeness; collect SOC 2 evidence | Security Engineer | 32 | 1.2 | 38 | 225 |  |  | Security Hardening complete
Testing | Cognito & Auth Testing | Test Okta-migrated user login flows, admin group permissions, per-user limit enforcement, and token refresh/expiry | Security Engineer | 16 | 1.2 | 19 | 225 |  |  | Cognito Setup complete
Testing | Artifact Quality Validation | Validate generated artifacts against internal QA rubric; target 90%+ first-review pass rate; iterative prompt tuning based on results | ML/AI Engineer | 32 | 1.2 | 38 | 275 |  |  | Functional Testing
Testing | UAT Coordination | Coordinate UAT with Head of Solutions (pre-sales consultants as primary users) and Delivery Consulting team; manage feedback and defect triage | Project Manager | 24 | 1.2 | 29 | 175 |  |  | Functional Testing complete
Testing | Defect Resolution | Address and resolve defects identified during functional, integration, performance, and UAT phases | Solutions Engineer | 40 | 1.2 | 48 | 200 |  |  | All testing phases
Testing | Test Results Report | Document test results; capture SOC 2 evidence artefacts; obtain CTO and Security Lead sign-off for go-live | QA Engineer | 8 | 1.2 | 10 | 150 |  |  | All testing complete
Deployment | Go-Live Planning | Plan phased rollout: Phase 1 pre-sales MVP by 2026-09-30 and Phase 2 delivery and Terraform by 2026-12-15; define rollback procedures | Project Manager | 16 | 1.1 | 18 | 175 |  |  | Test Results Report signed off
Deployment | Staging Environment Validation | Validate full solution stack in staging environment prior to production promotion; smoke-test all artifact types | Solutions Engineer | 16 | 1.1 | 18 | 200 |  |  | Go-Live Planning
Deployment | Production Deployment Phase 1 | Deploy pre-sales generation MVP to production (Bedrock, Lambda, API Gateway, Cognito, S3, DynamoDB); cutover from manual process | Cloud Engineer | 24 | 1.1 | 26 | 200 |  |  | Staging Environment Validation
Deployment | Okta Decommission & Cognito Cutover | Execute final Okta-to-Cognito DNS/SSO cutover; communicate to all 120 users; monitor login success rate for 48 hours post-cutover | Security Engineer | 16 | 1.1 | 18 | 225 |  |  | Production Deployment Phase 1
Deployment | Legacy EC2 Decommission | Decommission legacy internal monolith EC2 instance; archive data; update DNS and internal documentation | Cloud Engineer | 8 | 1.1 | 9 | 200 |  |  | Okta Decommission & Cognito Cutover
Deployment | Production Deployment Phase 2 | Deploy delivery automation and Terraform generation modules; validate GA readiness for Q1 2027 | Cloud Engineer | 16 | 1.1 | 18 | 200 |  |  | Phase 1 stable in production
Deployment | Admin Training | Train Amatra admins on Cognito user management, usage limit configuration, and audit log review | Trainer | 16 | 1.1 | 18 | 150 |  |  | Production Deployment Phase 1
Deployment | Pre-Sales Consultant Training | Conduct hands-on training sessions for pre-sales consultants: brief submission, artifact review, and regeneration workflows | Trainer | 24 | 1.1 | 26 | 150 |  |  | Admin Training
Deployment | Delivery Team Enablement | Enable Delivery Consulting team on Phase 2 outputs: generated implementation guides and Terraform automation artifacts | Trainer | 16 | 1.1 | 18 | 150 |  |  | Production Deployment Phase 2
Deployment | Runbook Development | Create operational runbooks: Bedrock quota management, Lambda cold-start mitigation, DynamoDB scaling, incident response, and DR procedures | Technical Writer | 32 | 1.1 | 35 | 125 |  |  | All Deployment tasks
Deployment | As-Built Documentation Delivery | Deliver final as-built architecture documentation, API reference, data dictionary, and SOC 2 evidence package | Technical Writer | 24 | 1.1 | 26 | 125 |  |  | Runbook Development
Deployment | Hypercare Support | 8-week post-go-live hypercare: monitor platform health, resolve production issues, tune Bedrock prompts, and support pre-sales consultant adoption | Support Engineer | 80 | 1.1 | 88 | 150 |  |  | Production Deployment Phase 1
Deployment | Optimization Recommendations | Document post-hypercare optimization roadmap: cost optimisation, model upgrades, additional artifact types, and GA feature enhancements | Solution Architect | 16 | 1.1 | 18 | 225 |  |  | Hypercare Support
Deployment | Project Closeout | Project retrospective, lessons learned, final project report to CTO and VP Engineering; handover to steady-state operations team | Project Manager | 8 | 1.1 | 9 | 175 |  |  | All phases complete
Management | Technical Leadership | Quarterback technical oversight across all phases: architecture governance, Bedrock/AI quality review, escalation management | Solution Architect |  | 1 |  | 225 |  |  | All phases
Management | Project Management | Project coordination, status reporting to CTO and VP Engineering, risk management, change control, and stakeholder communications | Project Manager |  | 1 |  | 175 |  |  | All phases
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -15000 | AWS Partner Network (APN) Advanced Tier credit applied to professional services for solution architecture and implementation of AWS-native services (Bedrock, Lambda, API Gateway, DynamoDB, S3, Cognito)
AWS Bedrock Early Adopter Incentive | -5000 | AWS Bedrock partner implementation incentive for generative AI solutions; eligible as APN partner deploying Bedrock in a production customer workload
Implementation Volume Discount | -10000 | Volume discount on professional services for engagements exceeding $300K; applied as approximately 3% reduction on total professional services cost
TOTAL |  | Total professional services cost minus AWS Partner and volume discount credits (Year 1 only); infrastructure credits are excluded and reported in infrastructure-costs.csv