## Cover
Test Plan
Generated: | August 17, 2026
Solution: | Tmpy52K93Pk
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
FT-001 | Unit | Control Tower Deployment Validation | Validate AWS Control Tower is deployed and governing both us-east-1 and us-east-2 | Control Tower deployment complete and Management account access available | 1. Log in to AWS Console as PlatformAdministrator 2. Navigate to AWS Control Tower dashboard 3. Verify landing zone status shows Enrolled in us-east-1 4. Verify us-east-2 appears as a governed home region 5. Confirm all OUs show green compliance status | Control Tower dashboard shows active governance in both regions with zero drift detected | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Sec4-CT DD-Sec3-LZ SOW-Phase1 | Prerequisite for all subsequent tests
FT-002 | Unit | Seven-OU Hierarchy Validation | Validate all seven OUs are created with correct names and nesting under AWS Organizations | Control Tower deployed and AWS Organizations accessible | 1. Navigate to AWS Organizations console 2. Verify Root OU exists 3. Verify child OUs: Security; Infrastructure; Workloads-Prod; Workloads-NonProd; Sandbox; Suspended 4. Confirm no additional unplanned OUs are present | All seven OUs (Root; Security; Infrastructure; Workloads-Prod; Workloads-NonProd; Sandbox; Suspended) exist with correct parent-child relationships | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Sec4-OU SOW-Scope-OU | Verify OU nesting matches detailed design Section 4
FT-003 | Unit | SCP Policy Attachment Validation | Validate all required Service Control Policies are attached to the correct OUs | SCPs deployed via Terraform and AWS Organizations console accessible | 1. Navigate to AWS Organizations > Policies > Service Control Policies 2. Verify ins-scp-deny-root is attached at Root OU 3. Verify ins-scp-restrict-regions is attached at Root OU 4. Verify ins-scp-cloudtrail-lock is attached at Root OU 5. Verify ins-scp-mfa-required is attached at Root OU 6. Verify Sandbox OU SCP relaxations are correctly scoped | All four root-level SCPs attached and active; Sandbox OU has reduced SCP set; Suspended OU has deny-all SCP; no SCP attachment errors | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec4-SCP SOW-Sec6-Preventative | Test each SCP individually via IAM Policy Simulator
FT-004 | Unit | RCP Data Perimeter Validation | Validate Resource Control Policy prevents S3 writes to buckets outside the AWS Organization boundary | RCP deployed and test IAM role in member account configured | 1. Assume a member account IAM role via IAM Identity Center 2. Attempt to write an S3 object to an external S3 bucket outside the Organization 3. Attempt to write an S3 object to the internal Log Archive bucket 4. Verify results for both attempts | External S3 write denied with AccessDenied error; internal write blocked by bucket policy as expected; no data exfiltration path exists | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec4-RCP SOW-Sec6-Preventative | Use a dedicated test bucket outside the Org for the external write attempt
FT-005 | Integration | IAM Identity Center SSO Login Flow | Validate end-to-end SSO login and cross-account access for all defined permission sets | IAM Identity Center configured and identity source integrated and test users assigned to permission sets | 1. Navigate to IAM Identity Center access portal URL 2. Authenticate as test user with valid MFA 3. Verify account list shows assigned AWS accounts 4. Select PlatformAdministrator role in a Platform account 5. Select WorkloadAdministrator role in a workload account 6. Select SecurityAuditor role across multiple accounts 7. Verify console session starts for each role | SSO portal accessible; MFA prompted and validated; each permission set generates a valid scoped console session; session duration capped at 8 hours | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec5-Roles SOW-Sec7-IAM | Test all five permission sets: PlatformAdministrator; WorkloadAdministrator; SecurityAuditor; NetworkOperator; FinOps
FT-006 | Integration | MFA Enforcement SCP Test | Validate SCP denies AWS console access when MFA is not registered or is absent | Test IAM Identity Center user without MFA registered and SCP active | 1. Attempt AWS console access with a test user with no MFA device registered 2. Verify SCP evaluation result via CloudTrail 3. Register MFA for the test user 4. Attempt console access again 5. Verify successful access with MFA | Console access denied when MFA is not present; CloudTrail records SCPDenied event; access granted after MFA registration and authentication | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-IAM SOW-Sec7-IAM SOW-Sec6-Preventative | Log SCP deny event in CloudTrail for audit evidence
FT-007 | Integration | CloudTrail Organisation Trail Validation | Validate CloudTrail organisation trail delivers management events to Log Archive S3 in both regions | Log Archive S3 bucket provisioned and CloudTrail org trail configured | 1. Perform a test API call in us-east-1 from a member account 2. Perform a test API call in us-east-2 from a member account 3. Wait up to 15 minutes for log delivery 4. Navigate to Log Archive S3 bucket and verify log files present for both regions 5. Validate CloudTrail log file integrity using digest files | CloudTrail log files appear in Log Archive S3 within 15 minutes for both regions; digest file validation confirms no tampering; events include correct accountId and eventSource | Critical | Integration | QA Engineer | Not Started | Not Executed | DD-Sec5-Audit DD-Sec4-Logging SOW-SuccessMetrics | Verify S3 Object Lock is active on the Log Archive bucket
FT-008 | Integration | AWS Config Recording Validation | Validate AWS Config is recording resource configurations in all accounts and both regions | Config recording enabled via AFT customisation and Log Archive S3 configured as delivery target | 1. Deploy a test security group in a workload account in us-east-1 2. Deploy a test security group in the same account in us-east-2 3. Wait up to 15 minutes for Config snapshot delivery 4. Navigate to AWS Config console in both regions 5. Verify configuration items appear for the test resources 6. Verify Config delivery to Log Archive S3 succeeds | Config recording active in both regions for all accounts; configuration items created within 15 minutes; delivery to Log Archive S3 confirmed; no delivery failures in CloudWatch | High | Integration | QA Engineer | Not Started | Not Executed | DD-Sec5-Compliance SOW-SuccessMetrics SOW-Scope-Config | Verify using Config delivery channel status page
FT-009 | Integration | Centralised Logging Account Isolation | Validate Log Archive and Audit accounts cannot be accessed by workload administrators | Log Archive and Audit accounts provisioned and SCP and IAM Identity Center assignments configured | 1. Attempt to log in to Log Archive account using WorkloadAdministrator permission set 2. Attempt to log in to Audit account using WorkloadAdministrator permission set 3. Attempt to access Log Archive S3 bucket from a workload account IAM role 4. Log in with PlatformAdministrator and verify access succeeds | WorkloadAdministrator access to Log Archive and Audit accounts denied; PlatformAdministrator and SecurityAuditor access succeeds; no cross-account S3 access from workload roles | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec4-LogArchive SOW-Sec7-IAM | Confirms isolation of Security OU per detailed design
FT-010 | System | AFT Account Vending End-to-End Flow | Validate complete AFT pipeline execution vends a new account enrolled in Control Tower with all baseline customisations | AFT pipeline deployed and Terraform Cloud workspace active and test account request Terraform file prepared | 1. Commit a new account request .tf file to the AFT account requests repository 2. Monitor CodePipeline execution in the Management account 3. Record start time of pipeline execution 4. Verify CodeBuild stages complete without error 5. Verify new account appears in AWS Organizations and Control Tower 6. Verify AFT customisations applied: spoke VPC; TGW attachment; GuardDuty enrolled; Security Hub enrolled; Budget alerts set; mandatory tags present 7. Record end time and calculate total vending duration | New account vended and enrolled in Control Tower within 30 minutes; all AFT customisations applied; no CodePipeline stage failures | Critical | System | QA Lead | Not Started | Not Executed | DD-Sec4-AFT DD-Sec4-Workload SOW-SuccessMetrics | Repeat 3 consecutive times to satisfy go-live success metric per SOW
FT-011 | System | Transit Gateway Spoke-to-Spoke Routing | Validate traffic between two spoke VPCs routes through the Network Hub Network Firewall | Two spoke VPCs attached to TGW and Network Firewall deployed and TGW route tables configured per design | 1. Deploy a test EC2 instance in Spoke VPC A in workload account 1 in us-east-1 2. Deploy a test EC2 instance in Spoke VPC B in workload account 2 in us-east-1 3. Send ICMP traffic from Instance A to Instance B 4. Capture VPC Flow Logs and Network Firewall alert logs 5. Verify traffic traverses the Network Firewall endpoint 6. Verify spoke-to-spoke traffic follows the Inspection Route Table path | Traffic between spoke VPCs routes through Network Firewall endpoint in Network Hub VPC; VPC Flow Logs confirm inspection path; permitted traffic forwarded; denied traffic logged in Firewall alert logs | Critical | System | QA Lead | Not Started | Not Executed | DD-Sec6-Network DD-Sec4-TGW SOW-Phase2 | Repeat with east-west deny test to verify default-deny firewall stance
FT-012 | System | Centralised NAT Gateway Egress | Validate internet-bound egress from spoke VPCs routes through the centralised NAT Gateway in the Network Hub account | Spoke VPC deployed and TGW and NAT Gateway configured and no Internet Gateway in spoke VPC | 1. Deploy a test EC2 instance in a spoke VPC with no Internet Gateway 2. Attempt an outbound HTTPS request to a public internet endpoint 3. Verify the source IP of the outbound request matches the NAT Gateway Elastic IP 4. Verify the traffic appears in Network Firewall north-south logs | Internet egress succeeds; source IP matches centralised NAT Gateway EIP not a spoke-VPC address; traffic recorded in Network Firewall north-south logs; spoke VPC has no direct internet path | High | System | QA Lead | Not Started | Not Executed | DD-Sec6-Network DD-Sec4-NATGateway SOW-Phase2 | Confirms no internet gateway bypass possible in spoke accounts
FT-013 | System | Site-to-Site VPN Connectivity | Validate VPN tunnel establishment and routing between Network Hub account and on-premises gateway in both regions | On-premises gateway configured and VPN connections created in Network Hub account for both regions | 1. Verify both VPN tunnels in us-east-1 show UP status in AWS Console 2. Verify both VPN tunnels in us-east-2 show UP status 3. Verify BGP routes are propagated on both tunnels 4. Send test traffic from a spoke VPC to an on-premises test host 5. Verify on-premises route table shows AWS CIDR blocks via VPN | Both VPN tunnels UP in both regions; BGP routes propagated; test traffic reaches on-premises host from AWS spoke VPC; baseline latency documented | High | Integration | QA Engineer | Not Started | Not Executed | DD-Sec6-VPN DD-Sec4-VPN SOW-Phase2 | Document baseline latency for DR planning; test tunnel failover procedure
FT-014 | Integration | Security Hub FSBP Compliance Score | Validate Security Hub is enabled in all accounts with FSBP standard and findings aggregate to Audit account | Security Hub enabled via AFT customisation and Audit account configured as delegated administrator | 1. Log in to Audit account as SecurityAuditor 2. Navigate to Security Hub > Summary 3. Verify FSBP standard is active for all member accounts 4. Verify findings from all member accounts aggregate in the Audit account 5. Record overall FSBP compliance score 6. Verify zero CRITICAL findings in Production and Platform accounts | Security Hub FSBP active in all accounts; findings aggregate from all accounts and both regions to Audit account; FSBP compliance score >= 80% at go-live; zero CRITICAL findings in Production and Platform accounts | Critical | Integration | Security Engineer | Not Started | Not Executed | DD-Sec5-Compliance SOW-SuccessMetrics SOW-Sec7-Compliance | Hard go-live gate; score below 80% blocks go-live
FT-015 | Integration | GuardDuty Organisation-Wide Deployment | Validate GuardDuty is enabled in all accounts and both regions with the Audit account as delegated administrator | GuardDuty enabled via AFT and delegated administrator configured in Audit account | 1. Log in to Audit account as SecurityAuditor 2. Navigate to GuardDuty > Accounts 3. Verify all member accounts show Enabled in us-east-1 4. Verify all member accounts show Enabled in us-east-2 5. Verify Audit account is the delegated administrator 6. Generate a test finding and verify it appears in the Audit account | GuardDuty active org-wide in both regions; all accounts show Enabled status; Audit account is delegated admin; test finding visible in Audit account console within 5 minutes | Critical | Integration | Security Engineer | Not Started | Not Executed | DD-Sec5-GuardDuty SOW-Sec7-Monitoring SOW-Sec6-Detective | Verify SNS alert fires for High-severity test finding
FT-016 | Regression | IaC Drift Detection Validation | Validate that Terraform drift detection identifies any manual console change in a Production account | A Production workload account provisioned and Terraform state current and CI/CD pipeline active | 1. Note the current Terraform state for a production security group resource 2. Manually modify the security group via AWS Console to add an inbound rule 3. Run terraform plan against the production workspace 4. Verify terraform plan shows the manual change as drift 5. Revert the change via terraform apply 6. Confirm production state matches IaC configuration | Terraform plan detects drift; drift alert raised; IaC state is authoritative and re-apply corrects the drift; zero manual changes remain after apply | High | System | QA Engineer | Not Started | Not Executed | DD-Sec4-Principles DD-Sec9-IaC SOW-SuccessMetrics | Confirms >= 95% IaC coverage requirement; perform in NonProd OU first

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
NFT-001 | Performance | AFT Account Vending SLA Validation | Validate AFT pipeline vends a guardrail-enrolled account in under 30 minutes across three consecutive test runs | AFT pipeline deployed and Terraform Cloud workspace active and three distinct test account request files prepared | 1. Commit test account request file #1 to AFT account requests repo 2. Record exact pipeline start time from CodePipeline 3. Monitor all pipeline stages to completion 4. Record end time and calculate elapsed duration for Run 1 5. Repeat steps 1-4 for test account request files #2 and #3 6. Document elapsed time for each run | All three consecutive runs complete in under 30 minutes; zero pipeline failures across all three runs; results documented in Test Results Report | Critical | System | Performance Engineer | Not Started | Not Executed | DD-Sec2-SLA DD-Sec4-AFT SOW-SuccessMetrics SOW-Sec8-Performance | Hard go-live gate per SOW success metrics; any run over 30 min is a failure
NFT-002 | Performance | Network Firewall Baseline Throughput | Measure baseline Network Firewall throughput in both regions and document for capacity planning | Network Firewall deployed in us-east-1 and us-east-2 and test EC2 instances in spoke VPCs | 1. Deploy two test EC2 instances in separate spoke VPCs in us-east-1 with traffic routed through firewall 2. Run iPerf3 sustained throughput test for 5 minutes 3. Record throughput and packet rate and drop count from Network Firewall metrics 4. Repeat test in us-east-2 5. Document baseline metrics in Network Testing Report | Baseline throughput measured and documented; Network Firewall drop rate equals zero for permitted traffic; results documented for future workload capacity planning | High | System | Performance Engineer | Not Started | Not Executed | DD-Sec6-Firewall DD-Sec9-HA SOW-Sec8-Performance | Baseline documentation only; no hard pass/fail throughput threshold for this test
NFT-003 | Performance | Transit Gateway Inter-Region Latency Baseline | Measure and document baseline latency between us-east-1 and us-east-2 via TGW inter-region peering | TGW inter-region peering active and test instances in both regions | 1. Deploy test EC2 instances in Network Hub VPCs in us-east-1 and us-east-2 2. Run continuous ping test for 5 minutes across TGW inter-region peering 3. Record average and minimum and maximum and 95th percentile round-trip latency 4. Document results in Network Testing Report | Latency baseline documented; typical us-east-1 to us-east-2 inter-region latency expected below 20ms; results used as DR failover planning baseline | High | System | Performance Engineer | Not Started | Not Executed | DD-Sec6-Network DD-Sec9-DR SOW-Sec8-Performance | Baseline documentation only; no hard latency threshold for this test
NFT-004 | Performance | CloudTrail Log Delivery Latency | Validate CloudTrail delivers management events to Log Archive S3 within 15 minutes of the API call | CloudTrail org trail active and Log Archive S3 configured and CloudWatch metric for log delivery active | 1. Record current timestamp T0 2. Execute a test API call in a member account 3. Monitor S3 Log Archive bucket for new log file delivery 4. Record timestamp T1 when log file containing the test event appears 5. Calculate delivery latency as T1 minus T0 6. Repeat 5 times at different times of day | CloudTrail log delivery latency under 15 minutes for all 5 test runs; average latency documented; CloudWatch metric shows no delivery failures | High | Integration | QA Engineer | Not Started | Not Executed | DD-Sec2-SLA DD-Sec5-Audit SOW-SuccessMetrics | Part of Log Archive SLA validation; 15-minute RPO depends on this test
NFT-005 | Security | SCP Deny-Root Enforcement | Validate SCP prevents root account actions across all member accounts | Root credentials sealed in Secrets Manager and SCP ins-scp-deny-root active at Root OU | 1. In a test member account attempt to perform an action using root account credentials 2. Verify the action is denied by SCP 3. Review CloudTrail for the SCPDenied error 4. Verify the denial event is logged with correct errorCode and errorMessage | Root account actions in all member accounts denied by SCP; CloudTrail records SCPDenied event for each attempt; no root-initiated resource changes succeed | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec4-SCP SOW-Sec7-Preventative | Use a dedicated test account in NonProd OU; do not test in Production
NFT-006 | Security | SCP Region Restriction Enforcement | Validate SCP prevents API calls to AWS regions other than us-east-1 and us-east-2 | SCP ins-scp-restrict-regions active and test IAM Identity Center user available | 1. Assume a WorkloadAdministrator role in a test member account 2. Attempt to create a resource in us-west-2 3. Attempt to create a resource in eu-west-1 4. Attempt to create a resource in us-east-1 which should succeed 5. Verify CloudTrail shows SCPDenied for us-west-2 and eu-west-1 attempts | API calls to all regions except us-east-1 and us-east-2 denied by SCP; CloudTrail SCPDenied events recorded for all out-of-region attempts; us-east-1 resource creation succeeds | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-Compliance DD-Sec4-SCP SOW-Sec7-DataResidency | Critical for US data residency compliance requirement
NFT-007 | Security | SCP CloudTrail and Config Lock Enforcement | Validate SCP prevents disabling of CloudTrail or Config recording in any member account | SCP ins-scp-cloudtrail-lock active and CloudTrail and Config recording active in member accounts | 1. Assume a WorkloadAdministrator role in a test member account 2. Attempt to stop the CloudTrail trail via StopLogging API 3. Attempt to delete the CloudTrail trail via DeleteTrail API 4. Attempt to stop Config recording via StopConfigurationRecorder API 5. Verify all attempts are denied by SCP | CloudTrail stop and delete and Config stop actions all denied by SCP for non-PlatformAdministrator roles; CloudTrail records SCPDenied events; logging remains uninterrupted | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-IAM DD-Sec4-SCP SOW-Sec7-Preventative | Evidence for SOC 2 CC7.2 audit logging requirement
NFT-008 | Security | S3 Log Archive Object Lock Validation | Validate S3 Object Lock prevents deletion or modification of CloudTrail log files within the retention period | Log Archive S3 bucket with Object Lock compliance mode active and CloudTrail log files present | 1. Identify a CloudTrail log file in the Log Archive S3 bucket 2. Attempt to delete the log file using PlatformAdministrator credentials 3. Attempt to overwrite the log file with modified content 4. Verify the Object Lock retention date on the file confirms 90-day minimum | Log file deletion denied with Object Lock compliance mode error; file overwrite denied; Object Lock expiry date confirms 90-day minimum retention; MFA-Delete active on bucket | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-DataProtection DD-Sec4-LogArchive SOW-Sec7-Compliance | Satisfies SOC 2; HIPAA; and NIST 800-53 AU-9 audit trail immutability requirement
NFT-009 | Security | Encryption at Rest and in Transit Validation | Validate all Log Archive S3 data is encrypted at rest and all API communication is TLS-encrypted | Log Archive S3 configured and CloudTrail delivering logs | 1. Inspect Log Archive S3 bucket default encryption settings 2. Verify SSE-S3 AES-256 is enforced as default encryption 3. Check S3 bucket policy for aws:SecureTransport condition 4. Attempt an HTTP non-TLS PUT request to the S3 bucket 5. Verify EBS volumes in shared accounts have encryption-by-default via Config rule | S3 bucket shows SSE-S3 encryption active; aws:SecureTransport condition rejects all HTTP requests; Config rule ec2-ebs-encryption-by-default shows COMPLIANT for all shared accounts | Critical | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-DataProtection SOW-Sec7-Encryption | Verify KMS key rotation enabled for all customer-managed keys
NFT-010 | Security | IAM Access Analyser No External Access Findings | Validate IAM Access Analyser reports zero external-access findings in Production and Platform accounts | IAM Access Analyser enabled in all accounts via Security Hub FSBP and Audit account aggregation active | 1. Navigate to IAM Access Analyser in Audit account 2. Review all findings across Production and Platform account zones of trust 3. Verify no external-access findings exist for resources accessible from outside the Organisation 4. Document any findings in NonProd or Sandbox for risk acceptance | Zero external-access findings in Production and Platform accounts; any findings in NonProd or Sandbox documented and risk-accepted by Client Security Lead | High | Security | Security Engineer | Not Started | Not Executed | DD-Sec5-Compliance DD-Sec5-SIEM SOW-Sec7-Compliance | External-access findings reduce FSBP compliance score
NFT-011 | Reliability | Network Firewall Multi-AZ Failover | Validate Network Firewall continues to pass traffic when one Availability Zone endpoint becomes unavailable | Network Firewall deployed in two AZs per region and traffic flowing through both AZ endpoints | 1. Record baseline spoke-to-spoke traffic throughput through the firewall 2. Simulate AZ-a endpoint failure by modifying the TGW route table to remove the AZ-a firewall endpoint 3. Verify traffic re-routes to AZ-b firewall endpoint 4. Measure time to re-route and traffic interruption duration 5. Restore AZ-a routing and verify traffic returns to dual-AZ distribution | Traffic re-routes to surviving AZ endpoint within 30 minutes; zero traffic loss after route reconvergence; Network Firewall metrics show no sustained drop rate increase; restoration to dual-AZ succeeds | High | System | QA Lead | Not Started | Not Executed | DD-Sec9-HA DD-Sec6-Firewall SOW-Sec9-DR | Test in us-east-1; repeat in us-east-2; document actual failover time
NFT-012 | Reliability | IaC Landing Zone Rebuild RTO Validation | Validate the landing zone can be rebuilt from Terraform state and AFT configuration within 4 hours | All Terraform workspaces in a known clean state and Terraform Cloud accessible and AFT repo available | 1. In a non-production test account simulate a component failure by destroying a defined resource subset via terraform destroy 2. Record start time 3. Execute terraform apply from current Terraform state to rebuild destroyed resources 4. Verify all resources recreated and healthy 5. Record end time and calculate elapsed duration | Complete resource rebuild from IaC state completes within 4 hours; all rebuilt resources match the current Terraform configuration; no manual intervention required; elapsed time documented | High | System | QA Lead | Not Started | Not Executed | DD-Sec9-DR DD-Sec9-Backup SOW-Sec6-DR | Test against a representative resource subset; full org rebuild is theoretical
NFT-013 | Reliability | Log Archive S3 Cross-Region Replication | Validate S3 CRR replicates Log Archive objects from us-east-1 to us-east-2 within the RPO target | S3 CRR configured on Log Archive bucket and us-east-2 replica bucket active | 1. Deliver a test CloudTrail log file to the us-east-1 Log Archive S3 bucket 2. Record the delivery timestamp 3. Monitor the us-east-2 replica bucket for the replicated object 4. Record the replication completion timestamp 5. Calculate replication lag | Log Archive objects replicated from us-east-1 to us-east-2 within 15 minutes; replication lag documented; Object Lock settings preserved on replicated objects | High | Reliability | QA Engineer | Not Started | Not Executed | DD-Sec9-DR DD-Sec9-Backup SOW-Sec6-DR | Verify Object Lock compliance mode is maintained on the us-east-2 replica
NFT-014 | Compliance | AWS Budgets Alert Delivery Validation | Validate per-account AWS Budget alerts fire at 80% and 100% spend thresholds for all accounts | AWS Budgets configured via AFT customisation on all accounts and SNS alerting topic active | 1. Log in to Management account as PlatformAdministrator 2. Navigate to AWS Budgets for a test workload account 3. Verify a budget exists with 80% threshold alert configured 4. Verify a budget exists with 100% threshold alert configured 5. Verify SNS topic is assigned as the alert notification target 6. Verify alert notification email is configured on the SNS topic | 80% and 100% budget alerts exist for all accounts; SNS topic correctly associated; email recipient confirmed; alert notification test delivery succeeds | High | Integration | QA Engineer | Not Started | Not Executed | DD-Sec9-Cost SOW-SuccessMetrics SOW-Sec6-FinOps | Verify all vended accounts have Budget alerts as part of go-live checklist
NFT-015 | Compliance | CloudWatch SNS Alert Routing for Critical Findings | Validate EventBridge rules route Security Hub CRITICAL and GuardDuty High-severity findings to SNS with email delivery | Security Hub and GuardDuty and EventBridge rules and SNS topic deployed in Audit account | 1. In the Audit account create a test Security Hub finding with Severity.Label = CRITICAL via the Security Hub API 2. Monitor EventBridge rule for finding match 3. Verify SNS message published to the alerting topic 4. Verify email notification received by the configured recipient 5. Repeat with a test GuardDuty finding of severity 7.0 or higher | EventBridge rule triggers on CRITICAL Security Hub finding; SNS message published within 2 minutes; email delivered to operations team; GuardDuty high-severity finding also triggers alert; DLQ remains empty | Critical | Integration | Security Engineer | Not Started | Not Executed | DD-Sec9-Alerting DD-Sec6-EventBridge SOW-Sec6-Responsive | Confirms go-live readiness for P1 incident escalation path
NFT-016 | Compliance | VPC IPAM /20 CIDR Auto-Allocation | Validate VPC IPAM automatically allocates a /20 CIDR from the correct regional pool when a spoke VPC is provisioned via AFT | VPC IPAM configured with 10.0.0.0/8 supernet and regional pools for us-east-1 and us-east-2 defined | 1. Submit an AFT account request targeting the Workloads-NonProd OU 2. Verify AFT customisation creates a spoke VPC in us-east-1 3. Verify the VPC CIDR is a /20 block within the 10.0.0.0/10 us-east-1 pool 4. Verify no IP overlap with any existing VPC CIDR in the IPAM console 5. Verify TGW attachment is created for the new spoke VPC | Spoke VPC receives a unique /20 CIDR from the correct regional IPAM pool; no CIDR overlap with existing VPCs; IPAM allocation record shows the new VPC; TGW attachment visible in Network Hub account | High | Integration | QA Engineer | Not Started | Not Executed | DD-Sec6-IPAM DD-Sec4-AFT SOW-Sec6-Networking | Verify IPAM pool utilisation is reported correctly; address-space exhaustion testing is out of scope

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Owner | Status | Pass/Fail | Requirements Traced | Notes
UAT-001 | Business Process | End-to-End Account Vending by Client IT Owner | Validate that the Client IT Owner can independently vend a new AWS account via the AFT pipeline without vendor assistance | AFT pipeline operational and Client IT Owner trained and Terraform Cloud access granted | 1. Client IT Owner logs in to Terraform Cloud and accesses the AFT account requests repository 2. Client IT Owner creates a new account request .tf file for a test workload account targeting Workloads-NonProd OU 3. Client IT Owner commits the file and triggers the AFT pipeline 4. Client IT Owner monitors the CodePipeline execution to completion 5. Client IT Owner validates the new account in Control Tower console 6. Client IT Owner verifies mandatory tags and budget alerts on the new account | Client IT Owner independently vends a new account in under 30 minutes without vendor assistance; account enrolled in Control Tower; all AFT customisations verified; Client IT Owner confirms process is clear and repeatable | Critical | UAT | Client IT Owner | Not Started | Not Executed | DD-Sec10-Handover SOW-Sec9-Handover SOW-UAT-AFT | Primary go-live gate; UAT sign-off is blocked until this test passes
UAT-002 | Business Process | Security Hub Dashboard Review and Finding Triage | Validate that the Client Security Lead can navigate Security Hub and interpret the FSBP score and perform a finding triage workflow | Security Hub operational and FSBP findings present in Audit account and Security Hub triage runbook delivered | 1. Client Security Lead logs in to Audit account via IAM Identity Center as SecurityAuditor 2. Client Security Lead navigates to Security Hub > Summary 3. Client Security Lead records the FSBP compliance score and verifies it is at or above 80% 4. Client Security Lead opens the Findings view and filters for CRITICAL severity 5. Client Security Lead follows the triage runbook to suppress a known-acceptable finding with a justification note 6. Client Security Lead verifies the finding is moved to SUPPRESSED status | Security Lead successfully navigates Security Hub independently; FSBP score at or above 80% confirmed; finding triage workflow completed per runbook; SUPPRESSED finding updated with justification; Security Lead confirms runbook is actionable | Critical | UAT | Client Security Lead | Not Started | Not Executed | DD-Sec10-Handover SOW-UAT SOW-Sec9-KT | Tests independence from vendor team; required for go-live sign-off
UAT-003 | Business Process | GuardDuty Alert Investigation Walkthrough | Validate that the Client Security Lead can investigate a GuardDuty finding and follow the escalation workflow defined in the runbook | GuardDuty operational and test finding generated and GuardDuty alert investigation runbook delivered | 1. Client Security Lead logs in to Audit account and navigates to GuardDuty > Findings 2. Client Security Lead locates the test High-severity finding 3. Client Security Lead follows the GuardDuty alert investigation runbook: reviews finding details; checks CloudTrail events for the affected resource; assesses blast radius 4. Client Security Lead documents investigation notes and marks the finding as reviewed 5. Client Security Lead identifies the correct escalation contact per the runbook | Security Lead completes GuardDuty investigation workflow independently; CloudTrail Lake query executed to support investigation; finding marked reviewed with notes; escalation path confirmed as understood | High | UAT | Client Security Lead | Not Started | Not Executed | DD-Sec10-Handover SOW-UAT SOW-Sec9-KT | Validates SOW Section 9 Knowledge Transfer Security Operations Track
UAT-004 | Business Process | CloudTrail Lake Investigation Query | Validate that the Client Security Lead can run a CloudTrail Lake investigation query in the Audit account to retrieve audit evidence | CloudTrail Lake event data store active and sample queries delivered in runbook and test events present in data store | 1. Client Security Lead logs in to Audit account as SecurityAuditor 2. Client Security Lead navigates to CloudTrail > Lake > Event data stores 3. Client Security Lead opens the CloudTrail Lake query editor 4. Client Security Lead runs the pre-built query for all console login events in the last 24 hours 5. Client Security Lead verifies query results include their own recent login events 6. Client Security Lead exports query results as CSV | CloudTrail Lake query returns results within 60 seconds; console login events visible for the past 24 hours; export to CSV succeeds; Client Security Lead confirms this is usable for audit evidence extraction | High | UAT | Client Security Lead | Not Started | Not Executed | DD-Sec5-Audit DD-Sec10-Handover SOW-Sec9-KT | Validates SOC 2 CC7.2 and HIPAA Section 164.312(b) audit capability
UAT-005 | Business Process | IAM Identity Center Cross-Account Navigation | Validate that Client team members can log in via SSO and navigate to their assigned AWS accounts using correct permission sets | IAM Identity Center configured and client team users assigned to groups and permission sets and training completed | 1. Client IT team member navigates to the IAM Identity Center access portal URL 2. User authenticates with credentials and MFA device 3. User views the list of assigned AWS accounts and roles 4. User selects the Workloads-Prod account with WorkloadAdministrator role and verifies console access 5. User selects the Audit account with SecurityAuditor role and verifies read-only access 6. User attempts a write action in the Audit account which should be denied 7. User verifies console session terminates after 8 hours | Users successfully authenticate via SSO with MFA; account list reflects correct assignments; WorkloadAdministrator provides expected access; SecurityAuditor is read-only in Audit account; write attempt denied; session expires at 8 hours | High | UAT | Client IT Owner | Not Started | Not Executed | DD-Sec5-IAM DD-Sec10-Handover SOW-UAT | Tests day-to-day access workflow for all client team members
UAT-006 | Business Process | CloudWatch Dashboards Operational Review | Validate that Client IT Owner can review the three CloudWatch dashboards and interpret the key landing zone health indicators | CloudWatch dashboards deployed in Shared Services account and monitoring data populated | 1. Client IT Owner logs in to Shared Services account as PlatformAdministrator 2. Client IT Owner opens Landing Zone Operations Dashboard and reviews Control Tower compliance and account count and AFT pipeline health and VPN tunnel status 3. Client IT Owner opens Security Posture Dashboard and reviews Security Hub FSBP score and GuardDuty finding volume and Config compliance score 4. Client IT Owner opens FinOps Dashboard and reviews organisation-wide cost trend and top accounts by spend and Budget alert status 5. Client IT Owner identifies at least one operational metric on each dashboard | All three dashboards load with current data; Client IT Owner correctly identifies green Control Tower compliance and FSBP score at or above 80% and budget alert status for all accounts; Client IT Owner confirms dashboards are sufficient for day-to-day operations | High | UAT | Client IT Owner | Not Started | Not Executed | DD-Sec9-Monitoring DD-Sec10-Handover SOW-Sec9-KT | Validates SOW Section 9 Knowledge Transfer Cloud Infrastructure Track Session 3
UAT-007 | Business Rules | Runbook Completeness and Accuracy Review | Validate that all six operational runbooks are complete and accurate and usable by the Client IT Owner and Security Lead independently | All six runbooks delivered and Client IT Owner and Security Lead have reviewed draft versions | 1. Client IT Owner reviews the Account Vending via AFT runbook and confirms all steps are actionable without vendor assistance 2. Client Security Lead reviews the Security Hub finding triage runbook and confirms escalation contacts and suppression steps are clear 3. Client IT Owner reviews the SCP policy change process runbook and confirms the dual-approval workflow is documented 4. Client Security Lead reviews the Incident Response runbook and confirms P1 escalation path is correct 5. Both stakeholders document any gaps or corrections needed | All six runbooks reviewed and accepted; Client IT Owner and Security Lead sign off that runbooks are complete and usable; any identified gaps resolved before go-live sign-off; no placeholder text or TBD items remain in runbooks | Critical | UAT | Client IT Owner | Not Started | Not Executed | DD-Sec10-Handover SOW-Deliverable22 SOW-UAT | Runbooks are a go-live gate deliverable; P1 issues here block go-live
UAT-008 | Acceptance | Go-Live Readiness Checklist Completion | Validate all 12 items on the Go-Live Readiness Checklist are confirmed pass before go-live is authorised | All functional and non-functional tests complete and all P1 UAT issues resolved and all deliverables submitted | 1. Vendor PM and Client IT Owner jointly review the 12-item Go-Live Readiness Checklist 2. For each item verify status using test evidence: all accounts in Control Tower green; CloudTrail org trail active; Security Hub FSBP at or above 80%; zero critical findings; GuardDuty active; AFT validated under 30 min across 3 runs; 2 workload accounts vended; rollback documented; team trained; runbooks delivered; break-glass access confirmed; Budget alerts active 3. Both parties sign the Go-Live Readiness Checklist 4. Client Executive Sponsor countersigns the UAT Sign-Off Document | All 12 checklist items confirmed pass; Go-Live Readiness Checklist signed by Vendor PM and Client IT Owner; UAT Sign-Off Document signed by Client Executive Sponsor and Client IT Owner; no P1 issues outstanding | Critical | UAT | Client Executive Sponsor | Not Started | Not Executed | DD-Sec2-Success SOW-Sec8-GoLive SOW-Deliverable21 | This test closes the entire test programme and its pass is the formal go-live authorisation
UAT-009 | Acceptance | Two Workload Accounts Vended and Validated | Validate that at least one Production and one Non-Production workload account have been vended via AFT and all baseline controls are confirmed active | AFT pipeline validated and at least two account request files committed and executed | 1. Navigate to AWS Control Tower and confirm workload-prod-001 account shows Enrolled status 2. Navigate to AWS Control Tower and confirm workload-nonprod-001 account shows Enrolled status 3. For each account verify: GuardDuty enabled; Security Hub enrolled; Config recording active; spoke VPC with /20 CIDR provisioned; TGW attachment created; five mandatory tags applied; Budget alerts at 80% and 100% active 4. Log in to each account via IAM Identity Center and verify WorkloadAdministrator access | Both workload accounts enrolled in Control Tower; all baseline controls active on both accounts; mandatory tags present; IAM Identity Center access functional for both accounts | Critical | UAT | Client Executive Sponsor | Not Started | Not Executed | DD-Sec4-AFT DD-Sec4-Workload SOW-SuccessMetrics SOW-Deliverable19 | Hard go-live gate; verifies the core delivery promise of the engagement
UAT-010 | Business Process | VPN Connectivity Confirmed by Client Networking Lead | Validate that the Client Networking Lead can confirm Site-to-Site VPN connectivity to on-premises and understands monitoring and runbook procedures | VPN tunnels UP in both regions and on-premises routing confirmed and VPN runbooks delivered | 1. Client Networking Lead logs in to Network Hub account as NetworkOperator 2. Client Networking Lead verifies both VPN tunnels show UP in us-east-1 3. Client Networking Lead verifies both VPN tunnels show UP in us-east-2 4. Client Networking Lead confirms BGP routes are propagated from on-premises in both regions 5. Client Networking Lead reviews the VPN troubleshooting runbook and confirms the escalation procedure for a tunnel-down event is clear | VPN tunnels UP confirmed in both regions by Client Networking Lead; on-premises routes visible in AWS route tables; Networking Lead confirms runbook is usable and escalation path to on-premises team is documented; sign-off provided | High | UAT | Client Networking Lead | Not Started | Not Executed | DD-Sec6-VPN DD-Sec10-Handover SOW-Deliverable14 SOW-Deliverable15 | Satisfies client acceptance for SOW Deliverables 14 and 15