## Slide 1
Project Closeout
Amatra Intelligent Solution Builder
EO Framework Consulting — Project Manager | 2027-01-31

## Slide 2
Slide 2: Executive Summary
Project Duration: 12 months, on schedule (Jul 2026 – Jan 2027)
Budget: $378,178 net Year 1, within approved $300K–$450K envelope
GA Go-Live: All 120 users onboarded by 31 January 2027 deadline
Artifact Turnaround: Reduced from ~3 weeks to ≤2 business days
Throughput: Scaled from 8 to 24+ active engagements per quarter
QA Pass Rate: ≥90% first-review acceptance achieved at GA
Platform Availability: 99.9% SLA met in production (us-west-2)
Consulting Efficiency: ≥40% reduction in hours per engagement
Compliance: SOC 2 Type II audit-ready; GDPR controls active
Okta Migration: 100% of user records migrated — zero auth outages
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Open with confidence: platform delivered on time, on budget, against every defined success metric.
- The 31 January 2027 hard deadline — protecting Amatra's flagship client renewal — was met with zero slippage.
- Year 1 net investment of $378,178 is well within the $300K–$450K budget approved by the CTO at engagement start.
*Budget Detail:*
- Professional Services: $395K list → $360K net (after $35K in AWS partner credits)
- Cloud Infrastructure: $18K list → $10K net (after $8K MAP and APN credits)
- Software Licences: $4,038 Year 1; Support & Maintenance: $4,140/year
- Run cost from Year 2: ~$25,428/year (steady-state infra + licences + support only)
*Quality & Compliance:*
- 100 functional test cases executed across all 7 artifact types; zero P1 defects at GA.
- SOC 2 Type II evidence package (Deliverable #16) accepted by Security & Compliance Lead.
- GDPR data-processing register in place; us-west-2 data residency enforced via SCP.
*Throughput Proof:*
- Phase 1 MVP live by 30 Sep 2026 — pre-sales team generating artifacts within 4 months.
- Phase 2 delivery pipeline live by 15 Dec 2026 — full 7-type pipeline operational.
- GA rollout completed on 31 Jan 2027, meeting the board-level commitment.

## Slide 3
Slide 3: Solution Architecture
Amatra Intelligent Solution Builder
AI Generation Core
  Amazon Bedrock (Claude 3 Sonnet/Haiku)
  Step Functions async orchestration
  SQS dead-letter queue for reliability
Platform & API Layer
  API Gateway + Lambda REST endpoints
  Amazon Cognito auth (migrated from Okta)
  AWS WAF rate-limiting and rule groups
Data & Observability
  S3 artifact store with lifecycle management
  DynamoDB solution state + usage tracking
  CloudWatch dashboards + Datadog APM
Notes: *Talking Points:*
- Walk the architecture left-to-right: users authenticate via Cognito, submit briefs through API Gateway/Lambda, jobs are queued in SQS and orchestrated by Step Functions, Bedrock generates content, artifacts land in S3.
- The async design (30–60 min jobs via Step Functions) is the key architectural decision that prevents job loss and timeout failures that plagued the legacy EC2 monolith.
- CloudWatch + Datadog provide full observability: async job completion rates, Bedrock token consumption vs. monthly budget, Lambda cold-start latency, and DynamoDB throttle events.
*Services Deployed (matching presales Solution Briefing):*
- Amazon Bedrock (Claude 3 Sonnet/Haiku) — AI generation engine
- AWS Lambda (Python 3.12) — API handlers and job workers
- Amazon API Gateway (REST) — single secure ingress
- AWS Step Functions + Amazon SQS — durable async orchestration
- Amazon Cognito — user pool replacing Okta
- Amazon DynamoDB (On-Demand) — SolutionState + UsageTracking tables
- Amazon S3 — artifact store with presigned URL delivery
- AWS Secrets Manager — credential management with auto-rotation
- AWS WAF — rate limiting and managed rule groups
- AWS GuardDuty, Security Hub, CloudTrail, KMS — security and compliance
- Amazon CloudWatch + Datadog APM — observability layer
- GitHub Actions + AWS CloudFormation/SAM — CI/CD pipeline
*Presales Alignment:*
- Architecture exactly matches Solution Briefing Slide 4 and SOW Section 5.
- No services added beyond presales scope.
- Greenfield build; legacy EC2 monolith retired as planned.
*Network and Security Design:*
- Fully serverless — no VPCs or NAT gateways required for core services.
- All traffic TLS 1.2+; S3 and DynamoDB encrypted via KMS CMKs.
- IAM least-privilege per Lambda function; no wildcard resource policies.
- CloudTrail S3 bucket with Object Lock (7-year WORM retention).

## Slide 4
Slide 4: Deliverables Inventory
Deliverable | Purpose | Location
Detailed Architecture Design & ADRs | Architecture decisions and specifications | `/delivery/detailed-design.md`
Pre-Sales Artifact Pipeline (4 types) | Discovery, briefing, SoW, infra cost model | Deployed — Production us-west-2
Delivery Artifact Pipeline (3 types) | Detailed design, impl guide, Terraform | Deployed — Production us-west-2
Okta-to-Cognito Identity Migration | 100% of users migrated; zero downtime | AWS Cognito User Pool (Production)
SOC 2 Type II Controls Evidence | Audit-ready compliance package | `/delivery/soc2-evidence-package/`
CI/CD Pipeline (GitHub Actions) | Multi-env automated deployment | Amatra GitHub Organisation
Operations Runbooks & Config Docs | Async job triage, admin procedures | `/delivery/runbook.md`
Training Materials (all cohorts) | Pre-sales, delivery, admin user guides | `/delivery/training/`
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- All 24 formal SOW deliverables have been completed, reviewed, and accepted.
- Eight highest-value deliverables shown here represent the core of the handover package.
- Every system deliverable is live in production; every document deliverable has been accepted.
*Deliverable Acceptance Status:*
- Deliverables #1–#12 (Phase 1): Accepted by CTO / VP Eng / Head of Solutions at Phase 1 gate (30 Sep 2026).
- Deliverables #13–#20 (Phase 2): Accepted at Phase 2 gate (15 Dec 2026).
- Deliverables #21–#24 (Phase 3/GA): Accepted at GA completion (31 Jan 2027).
*Key Deliverable Highlights:*
- Detailed Architecture Design (D#2): Includes full ADR set, data-flow diagrams, sequence diagrams, and security design — reviewed and approved by CTO + VP Engineering in Month 2.
- SOC 2 Evidence Package (D#16): Covers all five Trust Service Criteria; accepted by Security & Compliance Lead in Month 8.
- Operations Runbooks (D#23): Cover async job failure triage, Cognito user admin, usage-limit overrides, Bedrock quota management, and incident response escalation paths.
- Train-the-Trainer (D#22): Head of Solutions can independently onboard future hires; session recorded and archived.

## Slide 5
Slide 5: Quality & Performance
Testing Metrics
  Functional test cases: 100% executed
  P1 defects at GA go-live: 0
  QA first-review pass rate: ≥90% achieved
  Async job reliability: 99.8% completion rate
  Security validation: all P1/P2 findings resolved
Performance Metrics
  Platform availability: 99.9% SLA met (us-west-2)
  Job submission API: ≤500 ms p99 response
  Async generation: ≤60 min under peak load
  Lambda cold start: ≤3 s (provisioned concurrency)
  DynamoDB latency: ≤10 ms p99 under load
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Quality was gated throughout delivery — Phase 2 could not begin until Phase 1 tests passed; Production deployments required CTO sign-off on test results.
- Zero P1 defects at GA is the gold standard — achieved through a structured test approach across functional, performance, security, DR, and UAT streams.
*Test Phase Detail:*
- Phase 1 Functional Testing (Month 4, Week 3): 10–20 representative client briefs tested across 4 pre-sales artifact types; Head of Solutions UAT sign-off received before Phase 1 go-live.
- Phase 2 Functional Testing (Month 8, Week 3): All 7 artifact types and Terraform outputs validated; VP Engineering UAT sign-off received before Phase 2 go-live.
- Load Testing (Staging): 24 concurrent job submissions at 2× peak load — all generation jobs completed within 60 minutes; DynamoDB and Lambda handled load without throttling.
- DR Testing: DynamoDB PITR restore validated; S3 versioned object recovery confirmed; Step Functions failure injection with retry-and-resume verified; RTO ≤1 hour and RPO ≤15 minutes targets met.
- Security Testing: IAM Access Analyzer policy review clean; WAF rate-limit and injection rules validated; GuardDuty alert simulation confirmed detection and SNS routing.
*Presales SLA Alignment:*
- Platform availability 99.9%: SOW target achieved ✓
- QA first-review pass rate ≥90%: SOW target achieved ✓
- Artifact turnaround ≤2 business days: SOW target achieved ✓
- Identity migration 100% zero-downtime: SOW target achieved ✓

## Slide 6
Slide 6: Benefits Realized
Benefit | Target | Achieved | Impact
Artifact Turnaround | ≤2 business days | ≤2 business days | 90%+ improvement vs. 3-week manual cycle
Proposal Throughput | 24 engagements/quarter | 24+ engagements/quarter | Tripled from 8/quarter baseline
Consulting Hours/Engagement | ≥40% reduction | ≥40% reduction | FTEs reallocated to strategic client work
QA First-Pass Rate | ≥90% | ≥90% | Rework cycles eliminated
Platform Availability | 99.9% SLA | 99.9% SLA met | Mission-critical pre-sales operations supported
Identity Migration | 100% zero downtime | 100% zero downtime | No authentication disruption for 120 users
SOC 2 Readiness | Audit-ready at GA | Controls evidenced Month 8 | Enterprise client contracts protected
Year 1 Investment | ≤$450K net | $378,178 net | $71,822 below budget ceiling
Amatra Intelligent Solution Builder
Notes: *Talking Points:*
- Every benefit target defined in the SOW Success Metrics section has been met or exceeded.
- The financial headline: Year 1 net spend of $378,178 is $71,822 under the $450K budget ceiling — a 16% underspend achieved through effective scope management and AWS partner credits.
*Benefits Breakdown:*
- Artifact Turnaround: Pre-sales team went from submitting client briefs on Monday and getting artifacts the following week to receiving complete packages within 2 business days. Measured from Phase 1 MVP go-live (30 Sep 2026) through GA.
- Proposal Throughput: Platform capacity supports 24 concurrent engagements per quarter (24 simultaneous Step Functions pipelines). Amatra's sales pipeline is no longer gated by artifact production capacity.
- Consulting Hours: By eliminating manual authoring of discovery questionnaires, briefings, SOWs, infrastructure cost models, detailed designs, implementation guides, and Terraform scripts, each engagement now requires ~40% fewer consulting hours — freeing senior architects for client-facing and strategic work.
- QA Pass Rate: The QA validation layer (Phase 2, Deliverable #15) automates a subset of quality rubric checks; manual review covers the remainder. Combined result: ≥90% first-review acceptance across all 7 artifact types.
- Budget Savings: $35K in AWS professional services credits + $8K in infrastructure credits = $43K total Year 1 reduction. Net Year 1 run cost from Year 2 is only $25,428 — well within the ~$48K–$72K range projected in the SOW for steady-state operations.
*ROI Projection:*
- Tripling throughput (8 → 24 engagements/quarter) without proportional headcount increase represents significant revenue leverage.
- If each engagement yields $30K–$60K in consulting revenue, the incremental 16 engagements/quarter represent $1.9M–$3.8M annualised revenue opportunity.
- Platform run cost in Year 2 is $25,428 — the payback period is measured in weeks at current engagement volumes.

## Slide 7
Slide 7: Lessons Learned & Recommendations
What Worked Well
  Phase-gated milestones protected timeline and budget
  Async Step Functions design eliminated job-loss risk
  Early Head of Solutions involvement shaped prompt quality
  GitOps CI/CD model prevented production incidents
  SOC 2 designed-in from Day 1 avoided rework
Challenges Overcome
  Okta export latency: resolved with phased migration
  Bedrock cold token tuning: iterative prompt refinement
  Legacy PPT/Excel template parsing: custom adapters built
Recommendations
  Phase 4: multi-region DR replication to us-east-1
  Expand Bedrock pipeline to additional artifact types
  Enable CloudFront for artifact download performance
  Quarterly QA rubric reviews with Head of Solutions
Amatra Intelligent Solution Builder
Notes: *What Worked Well — Detail:*
- Phase-gated milestones: Each phase gate (M4 Phase 1 Go-Live, M6 Phase 2 Go-Live) acted as a financial and scope firewall. No budget was committed for Phase 2 until Phase 1 quality was validated. This protected both parties.
- Step Functions async design: The decision to use Step Functions + SQS (vs. a simple Lambda chain) was validated when load tests showed 30–60 min jobs completing reliably even when Bedrock API experienced transient throttling — retries handled transparently.
- Head of Solutions involvement: Artifact quality rubric defined in Month 2 with input from Head of Solutions gave the Bedrock prompt engineering team precise acceptance criteria. This is directly responsible for achieving ≥90% first-review pass rate.
- GitOps CI/CD: Zero unintended production changes throughout the engagement. All infrastructure changes tracked via GitHub pull requests with manual approval gates in the GitHub Actions workflow.
- SOC 2 from Day 1: CloudTrail, KMS, GuardDuty, and Security Hub were activated at AWS landing zone setup (Month 2). Evidence collection began at Phase 1 go-live, giving the Security & Compliance Lead 4+ months of control operation evidence before the Phase 2 evidence package deadline.
*Challenges — Detail:*
- Okta export latency: The Okta user directory export took 3 weeks instead of the assumed 2 (SOW Assumption #3). The vendor team used the buffer time to complete Cognito user pool configuration, allowing the migration to execute on schedule at Month 3, Week 2.
- Bedrock prompt tuning: Initial Claude 3 Sonnet prompts produced artifacts that met structural requirements but had low Head of Solutions satisfaction on tone and depth. Two additional prompt-tuning sprints in Phase 1 (Months 2–3) resolved this; ≥90% pass rate achieved by Phase 1 UAT.
- Legacy template parsing: Word/Excel/PowerPoint templates in Google Workspace required custom Lambda adapters to extract structured content for pipeline ingestion. Scope was within SOW bounds (Deliverable #13) but took 1 additional sprint week; absorbed within Phase 2 buffer.
*Recommendations — Priority Order:*
1. Multi-region DR (us-east-1): Highest priority for SOC 2 availability controls and enterprise client contractual requirements. Estimated 6–8 weeks effort; recommended as Phase 4 kickoff.
2. Additional artifact types: Current pipeline covers 7 types. Client onboarding decks, project status reports, and executive summaries are natural next targets. Existing Bedrock prompt framework and Step Functions state machine are reusable.
3. CloudFront: S3 presigned URL egress (~200 GB/month) can be optimised via CloudFront edge caching. Reduces artifact download latency for consultants outside us-west-2. Low effort, high UX impact.
4. Quarterly QA rubric reviews: As Amatra's artifact standards evolve, the quality rubric and Bedrock prompts should be reviewed quarterly. Head of Solutions trained as train-the-trainer to lead these reviews independently.

## Slide 8
Slide 8: Support Transition
Phase 1 Hypercare (Oct–Nov 2026, 8 weeks)
  Business hours coverage (09:00–18:00 CT)
  P1 critical issues: ≤2-hour response
  P2 standard issues: next-business-day response
  Dedicated Slack channel for vendor + Amatra
Phase 2 Hypercare (Jan 2027, 4 weeks)
  Delivery pipeline and Terraform issue triage
  QA validation layer tuning support
  P1 ≤2-hour / P2 next-business-day SLAs apply
Steady State (Post-Hypercare)
  VP Engineering owns platform operations
  CloudWatch dashboards and runbooks in place
  Quarterly QA rubric review recommended
Escalation Contacts
  Vendor PM: solutions@eoframework.com
  AWS Support: Business Plan — 1-hr critical SLA
Amatra Intelligent Solution Builder
Notes: *Hypercare Scope Detail — Phase 1 (Oct–Nov 2026):*
- Covers: generation failures, Bedrock prompt quality issues, Cognito authentication problems, async job failures, CloudWatch alarm investigation, and performance tuning.
- Communication: dedicated Slack channel (#amatra-hypercare) shared between EO Framework Consulting and Amatra's VP Engineering + Head of Solutions.
- Issue tracking: defects logged in GitHub Issues with severity classification (P1/P2/P3) and weekly summary report to CTO.
*Hypercare Scope Detail — Phase 2 (January 2027):*
- Covers: delivery pipeline issues, QA validation layer tuning, Terraform output quality, legacy template pipeline defects.
- Final hypercare period ends on 31 January 2027 — aligned with the GA deadline and formal engagement close.
*Steady-State Ownership Transfer:*
- VP Engineering team has completed Operations Training (Session 1, Phase 1 end) covering CloudWatch monitoring, Lambda deployment management, DynamoDB capacity review, Cognito user administration, and incident response runbook walkthrough.
- Delivery Consulting team completed Delivery Artifact Pipeline Enablement (Session 2, Phase 2 end).
- Head of Solutions completed Train-the-Trainer (Session 3, GA) for future hire onboarding.
- All three sessions recorded; videos archived in Amatra's internal knowledge base.
*Post-Hypercare Support Options:*
- Ongoing managed services are NOT included in this SOW.
- Amatra should initiate a Managed Services Agreement with EO Framework Consulting if post-hypercare operational support, ongoing Bedrock prompt optimisation, or platform feature development is required.
- AWS Business Support Plan (activated pre-Phase 1 go-live per SOW Assumption #11) provides 1-hour critical response for AWS service issues independent of vendor involvement.
*Recommended Steady-State Cadence:*
- Monthly: VP Engineering reviews CloudWatch SLA dashboard (availability, async job completion rate, Bedrock token consumption).
- Quarterly: Head of Solutions reviews QA rubric and artifact acceptance rates; initiates prompt tuning if pass rate trends below 90%.
- Annually: Security & Compliance Lead reviews SOC 2 evidence continuity and GDPR data-processing register.

## Slide 9
Slide 9: Acknowledgments & Next Steps
CTO for executive sponsorship and decisive phase-gate approvals
VP Engineering for environment provisioning and technical oversight
Head of Solutions for artifact quality standards and UAT leadership
Security & Compliance Lead for SOC 2 scoping and compliance sign-off
This Week: Final documentation and source code handover complete
Next 30 Days: Phase 2 hypercare support with Slack channel active
Next Quarter: Initiate Phase 4 multi-region DR planning workshop
Amatra Intelligent Solution Builder
Notes: *Acknowledgments — Specific Contributions:*
- CTO: Budget authority and phased approval model were essential. Decisive sign-off at each milestone (M2, M4, M6, M9) kept the project on its 12-month track. The 31 January 2027 deadline was set at the executive level and met — a direct result of CTO governance.
- VP Engineering: Delivered AWS account provisioning and IAM access in Week 1 (on time per SOW Assumption #2). Managed all Staging and Production environment access. Led Phase 2 UAT, ensuring delivery pipeline quality before go-live.
- Head of Solutions: Provided 10–20 representative client briefs in Week 2 (critical for Bedrock prompt engineering). Defined the artifact quality rubric that became the acceptance standard for ≥90% QA pass rate. Led Phase 1 UAT and the Train-the-Trainer session.
- Security & Compliance Lead: Delivered Okta user directory export, provided SOC 2 scoping input from Month 1, and reviewed and accepted the SOC 2 Type II evidence package in Month 8. Compliance-first posture enabled enterprise client renewal readiness.
*Next Steps Timeline:*
- This Week (31 Jan 2027): Formal handover of all source code to Amatra's GitHub organisation; final document package delivered to VP Engineering; engagement closure meeting with CTO.
- Next 30 Days: Phase 2 hypercare active (January 2027 4-week window); VP Engineering team operating platform independently with vendor on-call via Slack.
- Next Quarter (Q2 2027): Recommend scheduling Phase 4 planning workshop to scope multi-region DR (us-east-1), additional artifact types, and CloudFront optimisation.
- Ongoing: Monthly CloudWatch SLA reviews (VP Engineering); quarterly QA rubric reviews (Head of Solutions); annual SOC 2 evidence continuity (Security & Compliance Lead).
*Follow-up Actions (vendor):*
- Deliver final SOC 2 evidence package to Security & Compliance Lead before 31 January 2027.
- Transfer all source code repositories to Amatra GitHub organisation.
- Provide final invoice (10% project close payment: $37,818) upon written CTO acceptance.
- Archive project retrospective and lessons learned in EO Framework internal knowledge base.

## Slide 10
Slide 10: Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion.
- Have the following backup detail available for deep-dive questions:
- Investment Summary table (SOW Section 10) for any budget queries.
- SOC 2 evidence package summary for compliance queries.
- CloudWatch dashboard screenshots for platform performance queries.
- Phase 4 scope outline for next-steps and roadmap queries.
- Offer to schedule follow-up sessions for specific topics (Phase 4 scoping, Managed Services Agreement, additional artifact type roadmap).
- End on a positive note — celebrate the platform delivery and the flagship client renewal readiness that this project directly enabled.
- Remind the client that the EO Framework Consulting team is available for future engagements and ongoing support via a Managed Services Agreement.
*Anticipated Q&A:*
- "What happens after hypercare ends?" → VP Engineering owns operations; runbooks, dashboards, and training materials fully transfer. Managed Services Agreement available if ongoing support needed.
- "Can we add more artifact types ourselves?" → Yes. The Bedrock prompt framework is documented in the architecture design. New artifact types follow the same prompt-template + Step Functions pattern. Train-the-Trainer session covered the prompt engineering approach.
- "When is Phase 4 (multi-region DR) recommended?" → Q2 2027 planning workshop. Estimated 6–8 weeks effort. Addresses SOC 2 Availability criteria for enterprise clients requiring cross-region resilience.
- "Are there any open risks post-GA?" → All P1/P2 defects resolved. Three low-severity P3 items logged for Phase 4 scope: CloudFront optimisation, cross-region S3 replication, and Bedrock prompt library versioning. None affect platform operation or SLA.