## Cover
Level of Effort
Generated: | June 29, 2026
Solution: | Tmp2Vuewb8H
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Users / Clinical Staff | Single hospital unit | ~4200 staff across 18 hospitals and 60+ clinics | 50-100 users | 500-1000 users | 4000+ users | Alert consumers include nurses, hospitalists, and admins; phased rollout per facility
Regions / Facilities | Single facility | 18 hospitals + 60+ outpatient clinics (southeastern US) | 1 site | 2-5 sites | 18+ sites | Multi-region AWS resiliency required; phased go-live by facility cohort
Data Volume / Patient Records | Low-volume EHR feeds | ~2.1 million patients annually; real-time vitals, labs, and EHR events | < 100K records/yr | 100K-1M records/yr | 2M+ records/yr | Real-time streaming via Kinesis; latency SLA < 3 seconds end-to-end
Integration Points | No external integrations | Epic FHIR R4 API, Mirth Connect HL7 v2.3, Azure AD SSO, SQL Server nightly export | 1-2 integrations | 3-5 integrations | 6+ integrations | Event-driven only (no batch); Philips and GE bedside monitor streams included
Environments | Single environment | Dev / QA / Staging / Production (4 environments) | 1 (prod only) | 2 (dev + prod) | 4 (dev, QA, staging, prod) | Dedicated AWS account under MedCore Clinical Applications OU
AI/ML Models | Single pre-built model | 3 custom models (sepsis; readmission; rapid response) + LLM summarization | 1 model (pre-built) | 2-3 models (custom) | 4+ models + LLM | Model explainability required per alert; continuous retraining pipeline required
Compliance Frameworks | No specific compliance | HIPAA BAA + HITECH + SOC 2 Type II + PHI audit logging | No regulatory requirements | HIPAA baseline | HIPAA + HITECH + SOC 2 Type II | BAA with AWS required; all PHI must remain in US AWS regions; full audit log mandatory
SLA / Availability Target | Best-effort (99.0%) | 99.95% platform availability (excluding maintenance windows) | 99.0% | 99.9% | 99.95% | Multi-AZ + multi-region active/passive; automated failover required
Timeline Phases | Single-phase delivery | 3 phases: Phase 1 by 2026-10-31; Phase 2 by 2027-02-28; Phase 3 by 2027-06-30 | 1 phase | 2 phases | 3 phases | Phase 1 hard deadline tied to Joint Commission accreditation review (Nov 2026)

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | discovery_factor | 1.2 | Elevated due to complex HIPAA/PHI requirements and multi-stakeholder clinical environment
Planning | planning_factor | 1.3 | Large-scale AWS AI/ML platform design with multi-region HA and EHR integration complexity
Development | development_factor | 1.5 | Custom ML model development + real-time streaming pipeline + Epic FHIR integration at enterprise scale
Testing | testing_factor | 1.3 | Clinical validation and model accuracy testing required alongside standard QA; compliance testing mandatory
Deployment | deployment_factor | 1.2 | Phased rollout across 18 facilities with per-facility UAT and go-live coordination
Management | management_factor | 1 | Project management and technical leadership overhead (10% of engineering hours)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Project Initiation | Project kickoff meeting and stakeholder alignment across CMO, CIO, CISO and EHR Lead | Project Manager | 12 | 1.2 | 14 | 175 | 2450 |  | Multi-stakeholder kickoff; establish RACI and communication cadence
Discovery | Project Initiation | Clinical workflow discovery sessions with nursing staff and hospitalists | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | Kickoff complete | Document current alert workflow and pain points
Discovery | Current State Assessment | Assess Epic FHIR R4 API capabilities and HL7 v2.3 Mirth Connect integration topology | Solutions Engineer | 32 | 1.2 | 38 | 200 | 7600 |  | Catalog available FHIR resource types and Mirth adapter configurations
Discovery | Current State Assessment | Review existing on-premises data warehouse (SQL Server 2016) and downstream reporting dependencies | Data Engineer | 16 | 1.2 | 19 | 200 | 3800 |  | Out-of-scope for build but nightly export of readmission outcomes must be planned
Discovery | Current State Assessment | Document MedCore AWS Organization structure and Clinical Applications OU landing zone | Cloud Engineer | 12 | 1.2 | 14 | 200 | 2800 |  | Identify account vending process and network connectivity to on-prem Mirth Connect
Discovery | Requirements Gathering | Facilitate requirements workshops for sepsis model (Phase 1) feature inputs and alert thresholds | Solution Architect | 32 | 1.2 | 38 | 225 | 8550 | Current State Assessment | Clinical Informatics Lead must validate lab/vital signal list
Discovery | Requirements Gathering | Document HIPAA BAA governance requirements and PHI data-handling rules with CISO | Security Engineer | 24 | 1.2 | 29 | 225 | 6525 |  | HIPAA, HITECH and SOC 2 Type II constraints captured; audit log requirements defined
Discovery | Requirements Gathering | Capture model explainability and LLM narrative requirements with clinical informatics team | ML/AI Engineer | 20 | 1.2 | 24 | 275 | 6600 |  | Explainability output must accompany every alert; plain-language narrative for bedside staff
Discovery | Gap Analysis | Identify gaps in existing AWS landing zone for HIPAA-compliant ML workloads | Solution Architect | 16 | 1.2 | 19 | 225 | 4275 | Requirements Gathering | Gaps include HealthLake provisioning and VPC/PrivateLink configuration
Discovery | Gap Analysis | Assess Azure AD federation requirements for Cognito SAML 2.0 SSO | Security Engineer | 12 | 1.2 | 14 | 225 | 3150 |  | Validate SAML metadata exchange and attribute mapping for role-based access
Discovery | Data Assessment | Evaluate data quality and completeness of FHIR R4 resources for ML feature engineering | Data Engineer | 32 | 1.2 | 38 | 200 | 7600 |  | Identify missing/sparse fields that may degrade model accuracy
Discovery | Risk Assessment | Identify project risks and mitigation strategies (clinical safety, data privacy, timeline) | Project Manager | 12 | 1.2 | 14 | 175 | 2450 |  | Joint Commission deadline risk for Phase 1 is highest-priority risk item
Discovery | Assessment Report | Document discovery findings, architecture approach, and go/no-go recommendation | Solution Architect | 20 | 1.2 | 24 | 225 | 5400 | All Discovery tasks | Deliverable reviewed and approved by CMO and CIO before Planning phase begins
Planning | Detailed Architecture Design | Design multi-region AWS architecture: VPC, subnets, Transit Gateway and PrivateLink to Mirth Connect | Solution Architect | 40 | 1.3 | 52 | 225 | 11700 | Assessment Report | Multi-AZ primary + passive secondary region for 99.95% SLA
Planning | Detailed Architecture Design | Design real-time data ingestion pipeline: Kinesis Data Streams, Kinesis Data Firehose, Lambda and HealthLake | Solution Architect | 32 | 1.3 | 42 | 225 | 9450 | Assessment Report | < 3-second end-to-end latency constraint drives architecture choices
Planning | Detailed Architecture Design | Design ML platform: SageMaker Pipelines, Model Registry, real-time endpoints and Feature Store | ML/AI Engineer | 40 | 1.3 | 52 | 275 | 14300 | Assessment Report | Support training, versioning, and real-time serving for 3 custom models
Planning | Detailed Architecture Design | Design LLM summarization layer using Amazon Bedrock with clinical prompt templates | ML/AI Engineer | 24 | 1.3 | 31 | 275 | 8525 | ML platform design | Bedrock invocation must meet < 3-second inference SLA
Planning | Infrastructure Provisioning | Define Infrastructure-as-Code (Terraform/CDK) standards and CI/CD pipeline for platform deployments | DevOps Engineer | 32 | 1.3 | 42 | 200 | 8400 | Architecture designs complete | All environments provisioned via IaC; no manual console changes in prod
Planning | Security & Compliance Design | Design PHI encryption strategy: KMS CMKs, S3 SSE, HealthLake encryption and TLS 1.2+ in transit | Security Engineer | 32 | 1.3 | 42 | 225 | 9450 | Architecture designs complete | Every PHI data store must use CMK managed by MedCore
Planning | Security & Compliance Design | Design HIPAA-compliant audit logging architecture (CloudTrail, CloudWatch and Security Hub) | Security Engineer | 24 | 1.3 | 31 | 225 | 6975 | Security design | Every PHI access event logged; audit log retention 7 years per HIPAA
Planning | Security & Compliance Design | Design RBAC model: Cognito user pools, SAML 2.0 federation to Azure AD and IAM policies per clinical role | Security Engineer | 20 | 1.3 | 26 | 225 | 5850 | Security design | Roles: nurse, physician, admin, data scientist; enforce least privilege
Planning | Monitoring Design | Design observability stack: CloudWatch dashboards, alarms and X-Ray tracing for inference latency | DevOps Engineer | 20 | 1.3 | 26 | 200 | 5200 | Architecture designs complete | Latency alarm threshold: 3 seconds; availability alarm: < 99.95%
Planning | Design Documentation | Produce HLD and LLD architecture documents and data flow diagrams | Solution Architect | 32 | 1.3 | 42 | 225 | 9450 | All Planning tasks | Deliverables: HLD, LLD, Data Flow Diagram, Security Architecture doc
Planning | Design Documentation | Produce data dictionary and FHIR resource mapping specification | Data Engineer | 20 | 1.3 | 26 | 200 | 5200 | Data Assessment | Maps Epic FHIR R4 resource fields to ML feature store schema
Development | Environment Setup | Provision Dev, QA, Staging and Production AWS accounts and VPCs via IaC | Cloud Engineer | 40 | 1.5 | 60 | 200 | 12000 | Design Documentation | Accounts under Clinical Applications OU; apply SCPs and GuardRails
Development | Environment Setup | Configure Transit Gateway and PrivateLink connectivity to on-premises Mirth Connect engine | Cloud Engineer | 24 | 1.5 | 36 | 200 | 7200 | Environment provisioning | Private routing only; no public internet traversal for PHI data
Development | EHR Integration | Develop Epic FHIR R4 API connector for real-time patient data ingestion (vitals, labs, medications) | Solutions Engineer | 80 | 1.5 | 120 | 200 | 24000 | Environment Setup | Event-driven using FHIR subscription notifications; handle OAuth 2.0 SMART on FHIR
Development | EHR Integration | Develop HL7 v2.3 adapter for Mirth Connect bedside monitor streams (Philips and GE) | Solutions Engineer | 64 | 1.5 | 96 | 200 | 19200 | Environment Setup | Parse and normalize HL7 v2.3 ADT and ORU message types
Development | EHR Integration | Implement Azure AD SAML 2.0 federation with Amazon Cognito for SSO | Security Engineer | 24 | 1.5 | 36 | 225 | 8100 | Environment Setup | Attribute mapping for clinical role claims; test with all 4 role types
Development | Data Pipeline | Build Kinesis Data Streams ingestion pipeline with schema validation and dead-letter queue | Data Engineer | 48 | 1.5 | 72 | 200 | 14400 | EHR Integration | Validate FHIR and HL7 payloads before ingestion; DLQ for malformed messages
Development | Data Pipeline | Build SageMaker Feature Store pipelines for feature extraction from patient data streams | Data Engineer | 64 | 1.5 | 96 | 200 | 19200 | Kinesis pipeline | Real-time feature group for inference; offline feature group for training
Development | Data Pipeline | Build AWS HealthLake FHIR data store ingestion and query layer | Data Engineer | 40 | 1.5 | 60 | 200 | 12000 | SageMaker Feature Store | HIPAA-compliant FHIR persistence; supports longitudinal patient tracking
Development | ML Model Development | Develop and train sepsis risk prediction model (Phase 1) using SageMaker Pipelines | ML/AI Engineer | 120 | 1.5 | 180 | 275 | 49500 | Feature Store | XGBoost/ensemble model; minimum AUROC >= 0.85 clinical acceptance threshold
Development | ML Model Development | Develop model explainability pipeline using SHAP values output per inference call | ML/AI Engineer | 40 | 1.5 | 60 | 275 | 16500 | Sepsis model | SHAP output bundled with each risk score alert payload
Development | ML Model Development | Develop and train 30-day readmission prediction model (Phase 2) | ML/AI Engineer | 100 | 1.5 | 150 | 275 | 41250 | Feature Store | Phase 2 deliverable; separate SageMaker training pipeline and endpoint
Development | ML Model Development | Develop and train rapid response / early deterioration model (Phase 2) | ML/AI Engineer | 100 | 1.5 | 150 | 275 | 41250 | Feature Store | Phase 2 deliverable; combined with readmission model release
Development | LLM Integration | Implement Amazon Bedrock integration for LLM-powered clinical narrative generation | ML/AI Engineer | 48 | 1.5 | 72 | 275 | 19800 | ML Model Development | Prompt engineering for clinical-grade plain-language summaries; latency < 3 seconds
Development | Alert & Notification System | Build real-time alert routing service (SNS/EventBridge) with role-based alert delivery | Solutions Engineer | 48 | 1.5 | 72 | 200 | 14400 | LLM Integration | Route alerts to correct clinical role; suppress duplicate alerts within window
Development | Clinical Dashboard | Develop clinical staff dashboard (React/Amplify) for risk score visualization and alert management | Solutions Engineer | 80 | 1.5 | 120 | 200 | 24000 | Alert system | Role-specific views; mobile-responsive for tablet use at bedside
Development | Analytics Platform | Build longitudinal outcome tracking and model performance monitoring dashboards (QuickSight) | Data Engineer | 48 | 1.5 | 72 | 200 | 14400 | HealthLake | Tracks sepsis mortality, readmission rates, alert false-positive rates; refreshed daily
Development | Security Implementation | Implement KMS CMK key policies and enforce encryption on all PHI data stores | Security Engineer | 24 | 1.5 | 36 | 225 | 8100 | Environment Setup | Separate CMK per data classification tier; annual key rotation enabled
Development | Security Implementation | Implement HIPAA audit logging (CloudTrail, CloudWatch Logs and Athena query layer) | Security Engineer | 24 | 1.5 | 36 | 225 | 8100 | Security design | Every PHI access logged with user, timestamp, resource ID; Athena for CISO audit queries
Development | Security Implementation | Implement AWS Config rules and Security Hub findings for continuous compliance posture | Security Engineer | 20 | 1.5 | 30 | 225 | 6750 | Audit logging | Automate detection of non-compliant resource configurations
Development | CI/CD & DevOps | Build CI/CD pipelines (CodePipeline/CodeBuild) for model and application deployments | DevOps Engineer | 56 | 1.5 | 84 | 200 | 16800 | Environment Setup | Blue/green deployment for inference endpoints; automated rollback on latency breach
Development | CI/CD & DevOps | Implement infrastructure drift detection and automated compliance remediation | DevOps Engineer | 32 | 1.5 | 48 | 200 | 9600 | CI/CD pipelines | AWS Config + Lambda auto-remediation for common drift scenarios
Development | Configuration Documentation | Document all component configurations, IaC modules, and operational procedures | Technical Writer | 48 | 1.5 | 72 | 125 | 9000 | All Development tasks | As-built configuration catalog; stored in version-controlled documentation repository
Testing | Test Plan Development | Develop comprehensive test plan covering functional, integration, performance, security, and clinical acceptance | QA Engineer | 20 | 1.3 | 26 | 150 | 3900 | Development complete | Test plan reviewed and approved by Clinical Informatics Lead and CISO
Testing | Functional Testing | Execute functional test cases for data ingestion pipeline and feature store | QA Engineer | 32 | 1.3 | 42 | 150 | 6300 | Test Plan | Validate FHIR and HL7 message processing and feature extraction accuracy
Testing | Functional Testing | Execute functional test cases for ML inference endpoints and explainability output | QA Engineer | 32 | 1.3 | 42 | 150 | 6300 | Test Plan | Validate risk score computation and SHAP output structure per alert
Testing | Integration Testing | Test Epic FHIR R4 integration end-to-end with MedCore test environment | Solutions Engineer | 40 | 1.3 | 52 | 200 | 10400 | Functional Testing | Use synthetic PHI in test environment; validate all FHIR resource types
Testing | Integration Testing | Test HL7 v2.3 Mirth Connect adapter with Philips and GE monitor test feeds | Solutions Engineer | 24 | 1.3 | 31 | 200 | 6200 | Functional Testing | Simulate ADT and ORU message types at production throughput rates
Testing | Performance Testing | Conduct end-to-end latency load test (target: < 3 seconds per patient update at peak load) | Solutions Engineer | 32 | 1.3 | 42 | 200 | 8400 | Integration Testing | Simulate 18-hospital concurrent patient event load; stress test Kinesis and SageMaker endpoints
Testing | Performance Testing | Conduct availability failover test to validate 99.95% SLA with multi-region passive failover | Cloud Engineer | 20 | 1.3 | 26 | 200 | 5200 | Integration Testing | Simulate primary region outage; validate RTO and RPO meet clinical SLA
Testing | Model Accuracy Validation | Validate sepsis model AUROC, sensitivity and specificity against held-out clinical dataset | ML/AI Engineer | 40 | 1.3 | 52 | 275 | 14300 | Functional Testing | Clinical Informatics Lead and clinician reviewers must sign off on model performance
Testing | Model Accuracy Validation | Validate LLM narrative quality and clinical appropriateness with nurse and hospitalist reviewers | ML/AI Engineer | 24 | 1.3 | 31 | 275 | 8525 | Model accuracy validation | At least 5 clinical reviewers; qualitative scoring rubric defined with Informatics Lead
Testing | Security Testing | Execute HIPAA security controls validation checklist (encryption, access controls, audit logs) | Security Engineer | 24 | 1.3 | 31 | 225 | 6975 | All Development tasks | CISO sign-off required before production go-live
Testing | Security Testing | Coordinate penetration testing engagement (scoped to CDS platform boundary) | Security Engineer | 20 | 1.3 | 26 | 225 | 5850 | Security controls validation | External pen test firm; remediate all Critical and High findings before go-live
Testing | Compliance Validation | SOC 2 Type II readiness review and evidence collection | Security Engineer | 32 | 1.3 | 42 | 225 | 9450 | Security Testing | Evidence packages for CC6 (access), CC7 (monitoring) and A1 (availability) Trust Services Criteria
Testing | UAT Coordination | Coordinate and facilitate UAT sessions with clinical staff at pilot facility | Project Manager | 24 | 1.3 | 31 | 175 | 5425 | Model Accuracy Validation | Pilot facility selection aligned with Phase 1 deployment; collect structured feedback
Testing | Defect Resolution | Triage and resolve defects identified during all testing phases | Solutions Engineer | 48 | 1.3 | 62 | 200 | 12400 | All Testing phases | Priority: Critical and High blockers resolved before go-live; Medium resolved before GA
Testing | Test Results Report | Compile test results report and obtain CMO/CIO go-live sign-off | QA Engineer | 12 | 1.3 | 16 | 150 | 2400 | All Testing complete | Report includes model performance metrics and security validation summary
Deployment | Go-Live Planning | Develop phased rollout plan and per-facility cutover playbook for 18 hospitals | Project Manager | 24 | 1.2 | 29 | 175 | 5075 | Test sign-off | Cohort-based rollout schedule; rollback procedure documented per facility
Deployment | Phase 1 Production Deployment | Deploy sepsis model and ingestion pipeline to production (target: 2026-10-31) | Solutions Engineer | 32 | 1.2 | 38 | 200 | 7600 | Go-Live Planning | Blue/green deployment; monitor latency and error rates for 48 hours post-cutover
Deployment | Phase 1 Production Deployment | Configure production Epic FHIR R4 and Mirth Connect connections at pilot facility cohort | Solutions Engineer | 24 | 1.2 | 29 | 200 | 5800 | Phase 1 deployment | Coordinate with EHR Integration Lead; validate live data flow before clinical activation
Deployment | Phase 2 Production Deployment | Deploy readmission and rapid response models to production (target: 2027-02-28) | Solutions Engineer | 32 | 1.2 | 38 | 200 | 7600 | Phase 1 stable in production | Incremental deployment; no disruption to live sepsis alerting
Deployment | Phase 3 Full Facility Rollout | Execute full 18-hospital and 60+ clinic rollout (target: 2027-06-30) | Solutions Engineer | 80 | 1.2 | 96 | 200 | 19200 | Phase 2 deployment | Facility-by-facility activation with per-facility UAT sign-off before activation
Deployment | Phase 3 Full Facility Rollout | Conduct per-facility Epic integration validation and alert workflow activation | Solutions Engineer | 48 | 1.2 | 58 | 200 | 11600 | Phase 3 rollout | Validate FHIR subscriptions and alert routing for each facility before activation
Deployment | Runbook Development | Create operational runbooks for ingestion pipeline, ML inference, and alert system | Technical Writer | 32 | 1.2 | 38 | 125 | 4750 | Configuration Documentation | Runbooks cover monitoring, common failure modes, escalation paths
Deployment | Knowledge Transfer | Deliver architecture and operations knowledge transfer sessions for MedCore IT and data engineering team | Solution Architect | 24 | 1.2 | 29 | 225 | 6525 | Runbooks complete | Sessions cover SageMaker pipeline operations, Kinesis troubleshooting, and model retraining
Deployment | Knowledge Transfer | Conduct clinical staff training on alert dashboard and risk score interpretation | Trainer | 48 | 1.2 | 58 | 150 | 8700 | Phase 3 rollout | Train-the-trainer model; target >= 75% adoption within 90 days per facility
Deployment | Documentation Delivery | Deliver final as-built documentation package and hand over all IaC repositories | Technical Writer | 20 | 1.2 | 24 | 125 | 3000 | All Deployment tasks | Includes architecture diagrams, data flow docs, and model cards for each ML model
Deployment | Hypercare Support | Provide 8-week post-go-live hypercare support (Phase 3 GA in Q3 2027) | Support Engineer | 160 | 1.2 | 192 | 150 | 28800 | Documentation delivery | On-call support SLA: 1-hour response for Critical; 4-hour for High severity issues
Deployment | Project Closeout | Conduct project retrospective, lessons learned, and formal project closure | Project Manager | 12 | 1.2 | 14 | 175 | 2450 | Hypercare complete | Deliver outcomes report to CMO and CIO with KPI baseline vs. actual metrics
Management | Technical Leadership | Quarterback technical oversight and cross-phase architecture governance across all 3 project phases | Solution Architect |  | 1 |  | 225 |  |  | 10% of engineering task hours; covers architecture reviews and escalation resolution
Management | Project Management | Project coordination, status reporting, risk management, and stakeholder communications | Project Manager |  | 1 |  | 175 |  | Technical Leadership | 10% of engineering task hours; covers weekly status meetings and PMO reporting
[5 empty] | TOTAL HOURS |  | TOTAL COST

## Credits
CREDITS
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -15000 | AWS Partner Network (APN) Advanced Tier services credit for solution architecture and ML platform implementation; applied to Year 1 professional services cost
AWS Healthcare Competency Credit | -10000 | AWS Healthcare Competency partner credit for HIPAA-compliant solution delivery; requires AWS Healthcare Competency designation and active BAA with end customer
Implementation Volume Discount | -12500 | Volume discount on professional services for engagement exceeding $1M total PS spend; approximately 5% discount on Year 1 services
Training & Enablement Credit | -5000 | AWS Training credit applied toward MedCore IT and data engineering team enablement sessions; covers SageMaker, Kinesis, and HealthLake training modules
TOTAL |  | Total professional services cost minus all partner and volume credits applied in Year 1; infrastructure credits (Reserved Instances, SageMaker Savings Plans) are captured in infrastructure-costs.csv