## Cover
Project Plan
Generated: | June 05, 2026
Solution: | Tmphvehf53R
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff & Stakeholder Alignment | 1 day | 2026-01-05 | 2026-01-05 | None | Project Manager | Not Started
Phase 1 | AWS Account Access & IAM Permissions Confirmed | 1 day | 2026-01-05 | 2026-01-05 | Project Kickoff & Stakeholder Alignment | Cloud Engineer | Not Started
Phase 1 | Current State Assessment & Gap Analysis | 5 days | 2026-01-06 | 2026-01-12 | AWS Account Access & IAM Permissions Confirmed | Solution Architect | Not Started
Phase 1 | Architecture Design Document & ADRs | 10 days | 2026-01-06 | 2026-01-19 | AWS Account Access & IAM Permissions Confirmed | Solution Architect | Not Started
Phase 1 | AWS Landing Zone & VPC Provisioning | 5 days | 2026-01-06 | 2026-01-12 | AWS Account Access & IAM Permissions Confirmed | Cloud Engineer | Not Started
Phase 1 | Cognito User Pool Design & Post-Confirmation Lambda | 5 days | 2026-01-13 | 2026-01-19 | Architecture Design Document & ADRs | Cloud Engineer | Not Started
Phase 1 | CTO Sign-Off on Cognito User Pool | 1 day | 2026-01-20 | 2026-01-20 | Cognito User Pool Design & Post-Confirmation Lambda | Solution Architect | Not Started
Phase 1 | DynamoDB Schema & Quota Enforcement Tables | 5 days | 2026-01-13 | 2026-01-19 | Architecture Design Document & ADRs | Cloud Engineer | Not Started
Phase 1 | API Gateway HTTP API v2 & Lambda Route Stubs | 5 days | 2026-01-20 | 2026-01-26 | DynamoDB Schema & Quota Enforcement Tables | Cloud Engineer | Not Started
Phase 1 | Secrets Manager & KMS Key Policy Setup | 3 days | 2026-01-20 | 2026-01-22 | AWS Landing Zone & VPC Provisioning | Security Engineer | Not Started
Phase 1 | CloudTrail & GuardDuty Enablement | 2 days | 2026-01-21 | 2026-01-22 | AWS Landing Zone & VPC Provisioning | Security Engineer | Not Started
Phase 1 | CLI Authentication Subcommands (login/logout/refresh) | 5 days | 2026-01-20 | 2026-01-26 | Cognito User Pool Design & Post-Confirmation Lambda | Solutions Engineer | Not Started
Phase 1 | Foundation Infrastructure Acceptance Report | 2 days | 2026-01-27 | 2026-01-28 | API Gateway HTTP API v2 & Lambda Route Stubs; CTO Sign-Off on Cognito User Pool | Project Manager | Not Started
Phase 2 | Docker Image Build & ECR Repository Setup | 5 days | 2026-02-02 | 2026-02-06 | Foundation Infrastructure Acceptance Report | DevOps Engineer | Not Started
Phase 2 | Strands Agent Graph Design & Inter-Agent Contracts | 5 days | 2026-02-02 | 2026-02-06 | Foundation Infrastructure Acceptance Report | Solution Architect | Not Started
Phase 2 | AgentCore Runtime Registration — All 5 Agents | 5 days | 2026-02-09 | 2026-02-13 | Docker Image Build & ECR Repository Setup; Strands Agent Graph Design & Inter-Agent Contracts | Cloud Engineer | Not Started
Phase 2 | eof-tools Container Image Build & Validation | 5 days | 2026-02-09 | 2026-02-13 | Docker Image Build & ECR Repository Setup | DevOps Engineer | Not Started
Phase 2 | Step Functions Orchestration State Machine | 5 days | 2026-02-16 | 2026-02-20 | AgentCore Runtime Registration — All 5 Agents | Solution Architect | Not Started
Phase 2 | Bedrock Model Integration & Prompt Templates | 5 days | 2026-02-09 | 2026-02-13 | AgentCore Runtime Registration — All 5 Agents | ML/AI Engineer | Not Started
Phase 2 | Complete CLI Package — All 14 Subcommands | 10 days | 2026-02-16 | 2026-02-27 | CLI Authentication Subcommands (login/logout/refresh) | Solutions Engineer | Not Started
Phase 2 | All 11 Lambda API Routes — JWT-Protected & Quota-Enforced | 10 days | 2026-02-16 | 2026-02-27 | Bedrock Model Integration & Prompt Templates | Solutions Engineer | Not Started
Phase 2 | GitHub PAT Integration & Commit Workflow | 5 days | 2026-02-23 | 2026-02-27 | All 11 Lambda API Routes — JWT-Protected & Quota-Enforced | Solutions Engineer | Not Started
Phase 2 | CI/CD Pipeline — CodePipeline & CodeBuild | 5 days | 2026-02-23 | 2026-02-27 | AgentCore Runtime Registration — All 5 Agents | DevOps Engineer | Not Started
Phase 2 | Terraform IaC Full Platform Modules | 10 days | 2026-02-16 | 2026-02-27 | Foundation Infrastructure Acceptance Report | DevOps Engineer | Not Started
Phase 2 | Agent Integration Milestone Report | 2 days | 2026-03-02 | 2026-03-03 | GitHub PAT Integration & Commit Workflow; Complete CLI Package — All 14 Subcommands | Project Manager | Not Started
Phase 3 | Test Plan Development | 3 days | 2026-03-09 | 2026-03-11 | Agent Integration Milestone Report | QA Engineer | Not Started
Phase 3 | Token Usage Instrumentation — CLI & Admin API | 3 days | 2026-03-09 | 2026-03-11 | Agent Integration Milestone Report | ML/AI Engineer | Not Started
Phase 3 | Unit Test Suite — Greater Than 80% Coverage | 5 days | 2026-03-09 | 2026-03-13 | Test Plan Development | Solutions Engineer | Not Started
Phase 3 | Integration Tests — All 12 Artifact Types | 5 days | 2026-03-09 | 2026-03-13 | Test Plan Development | QA Engineer | Not Started
Phase 3 | Load Testing — 200 Solutions/Month Throughput | 3 days | 2026-03-16 | 2026-03-18 | Unit Test Suite — Greater Than 80% Coverage; Integration Tests — All 12 Artifact Types | Solutions Engineer | Not Started
Phase 3 | Security Testing — IAM & OWASP API Top 10 | 5 days | 2026-03-09 | 2026-03-13 | Test Plan Development | Security Engineer | Not Started
Phase 3 | UAT Coordination & Sign-Off | 3 days | 2026-03-16 | 2026-03-18 | Integration Tests — All 12 Artifact Types; Security Testing — IAM & OWASP API Top 10 | QA Engineer | Not Started
Phase 3 | Green CloudWatch Metrics Baseline Dashboard | 2 days | 2026-03-19 | 2026-03-20 | Load Testing — 200 Solutions/Month Throughput | DevOps Engineer | Not Started
Phase 3 | Production Deployment — Full Platform in us-west-2 | 1 day | 2026-03-23 | 2026-03-23 | UAT Coordination & Sign-Off; Green CloudWatch Metrics Baseline Dashboard | Cloud Engineer | Not Started
Phase 3 | Operational Runbooks Delivery | 3 days | 2026-03-19 | 2026-03-23 | UAT Coordination & Sign-Off | Solutions Engineer | Not Started
Phase 3 | As-Built Documentation Package | 5 days | 2026-03-16 | 2026-03-20 | Agent Integration Milestone Report | Solution Architect | Not Started
Phase 3 | Knowledge Transfer — Engineering Deep-Dive | 1 day | 2026-03-24 | 2026-03-24 | Production Deployment — Full Platform in us-west-2 | Solution Architect | Not Started
Phase 3 | Knowledge Transfer — Pre-Sales Workflow Training | 1 day | 2026-03-25 | 2026-03-25 | Knowledge Transfer — Engineering Deep-Dive | Project Manager | Not Started
Phase 3 | Executive Sponsor Demonstration | 1 day | 2026-04-30 | 2026-04-30 | Knowledge Transfer — Pre-Sales Workflow Training | Project Manager | Not Started
Hypercare | Hypercare Support — P1/P2 Incident Response | 40 days | 2026-03-26 | 2026-05-21 | Production Deployment — Full Platform in us-west-2 | Cloud Engineer | Not Started
Hypercare | Optimisation Recommendations & Phase 2 Roadmap | 5 days | 2026-05-14 | 2026-05-21 | Hypercare Support — P1/P2 Incident Response | Solution Architect | Not Started
Hypercare | Project Closeout & BAU Handover | 1 day | 2026-05-22 | 2026-05-22 | Optimisation Recommendations & Phase 2 Roadmap | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Phase | Success Criteria | Owner | Status | Actual Date
MS-001 | Kickoff Complete | 2026-01-05 | Phase 1 | Stakeholder alignment achieved; project charter acknowledged; CTO briefing scheduled; architecture design underway | Project Manager | Not Started
MS-002 | Foundation Live | 2026-01-28 | Phase 1 | Cognito User Pool live; API Gateway provisioned; DynamoDB tables operational; S3 and IAM baseline accepted; CTO sign-off on Cognito obtained | Cloud Engineer | Not Started
MS-003 | First End-to-End Generation | 2026-02-13 | Phase 2 | At least one complete twelve-artifact solution bundle generated and validated through all five Bedrock AgentCore agents without manual intervention | Solution Architect | Not Started
MS-004 | Agent Integration Complete | 2026-03-03 | Phase 2 | All five agents registered in AgentCore Runtime; all fourteen CLI subcommands operational; all eleven API routes JWT-protected; eof-tools converters for all twelve artifact types validated | Solution Architect | Not Started
MS-005 | UAT Sign-Off | 2026-03-18 | Phase 3 | UAT completed and formally signed off by Marcus Patel, Daniel Park, and CTO; all P1 and P2 defects resolved | QA Engineer | Not Started
MS-006 | Green Baseline | 2026-03-20 | Phase 3 | CloudWatch metrics baseline certified green; per-solution Bedrock token spend at or below $5; P95 end-to-end latency under 60 minutes confirmed under 200 solutions/month load | DevOps Engineer | Not Started
MS-007 | Go-Live | 2026-03-23 | Phase 3 | Full platform deployed to production us-west-2; GitHub PAT integration live; CLI published to PyPI; all deliverables accepted by Marcus Patel and Daniel Park; CTO production sign-off obtained | Project Manager | Not Started
MS-008 | Executive Demo | 2026-04-30 | Phase 3 | Live demonstration to Sarah Lin (CRO) confirming 90% effort reduction and end-to-end generation under 60 minutes; executive sponsor presentation delivered and acknowledged | Project Manager | Not Started
MS-009 | Hypercare End | 2026-05-22 | Hypercare | Eight-week hypercare period concluded; Optimisation Recommendations and Phase 2 Roadmap delivered and accepted; full BAU handover to PREDICTif operations team complete | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | Vendor PM | Vendor Arch | Vendor Eng | Vendor QA | Client IT | Client PM
Project Kickoff & Stakeholder Alignment | R | C | I | I | C | C
Current State Assessment & Gap Analysis | I | R | C | I | C | C
Architecture Design Document & ADRs | C | R | C | I | C | I
AWS Landing Zone & IAM Baseline | I | A | R | I | C | I
Cognito User Pool Design & CTO Sign-Off | C | A | R | I | C | C
DynamoDB Schema & Quota Enforcement | I | A | R | I | C | I
API Gateway & Lambda Route Development | I | C | R | C | I | I
Secrets Manager & KMS Configuration | C | C | R | C | C | I
CloudTrail & GuardDuty Enablement | C | C | R | I | C | I
CLI Development — All 14 Subcommands | I | C | R | C | I | I
Strands Agent Graph Design | C | R | C | I | I | I
AgentCore Runtime Registration — 5 Agents | I | A | R | C | I | I
eof-tools Container Image Build & Validation | I | C | R | C | I | I
Step Functions Orchestration State Machine | I | A | R | C | I | I
Bedrock Model Integration & Retry Logic | I | A | R | C | I | I
GitHub PAT Integration & Commit Workflow | I | C | R | C | I | C
CI/CD Pipeline — CodePipeline & CodeBuild | I | C | R | C | I | I
Terraform IaC Full Platform Modules | I | C | R | C | I | I
Security Hardening & Secrets Manager | C | C | R | C | C | I
Token Usage Instrumentation | I | A | R | C | I | I
CloudWatch Dashboards & Alarms | I | C | R | C | I | I
Test Plan Development | C | C | C | R | I | C
Unit & Integration Testing | I | C | R | A | I | I
Load & Performance Testing | I | C | R | A | I | I
Security Testing — IAM & OWASP API Top 10 | C | C | R | A | C | I
UAT Coordination & Sign-Off | A | C | C | R | R | A
Production Deployment | A | C | R | C | C | C
Operational Runbooks Development | C | C | R | I | C | A
Knowledge Transfer — Engineering Deep-Dive | C | R | C | I | R | C
Knowledge Transfer — Pre-Sales Workflow | A | C | C | I | I | R
Executive Sponsor Demonstration | A | R | C | I | I | C
Hypercare Support | A | C | R | C | I | C
Project Closeout & Phase 2 Roadmap | R | C | I | I | I | C
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Legend:
R | Responsible - Does the work
A | Accountable - Ultimate ownership
C | Consulted - Provides input
I | Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders; Amatra full delivery team; Marcus Patel; Sarah Lin; Daniel Park; CTO; Client IT Lead | Launch project; align on scope, RACI, governance, and communication cadence; confirm AWS account access and CTO briefing schedule | Project Manager | 2026-01-05 09:00 PT
Weekly Status Call | Weekly | Marcus Patel; Daniel Park; Project Manager; Vendor team leads | Review progress against plan; surface blockers and decisions; update RAID log; confirm next-week deliverables | Project Manager | Mondays 10:00 PT
Architecture Review Workshop | Once — Week 3 | Marcus Patel; CTO; Solution Architect; Cloud Engineer | Review and obtain CTO sign-off on Architecture Design Document, Cognito User Pool design, and ADRs | Solution Architect | 2026-01-20 10:00 PT (3 hours)
Phase 1 Gate Review | Once — End of Week 4 | Marcus Patel; Daniel Park; Project Manager | Review Foundation Infrastructure Acceptance Report; confirm Phase 1 completion criteria; approve Phase 2 kickoff | Project Manager | 2026-01-28 10:00 PT (1 hour)
Phase 2 Integration Checkpoint | Bi-weekly during Phase 2 | Marcus Patel; Solution Architect; Cloud Engineer; ML/AI Engineer | Review agent registration progress, eof-tools validation status, and integration risks; adjust sprint priorities | Solution Architect | Wednesdays 10:00 PT (Weeks 5–9)
Phase 2 Gate Review | Once — End of Week 9 | Marcus Patel; Daniel Park; Project Manager | Review Agent Integration Milestone Report; confirm all five agents live and end-to-end generation validated; approve Phase 3 kickoff | Project Manager | 2026-03-03 10:00 PT (1 hour)
UAT Session | Once — Week 11 | Marcus Patel; Daniel Park; CTO; QA Engineer; Project Manager | Execute UAT scenarios across pre-sales and delivery artifact types; review defect log; obtain formal UAT sign-off | QA Engineer | 2026-03-16 09:00 PT (4 hours)
Go-Live Readiness Review | Once — Week 12 | Marcus Patel; CTO; Sarah Lin; Project Manager; DevOps Engineer | Review green CloudWatch baseline, security attestation, and go-live readiness checklist; obtain CTO and executive sign-off for production deployment | Project Manager | 2026-03-20 10:00 PT (1 hour)
Executive Sponsor Demonstration | Once — End of April 2026 | Sarah Lin (CRO); Marcus Patel; Daniel Park; Project Manager; Solution Architect | Deliver live end-to-end platform demonstration confirming 90% effort reduction and sub-60-minute generation; present Phase 2 roadmap | Project Manager | 2026-04-30 10:00 PT (2 hours)
Hypercare Incident Escalation | As required | Marcus Patel; Cloud Engineer; Project Manager | Notify and resolve P1/P2 incidents during eight-week hypercare period; confirm root cause and remediation steps | Cloud Engineer | Within 1 business hour of P1 detection
Monthly Executive Status Report | Monthly during Hypercare | Sarah Lin; Marcus Patel; Project Manager | Report platform usage metrics, token spend vs budget, open defects, and Phase 2 readiness status | Project Manager | First Monday of each month
Project Closeout | Once — Week 20 | Marcus Patel; Daniel Park; CTO; Sarah Lin; Project Manager | Formal project closure; confirm BAU handover; accept Optimisation Recommendations and Phase 2 Roadmap; conclude hypercare | Project Manager | 2026-05-22 10:00 PT (1 hour)